## Q6 Current Contruction Projects
Record | Project Manager | Project Title | PFA | Project Number | Project # | PTS_PRJ_TMA | Status | PTS_PRJ_DESIGNER | PTS_PRJ_CONTRACT | Final Cost | Petition to Close | Fiscal Year | Actual Budget | Plant Fund Closed | Date Established | Planned Budget | Deferred Maintenance | Customer Funded | Planner | Combo266 | Combo268 | Estimate Completed by | Date Established | Balance | Fiscal Year
2174 | Azar | Expansion 3rd Floor Jeffress Center | 772172 | 565-287125 | 565 | 287125 | Under Construction |  |  | 0 |  | 2016 | 350000 |  | 2016-08-05 | 350000 | FALSE | TRUE | Azar |  |  | Other (Design Consultant) | 2016-08-08 | 298787.69 | 2016
2120 | *UNASSIGNED | Diesel Fuel Tank Replacement | 772171 | 066-278595 | 066 | 278595 | Study |  |  | 0 |  | 2016 | 150000 |  |  | 150000 | TRUE | FALSE | Albaari |  |  | Other (Design Consultant) | 2016-08-08 | 150000 | 2016
2152 | Vandenbussche | Football Locker Room Expansion | 772142 | 078-279021 | 078 | 279021 | Substantially Complete |  |  | 0 |  | 2016 | 499990 |  | 2016-06-23 | 499990 | FALSE | TRUE | Flintoff | Barton Malow L.S. Brinker |  | Other (Design Consultant) | 2016-05-17 | 1099.07 | 2016
2145 | Edwards | Campus Housing Camera Project | 772139 | 565-287125 | 999 | 283361 | Under Construction |  |  | 0 | 2016-12-23 | 2016 | 310600 |  | 2016-04-29 | 310600 | FALSE | TRUE | Albaari | D&CS | Suntel | Other (Design Consultant) | 2016-05-02 | 210601 | 2016
2134 | Gibbons | Tierney Alumni House IT infrastructure | 772132 | 066-278595 | 505 | 281665 | Under Construction |  |  | 0 | 2017-02-16 | 2016 | 308000 |  |  |  | FALSE | FALSE | Padilla | Hamilton Anderson Associates | Integrity Building Group dba: studiozONE, Inc. | Other (Design Consultant) | 2016-03-29 | 75684.16 | 2016
2130 | Ahern | Chatsworth Carpet Replacement | 772129 | 078-279021 | 136 | 279909 | Substantially Complete |  |  | 0 | 2016-11-03 | 2016 | 81760 |  | 2016-02-11 | 71760 | FALSE | TRUE |  |  | Detroit Interiors | Other (Design Consultant) | 2016-02-12 | 27930 | 2016
2125 | Moore | Towers Cafe Floor Polishing | 772124 | 999-283361 | 127 | 278583 | Construction Complete |  |  | 0 |  | 2016 | 82800 |  | 2016-01-22 | 82800 | FALSE | TRUE | Flintoff |  |  | Other (Design Consultant) | 2016-01-22 | 39163.92 | 2016
2078 | Alhyari | Renovation of Geology Labs for HF Fume Hood | 772106 | 505-281665 | 003 | 271986 | Under Construction |  |  | 0 | 2017-06-15 | 2016 | 315000 |  | 2015-12-10 | 315000 | FALSE | TRUE | Flintoff | SSOE, Inc. | Detroit Contracting Inc. | Other (Design Consultant) | 2015-12-10 | 49950 | 2016
2100 | Ahern | New Anthony Wayne Housing | 772104 | 136-279909 | 999 | 276855 | Planned |  |  | 0 |  | 2016 | 76000 |  | 2015-12-02 | 76000 | FALSE | TRUE | Azar | iDesign |  | Other (Design Consultant) | 2015-12-03 | 2475 | 2016
2181 | *UNASSIGNED | Geology Rock Collection Relocation | 772180 | 127-278583 | 217 | 287843 | Planned |  |  | 0 | 2017-04-07 | 2016 | 165000 |  | 2016-08-31 | 165000 | FALSE | FALSE | Flintoff | NORR, LLC dba: Giffels Holdings America Inc |  | D&CS | 2016-09-06 | 155720 | 2016
2178 | Brazen | Provost Office Renovation 2016 | 772177 | 003-271986 | 130 | 287822 | Contract in Progress - Construction |  |  | 0 | 2017-04-11 | 2016 | 36630 |  |  | 36630 | FALSE | TRUE | Padilla | D&CS | T&M | D&CS | 2016-08-11 | 6918.75 | 2016
2179 | *UNASSIGNED | Digital Arts Flooring | 772176 | 999-276855 | 001 | 279876 | In Design |  |  | 0 |  | 2016 | 44705 |  | 2016-08-10 |  | FALSE | TRUE | Flintoff |  |  | D&CS | 2016-08-10 | 44705 | 2016
2180 | Alhyari | Art Rooms 250 & 254 Renovation | 772175 | 217-287843 | 040 | 284897 | In Design |  |  | 0 |  | 2016 | 75000 |  | 2016-08-10 | 75000 | FALSE | TRUE | Flintoff | NORR, LLC dba: Giffels Holdings America Inc |  | D&CS | 2016-08-10 | 75000 | 2016
2176 | Moore | Purdy Second Floor Carpet | 772173 | 130-287822 | 026 | 285663 | In Design |  |  | 0 |  | 2016 | 69965 |  |  | 69965 | FALSE | TRUE | Padilla |  |  | D&CS | 2016-08-08 | 69965 | 2016
2150 | *UNASSIGNED | Manoogian Room 518 Improvements | 772166 | 001-279876 | 155 | 280039 | In Design |  |  | 0 | 2017-04-17 | 2016 | 36890 |  |  | 36890 | FALSE | TRUE | Padilla | Stucky Vitale Architects |  | D&CS | 2016-07-28 | 31048.9 | 2016
2165 | *UNASSIGNED | Chemistry Lab 150 Renovation | 772164 | 040-284897 | 007 | 286023 | Planned |  |  | 0 | 2017-07-28 | 2016 | 25000 |  | 2016-07-20 | 25000 | FALSE | TRUE | Flintoff | iDesign |  | D&CS | 2016-07-22 | 11022 | 2016
2166 | Moore | UGL General Painting Improvements 2016 | 772157 | 026-285663 | 096 | 285392 | Under Construction |  |  | 0 |  | 2016 | 35000 |  | 2016-06-30 | 35000 | FALSE | TRUE |  | D&CS |  | D&CS | 2016-07-01 | 10500 | 2016
2156 | Padilla | SCB 5th and 7th Floor Furniture | 772155 | 155-280039 | 034 | 284898 | In Design |  |  | 0 |  | 2016 | 41490.53 |  | 2016-06-30 | 41490.53 | FALSE | TRUE | Padilla |  |  | D&CS | 2016-07-01 | 13576.65 | 2016
2164 | Padilla | Applebaum Study Spaces | 772154 | 007-286023 | 603 | 280820 | In Design |  |  | 0 |  | 2016 | 35000 |  | 2016-06-30 | 35000 | FALSE | TRUE | Padilla | D&CS | Krueger International, Inc. | D&CS | 2016-07-01 | 12847.92 | 2016
2163 | Alhyari | Old Main - Theatre and Dance Room Refresh | 772153 | 096-285392 | 001 | 278242 | Under Construction |  |  | 0 |  | 2016 | 59160 |  |  | 59160 | FALSE | TRUE | Flintoff | Berbiglia Associates, Inc. |  | D&CS | 2016-06-24 | 28423.95 | 2016
2161 | Moore | Suite 1600 Carpet and Paint | 772152 | 034-284898 | 096 | 282771 | Contract in Progress - Construction |  |  | 0 |  | 2016 | 27560 |  | 2016-06-24 | 27560 | FALSE | TRUE | Padilla |  |  | D&CS | 2016-06-24 | 26080 | 2016
2160 | *UNASSIGNED | Scott Hall - Human Crematory Repair | 772149 | 603-280820 | 612 | 278558 | Study |  |  | 0 |  | 2016 | 22000 |  | 2016-06-23 | 22000 | TRUE | TRUE | Albaari | Multiple Vendors |  | D&CS | 2016-06-24 | 7433 | 2016
2155 | Camilleri | Scott Hall First Floor Refresh 2016 | 772148 | 001-278242 | 612 | 284323 | In Design |  |  | 0 | 2017-09-18 | 2016 | 269000 |  | 2016-06-08 | 25000 | FALSE | TRUE | Flintoff | Fishbeck, Thompson, Carr & Huber, Inc. |  | D&CS | 2016-06-08 | 202300 | 2016
2129 | Alhyari | Cohn Building East Stairwell Window Sealant Analysis | 772144 | 096-282771 | 048 | 278478 | Planned |  |  | 0 | 2017-04-03 | 2016 | 50000 |  | 2016-05-24 | 50000 | TRUE | FALSE | Albaari | Fishbeck, Thompson, Carr & Huber, Inc. |  | D&CS | 2016-05-26 | 22540 | 2016
2147 | Padilla | EACHPS Room 2129 Renovation | 772141 | 612-278558 | 603 | 282200 | Under Construction |  |  | 0 | 2017-03-14 | 2016 | 33460 |  | 2016-05-13 | 33460 | FALSE | TRUE | Brazen |  |  | D&CS | 2016-05-16 | 8364.17 | 2016
2149 | Ahern | Law School Building Media Wall | 772140 | 612-284323 | 049 | 279772 | Substantially Complete |  |  | 0 | 2017-02-19 | 2016 | 100000 |  | 2016-05-13 | 100000 | FALSE | TRUE | Azar | D&CS |  | D&CS | 2016-05-16 | 12610.09 | 2016
2144 | Camilleri | SCB Loading Dock Leak Repairs | 772138 | 048-278478 | 034 | 282276 | Out for Bid |  |  | 0 | 2017-03-24 | 2016 | 204000 |  | 2016-04-29 | 204000 | FALSE | TRUE | Albaari | Desai/Nasr Consulting Engineers Inc. |  | D&CS | 2016-05-02 | 188042.9 | 2016
2146 | Brazen | 4th Floor AAB Reconfiguration 2016 | 772137 | 603-282200 | 062 | 283328 | Under Construction |  |  | 0 |  | 2016 | 93840 |  | 2016-04-29 | 98840 | FALSE | TRUE | Brazen | D&CS | T & M | D&CS | 2016-05-02 | 49011.25 | 2016
2142 | Gibbons | FAB 4th Floor Renovations 2016 | 772136 | 049-279772 | 130 | 283192 | Under Construction |  |  | 0 | 2017-02-15 | 2016 | 58000 |  | 2016-04-25 |  | FALSE | TRUE | Brazen | D&CS | T&M | D&CS | 2016-05-02 | -1434.1 | 2016
2136 | Moore | One Card Office Renovation | 772131 | 034-282276 | 082 | 278485 | Under Construction |  |  | 0 | 2017-03-26 | 2016 | 57480 |  | 2016-03-18 | 38150 | FALSE | TRUE | Rooks |  |  | D&CS | 2016-03-23 | 4694.92 | 2016
2135 | Gibbons | Tierney Parking Lot | 772130 | 062-283328 | 505 | 281674 | Out for Bid |  |  | 0 | 2017-03-15 | 2016 | 225000 |  | 2016-03-23 | 225000 | FALSE | TRUE | Padilla | D&CS |  | D&CS | 2016-03-23 | 220000 | 2016
2133 | Vandenbussche | RHA Office | 772128 | 130-283192 | 115 | 279543 | Under Construction |  |  | 0 | 2016-11-28 | 2016 | 80000 |  | 2016-02-11 | 80000 | FALSE | TRUE | Rooks | NSA Architects, Engineers, Planners dba: Nordstrom-Samson & Associates Inc. | Allied Building Services Company | D&CS | 2016-02-12 | 2141.85 | 2016
2102 | Moore | Grad School Relocation/Expansion to 11th Floor | 772127 | 082-278485 | 071 | 276967 | Under Construction |  |  | 0 | 2017-04-15 | 2016 | 202830 |  | 2016-02-11 | 202830 | FALSE | TRUE | Padilla | NSA Architects, Engineers, Planners dba: Nordstrom-Samson & Associates Inc. |  | D&CS | 2016-02-12 | 26311.8 | 2016
2127 | Brazen | Jiu Jitsu Club Renovation | 772126 | 505-281674 | 080 | 279704 | Contract in Progress - Construction |  |  | 0 | 2016-01-15 | 2016 | 35000 |  | 2016-02-05 | 35000 | FALSE | TRUE | Brazen | D&CS |  | D&CS | 2016-02-09 | 16095 | 2016
2105 | Ahern | Law Journal Office Relocation | 772111 | 115-279543 | 046 | 274608 | Substantially Complete |  |  | 0 | 2017-02-01 | 2016 | 57000 |  | 2015-12-21 | 57000 | FALSE | TRUE | Rooks | D&CS |  | D&CS | 2015-12-21 | 2000.56 | 2016
2099 | *UNASSIGNED | Parking Structure #1 Elevator Pit Sump Pump Backup & Alarm | 772105 | 071-276967 | 051 | 274514 | On Hold |  |  | 0 | 2017-05-01 | 2016 | 30000 |  | 2015-12-02 | 30000 | FALSE | TRUE | Albaari | SSOE, Inc. |  | D&CS | 2015-12-03 | 2195 | 2016
2098 | Alhyari | Blue Lights - Athletic Campus | 772101 | 080-279704 | 080 | 275368 | Construction Complete |  |  | 0 | 2016-09-19 | 2016 | 130000 |  | 2015-11-13 | 130000 | FALSE | TRUE | Azar | D&CS | Compass Technology Solutions LLC | D&CS | 2015-11-19 | 12586.9 | 2016
2096 | Vandenbussche | Parking Lot #34 | 772100 | 046-274608 | 999 | 274515 | Construction Complete |  |  | 0 | 2016-10-14 | 2016 | 175000 |  | 2015-11-13 | 175000 | FALSE | TRUE | Albaari | D&CS | Asphalt Specialists, Inc. | D&CS | 2015-11-13 | 158636.05 | 2016
2182 | Edwards | Life Science: DTE-PLD Electrical Infrastructure Conversion | 772179 | 051-274514 | 006 | 285977 | In Design |  |  | 0 |  | 2016 | 50000 |  |  | 50000 | FALSE | FALSE | Edwards | Hamilton Anderson Associates |  |  | 2016-08-30 | 50000 | 2016
2183 | Camilleri | SOM Digital Signage | 772178 | 080-275368 | 612 | 287569 | In Design |  |  | 0 |  | 2016 | 20000 |  | 2016-08-15 | 20000 | FALSE | TRUE | Flintoff |  | MICCO |  | 2016-08-16 | 6166.86 | 2016
2175 | Alhyari | Chemistry Roof Screen Wall Replacement | 772168 | 007-287391 | 007 | 287391 | In Design |  |  | 0 | 2018-01-08 | 2016 | 150000 |  | 2016-08-04 | 150000 | TRUE | FALSE | Albaari | Harley Ellis Devereaux |  |  | 2016-08-08 | 95951 | 2016
2171 | Edwards | McGregor: DTE-PLD Electrical Infrastructure Conversion | 772161 | 043-286005 | 043 | 286005 | In Design |  |  | 0 |  | 2016 | 80000 |  | 2016-07-19 | 80000 | FALSE | FALSE | Edwards | Hamilton Anderson Associates |  |  | 2016-07-21 | 35169.16 | 2016
2170 | Edwards | Community Arts: DTE-PLD Electrical Infrastructure Conversion | 772160 | 039-285978 | 039 | 285978 | In Design |  |  | 0 |  | 2016 | 80000 |  | 2016-07-19 | 80000 | FALSE | FALSE | Edwards | Hamilton Anderson Associates |  |  | 2016-07-21 | 39569.16 | 2016
2169 | Alhyari | Reuther Library Emergency RTU Replacement | 772159 | #REF! | 036 | 286594 | Under Construction |  |  | 0 | 2016-04-08 | 2016 | 130000 |  | 2016-07-19 | 130000 | TRUE | FALSE | Pecic |  | Temperature Services, Inc. |  | 2016-07-21 | 11210 | 2016
2162 | Edwards | Chemistry: DTE-PLD Electrical Infrastructure Conversion | 772151 | 007-285283 | 007 | 285283 | In Design |  |  | 0 |  | 2016 | 25000 |  | 2016-06-23 | 25000 | FALSE | FALSE | Edwards | Hamilton Anderson Associates |  |  | 2016-06-24 | -1080 | 2016
2154 | Edwards | State Hall: DTE-PLD Electrical Infrastructure Conversion | 772147 | 016-284939 | 016 | 284939 | In Design |  |  | 0 |  | 2016 | 90000 |  | 2016-06-08 | 90000 | FALSE | FALSE | Edwards | Hamilton Anderson Associates |  |  | 2016-06-08 | 47195.27 | 2016
2128 | Alhyari | MHRFC South Elevation Glazing Sealant | 772143 | 025-279871 | 025 | 279871 | Planned |  |  | 0 |  | 2016 | 100000 |  | 2016-05-24 | 100000 | TRUE | FALSE | Albaari |  |  |  | 2016-05-25 | 99827.53 | 2016
2141 | Kamalia | Precast Panel Repair | 772135 | 127-282845 | 127 | 282845 | In Design |  |  | 0 | 2018-01-22 | 2016 | 20000 |  |  | 20000 | FALSE | TRUE | Azar | Hamilton Anderson Associates | T & M |  | 2016-05-02 | 780 | 2016
2138 | Camilleri | Chatsworth Masonry Veneer Inspection and Repair | 772134 | 608-261912 | 136 | 282841 | In Design |  |  | 0 |  | 2016 | 35000 |  | 2016-04-20 | 35000 | FALSE | TRUE | Azar | Carl Walker, Inc. |  |  | 2016-05-02 | 12320 | 2016
2126 | Kamalia | Medical Education Commons - Shiffman Library: Prasad Collaboration Space | 772125 | 608-261912 | 608 | 261912 | Contract in Progress - Construction |  |  | 0 | 2017-04-30 | 2016 | 100000 |  | 2016-01-26 | 100000 | FALSE | TRUE | Azar | Stucky Vitale Architects |  |  | 2016-01-29 | 83100 | 2016
2124 | Alhyari | IBio Proteomics and RadioChemsitry Facilities | 772123 | 127-282845 | 590 | 277899 | Under Construction |  |  | 0 | 2017-05-20 | 2016 | 300000 |  | 2016-01-22 | 50000 | FALSE | TRUE | Flintoff | Harley Ellis Devereaux | Detroit Contracting Inc. |  | 2016-01-22 | 33100 | 2016
2119 | Camilleri | Thompson Home New Student Housing | 772119 | #REF! | 504 | 277444 | Under Construction |  |  | 0 | 2017-10-06 | 2016 | 350000 |  | 2016-01-20 | 350000 | FALSE | TRUE | Padilla | Hamilton Anderson Associates |  |  | 2016-01-22 | 8527.78 | 2016
2117 | Alhyari | Parking Structure #5 2016 Renovations | 772117 | #REF! | 045 | 278270 | Substantially Complete |  |  | 0 | 2017-01-19 | 2016 | 495000 |  | 2016-01-20 | 473000 | FALSE | TRUE | Ahern | Walker Parking Consultants dba: Walker Restoration | RAM Construction Svcs of Michigan Inc |  | 2016-01-21 | 44117.77 | 2016
2114 | Alhyari | Parking Structure #4 2016 Renovations | 772115 | 504-277444 | 613 | 278269 | Construction Complete |  |  | 0 | 2017-01-26 | 2016 | 59000 |  | 2016-01-20 | 50000 | FALSE | TRUE | Ahern | Walker Parking Consultants dba: Walker Restoration | RAM Construction Svcs of Michigan Inc |  | 2016-01-21 | 8095.55 | 2016
2112 | Edwards | Parking Structure #3 2016 Renovations | 772114 | #REF! | 498 | 278268 | Petition to Close |  |  | 0 | 2017-01-26 | 2016 | 76000 |  | 2016-01-20 | 50000 | FALSE | TRUE | Ahern | Walker Parking Consultants dba: Walker Restoration | ram |  | 2016-01-21 | 2530.96 | 2016
2113 | Edwards | Parking Structure #2 2016 Renovations | 772113 | 045-278270 | 056 | 278267 | Substantially Complete |  |  | 0 | 2017-01-26 | 2016 | 981000 |  | 2016-01-20 | 1225000 | FALSE | TRUE | Ahern | Walker Parking Consultants dba: Walker Restoration | ram |  | 2016-01-21 | 81045.01 | 2016
2111 | Camilleri | Parking Structure #1 2016 Renovations | 772112 | 613-278269 | 051 | 278266 | Substantially Complete |  |  | 0 | 2017-01-26 | 2016 | 1575000 |  | 2016-01-20 | 1575000 | FALSE | TRUE | Ahern | Walker Parking Consultants dba: Walker Restoration |  |  | 2016-01-21 | 109807.5 | 2016
2103 | Camilleri | North Canopy Repairs | 772108 | 056-278267 | 034 | 274959 | Construction Complete |  |  | 0 | 2016-11-17 | 2016 | 34800 |  | 2015-12-17 | 34800 | FALSE | TRUE | Camilleri |  |  |  | 2015-12-18 | 807.08 | 2016
2057 | Gibbons | Freer Landscape Project | 772079 | #REF! | 511 | 268351 | Contract in Progress - Construction |  |  | 0 | 2016-05-15 | 2015 | 279177.33 |  | 2015-08-05 | 279177 | FALSE | TRUE | UNASSIGNED | D&CS | Brencal Contractors | Other (Design Consultant) | 2015-08-06 | 128291.16 | 2015
2053 | Kamalia | Computing Service Center Breakroom and Hallway Improvements | 772065 | #REF! | 193 | 258618 | Construction Complete |  |  | 0 | 2016-09-06 | 2015 | 256800 |  | 2015-06-11 | 25000 | FALSE | TRUE | Padilla | Stucky Vitale Architects | Advanced Building Group LLC | Other (Design Consultant) | 2015-06-11 | 5518.02 | 2015
2051 | Alhyari | ELJ Gallery Curtain wall and Foundation | 772064 | #REF! | 001 | 264807 | Under Construction |  |  | 0 | 2017-03-28 | 2015 | 300500 |  | 2015-06-09 | 304366 | TRUE | FALSE | Albaari | SmithGroup Inc. | Brix Corporation | Other (Design Consultant) | 2015-06-09 | 25523.9 | 2015
2044 | Ahern | Scott Hall HVAC Study | 772058 | 511-268351 | 612 | 267465 | Other (See Comments) |  |  | 0 |  | 2015 | 55000 |  | 2015-05-26 | 55000 | FALSE | TRUE | Flintoff | Fishbeck, Thompson, Carr & Huber, Inc. |  | Other (Design Consultant) | 2015-05-26 | 500 | 2015
2031 | Camilleri | SCB basement and first floor toilet room tile replacement | 772049 | 193-258618 | 034 | 265000 | Construction Complete |  |  | 0 | 2016-03-30 | 2015 | 187000 |  | 2015-04-30 | 187000 | FALSE | TRUE | Azar | Neumann Smith & Associates | Turner Construction Company | Other (Design Consultant) | 2015-04-24 | -94.92 | 2015
2007 | Camilleri | Student Center Building - 5th and 7th Floor Renovation | 772045 | 001-264807 | 034 | 261806 | Substantially Complete | Newmann Smith |  | 0 | 2017-01-14 | 2015 | 3855000 |  |  | 75000 | FALSE | FALSE | Azar | Neumann Smith & Associates |  | Other (Design Consultant) | 2015-04-30 | 262566.38 | 2015
2025 | Edwards | McGregor AV Upgrades and Renovation | 772039 | 612-267465 | 043 | 261016 | In Design |  |  | 0 |  | 2015 | 57000 |  |  | 57000 | FALSE | TRUE | Azar | Acoustics By Design |  | Other (Design Consultant) |  | 2000 | 2015
1996 | Paquette | Engineering Machine Shop Move | 772032 | 034-265000 | 090 | 258510 | Construction Complete |  |  | 52527.79 |  | 2015 | 62000 |  | 2015-02-19 | 25000 | FALSE | TRUE | Crist | D&CS | Stevens Van Lines | Other (Design Consultant) | 2015-02-19 | 7972.21 | 2015
1998 | Kamalia | Scott Hall Building Upgrades 2015 | 772027 | 034-261806 | 612 | 258360 | Substantially Complete |  |  | 0 | 2016-11-21 | 2015 | 5000000 |  | 2015-02-17 | 5000000 | FALSE | FALSE | Flintoff | Fishbeck, Thompson, Carr & Huber, Inc. | DeMaria Building Company, Inc. | Other (Design Consultant) | 2015-02-17 | 1179379.08 | 2015
1997 | Edwards | CSC- Voice Transformation 2014 - Telecom Electrical Upgrade | 772026 | 043-261016 | 193 | 248452 | Under Construction |  |  | 0 |  | 2015 | 391000 |  | 2015-01-21 | 391000 | FALSE | TRUE | Albaari | D&CS | Allied Building Services Company | Other (Design Consultant) | 2015-01-21 | 114444.37 | 2015
1994 | Gibbons | Tierney Alumni House - Purchase of 5510 Woodward Ave. | 772003 | 090-258510 | 505 | 259171 | Under Construction |  |  | 0 | 2016-02-16 | 2015 | 430500 |  | 2015-01-06 | 430500 | FALSE | TRUE | Padilla | D&CS | Detroit Spectrum Painters, Inc. | Other (Design Consultant) | 2015-01-06 | 17142.32 | 2015
2079 | Vandenbussche | New School of Business Administration (Mike Ilitch School of Business) | 771193 | 612-258360 | 175 | 270806 | In Design |  |  | 0 | 2018-07-28 | 2015 | 3000000 |  |  | 50000000 | FALSE | FALSE | Rooks | SmithGroup Inc. | Christman Company (The) | Other (Design Consultant) | 2015-10-01 | 282533.71 | 2015
2081 | Moore | Learning Space Camera Installation | 772089 | 193-248452 | 608 | 269533 | Construction Complete |  |  | 0 | 2016-01-26 | 2015 | 50000 |  | 2015-10-14 | 50000 | FALSE | TRUE | Albaari | C&IT |  | D&CS | 2015-10-15 | 19560 | 2015
2080 | Moore | Lande Development Renovation | 772084 | 505-259171 | 611 | 273111 | Under Construction |  |  | 0 | 2016-09-29 | 2015 | 73000 |  | 2015-09-23 | 73000 | FALSE | TRUE | Padilla | D&CS |  | D&CS | 2015-12-15 | 13098.92 | 2015
2073 | Vandenbussche | Manoogian - Relocation of the Confucius Institute | 772080 | 175-270806 | 155 | 270653 | Construction Complete |  |  | 0 | 2016-04-29 | 2015 | 230720.9 |  | 2015-08-21 | 230720.93 | FALSE | TRUE | Rooks | NSA Architects, Engineers, Planners dba: Nordstrom-Samson & Associates Inc. | Dumas Concepts In Building | D&CS | 2015-08-21 | 86605.76 | 2015
2064 | Gibbons | R-FaST: CMMG New Researchers | 772072 | 612-268570 | 612 | 268570 | Under Construction |  |  | 0 | 2016-07-29 | 2015 | 42080 |  | 2015-06-29 | 42080 | FALSE | TRUE | Flintoff | D&CS | T & M | D&CS | 2015-07-01 | 883.23 | 2015
2046 | Gibbons | Shapero Graduate Classroom | 772059 | 050-267559 | 050 | 267559 | Construction Complete |  |  | 0 | 2016-07-01 | 2015 | 416825 |  | 2015-06-02 | 365000 | FALSE | TRUE | Rooks | iDesign | T & M | D&CS | 2015-06-02 | 878.7 | 2015
2077 | Alhyari | Parking Structures 4 & 5 Roofs | 772087 | 613-271498 | 613 | 271498 | Under Construction |  |  | 0 | 2017-02-28 | 2015 | 252610 |  | 2015-10-14 | 252610 | FALSE | TRUE | Flintoff | NSA Architects, Engineers, Planners dba: Nordstrom-Samson & Associates Inc. | RAM Construction Svcs of Michigan Inc |  | 2015-10-14 | 30713 | 2015
2093 | Vandenbussche | Lot 12 Parking Lot Improvements | 772085 | 999-274013 | 999 | 274013 | Under Construction |  |  | 0 | 2016-12-01 | 2015 | 850000 |  |  | 850000 | FALSE | TRUE | Davis | MEP Engineers LLC | Dumas Concepts In Building |  | 2015-10-14 | 96877.28 | 2015
2076 | Alhyari | Parking Structure 6 Upgrades | 772083 | 088-271457 | 088 | 271457 | Petition to Close |  |  | 0 | 2016-11-15 | 2015 | 250000 |  | 2015-09-23 | 350000 | FALSE | TRUE | Flintoff | D&CS | Johnson Controls, Inc. |  | 2015-09-23 | 22641.65 | 2015
2040 | Edwards | Campus PLD to DTE Integration | 772054 | 999-267153 | 999 | 267153 | In Design |  |  | 0 |  | 2015 | 250000 |  | 2015-05-20 | 1050000 | FALSE | FALSE | Edwards | Peter Basso Associates |  |  | 2015-05-26 | 124133.57 | 2015
2035 | Alhyari | Physics AHU Study | 772050 | 003-266088 | 003 | 266088 | Under Construction |  |  | 0 | 2017-02-16 | 2015 | 680000 |  | 2015-05-07 | 680000 | TRUE | FALSE |  | DiClemente Siegel Design, Inc. | Johnson Controls, Inc. |  | 2015-05-08 | 74737.61 | 2015
2001 | Brazen | UGL Compact Shelving 2015 | 772044 | #REF! | 096 | 260216 | In Design |  |  | 0 |  | 2015 | 103000 |  | 2015-04-29 | 103000 | FALSE | TRUE | Flintoff | Casper Corporation |  |  | 2015-04-29 | 96375 | 2015
1986 | Alhyari | University Tower Utility Relocation for Development | 772042 | 507-258173 | 507 | 258173 | Construction Complete |  |  | 0 | 2016-11-17 | 2015 | 145000 |  | 2015-04-23 | 145000 | FALSE | TRUE |  | Peter Basso Associates | Brencal Contractors |  | 2015-04-23 | 7413.24 | 2015
2033 | Vandenbussche | Lot 14 Parking Lot Improvements | 772041 | 999-256801 | 999 | 256801 | Construction Complete |  |  | 0 | 2016-11-17 | 2015 | 650000 |  | 2015-04-16 | 75000 | FALSE | TRUE | Davis | Mannik & Smith Group, Inc. (The) | White & Associates Inc. |  | 2015-04-16 | 29640 | 2015
1980 | Alhyari | Biologocal Science - Boiler and Boiler Parts, controls replacements | 772022 | 089-257465 | 089 | 257465 | Out for Bid |  |  | 0 | 2017-08-26 | 2015 | 100000 |  | 2015-01-06 | 100000 | TRUE | FALSE | Pecic | DiClemente Siegel Design, Inc. |  |  | 2015-01-06 | 32524.99 | 2015
1977 | Alhyari | 5057 Woodward - Heat Pump Replacements Phase 1 | 772021 | 071-257462 | 071 | 257462 | Under Construction |  |  | 0 | 2017-05-21 | 2015 | 485000 |  | 2015-01-06 | 485000 | TRUE | FALSE | Alhyari | D&CS |  |  | 2015-01-06 | 296844 | 2015
1984 | Paquette | Chatsworth Apartment Entry Steps | 772013 | 136-255250 | 136 | 255250 | Construction Complete |  |  | 0 | 2015-11-30 | 2015 | 53505 |  | 2014-10-29 |  | FALSE | TRUE | Rooks | D&CS | Akins Construction Inc. |  | 2014-10-29 | 15543.29 | 2015
1972 | Camilleri | USB - Basement Structural Remediation | 772010 | 060-256694 | 060 | 256694 | On Hold |  |  | 0 | 2016-10-27 | 2015 | 228000 |  | 2014-10-13 | 228000 | TRUE | FALSE | Azar | Walker Parking Consultants dba: Walker Restoration |  |  | 2014-10-15 | 202871.2 | 2015
1858 | Alhyari | Engineering Makeup Air Fan Controls Conversion | 771890 | 090-240937 | 090 | 240937 | Construction Complete |  |  | 0 | 2016-10-06 | 2015 | 350000 |  | 2013-10-15 | 350000 | TRUE | FALSE | Azar | D&CS | Siemens Industry, Inc. |  | 2013-10-15 | 106658.55 | 2015
1991 | Alhyari | Freer Occupant Thermal Comfort | 771803 | 511-254496 | 511 | 254496 | Under Construction |  |  | 0 | 2017-03-21 | 2015 |  |  |  | 810000 | TRUE | FALSE | Rooks | DiClemente Siegel Design, Inc. | Brencal Contractors |  |  |  | 2015
1968 | Ahern | Prentis Building Facade Repairs | 772005 | 022-255015 | 022 | 255015 | On Hold |  |  | 0 |  | 2014 | 125000 |  | 2014-10-09 | 275000 | TRUE | FALSE | Albaari | Quinn Evans Architects |  |  | 2014-10-09 | 24724.81 | 2014
1969 | Vandenbussche | University Towers Lobby Upgrades | 772004 | 507-243838 | 507 | 243838 | Substantially Complete |  |  | 0 | 2016-10-10 | 2014 | 350000 |  | 2014-10-09 |  | FALSE | TRUE | Rooks | inFORM Studio | Dumas Concepts In Building |  | 2014-10-09 | 48975.08 | 2014
1962 | Camilleri | Life Science Exterior Wall System Stabilization | 772002 | 006-253400 | 006 | 253400 | Construction Complete |  |  | 0 | 2016-11-10 | 2014 | 112000 |  | 2014-09-05 |  | TRUE | FALSE | Albaari | Desai/Nasr Consulting Engineers Inc. |  |  | 2014-09-05 | 22082.52 | 2014
1964 | Rooks | Engineering Student Innovation Center | 771998 | 999-253056 | 999 | 253056 | On Hold |  |  | 0 | 2017-11-20 | 2014 | 50000 |  | 2014-08-21 |  | FALSE | TRUE | Rooks | NORR, LLC dba: Giffels Holdings America Inc |  |  | 2014-07-21 | -10186 | 2014
1958 | Paquette | EACPHS Team Based Learning Facility | 771996 | 603-249987 | 603 | 249987 | Under Construction |  |  | 0 | 2015-11-23 | 2014 | 224000 |  | 2014-07-31 | 224000 | FALSE | TRUE | Rooks | Integrated Architecture | Brencal Contractors |  | 2014-07-31 | 11818.54 | 2014
1960 | Alhyari | FAB Roof Top Air-conditioning unit replacement | 771994 | 130-252650 | 130 | 252650 | Under Construction |  |  | 0 | 2017-03-15 | 2014 | 1680000 |  | 2014-07-31 |  | TRUE | FALSE | Albaari | DiClemente Siegel Design, Inc. | Brix Corporation |  | 2014-07-31 | 124049.29 | 2014
1921 | Ahern | Schoolcraft Extension Center | 771982 | 565-248096 | 565 | 248096 | Petition to Close | IDS | Auch Constructions | 282565.01 | 2015-01-26 | 2014 | 326709.47 |  | 2014-06-25 | 250000 | FALSE | TRUE | Azar | D&CS |  |  | 2014-07-08 | 16280.46 | 2014
1948 | Gibbons | UGL Carpet Replacement | 771981 | 096-247851 | 096 | 247851 | Substantially Complete |  |  | 0 | 2017-02-09 | 2014 | 733575 |  | 2014-06-25 |  | FALSE | TRUE | Padilla | D&CS | City Carpet & Flooring |  | 2015-06-16 | 30665.31 | 2014
1923 | Vandenbussche | Engineering - Materials Science and Nanoengineering Lab | 771976 | 090-248124 | 090 | 248124 | Cash Deficit - Cannot Close |  |  | 0 | 2016-06-01 | 2014 | 510000 |  | 2014-06-25 | 250000 | FALSE | TRUE | Flintoff | iDesign | DeMaria Building Company, Inc. |  | 2015-04-09 | -12237.52 | 2014
1943 | Gibbons | Engineering Research Laboratory Upgrades (2nd and 3rd Floors) | 771975 | 090-250890 | 090 | 250890 | Under Construction |  |  | 0 | 2017-03-11 | 2014 | 2500000 |  | 2014-06-04 | 1000000 | FALSE | FALSE | Brazen | iDesign | Livingston Power Co., LLC |  | 2014-06-04 | 224695.56 | 2014
1926 | Kamalia | Chemistry UPS Electrical Reliability Upgrade | 771962 | 007-248857 | 007 | 248857 | Other (See Comments) | Commonwealth Associates |  | 0 |  | 2014 | 385000 |  | 2014-05-08 |  | FALSE | FALSE | Kamalia | Commonwealth Associates, Inc. | Roth Electrical, LLC |  | 2014-05-08 | 36157.47 | 2014
1927 | Kamalia | Biological Science UPS Electrical Reliability Upgrade | 771961 | 089-248858 | 089 | 248858 | Other (See Comments) | Commonwealth |  | 0 |  | 2014 | 200000 |  | 2014-05-08 |  | FALSE | FALSE | Kamalia | Commonwealth Associates, Inc. | Roth Electrical, LLC |  | 2014-05-08 | 15942.82 | 2014
1929 | Kamalia | CS Mott UPS Electrical Reliability Upgrade | 771960 | 609-248861 | 609 | 248861 | Other (See Comments) | Commonwealth |  | 0 |  | 2014 | 275000 |  | 2014-05-08 |  | FALSE | FALSE | Kamalia | Commonwealth Associates, Inc. | Roth Electrical, LLC |  | 2014-05-08 | 56118 | 2014
1930 | Kamalia | Scott Hall UPS Electrical Reliability Upgrade | 771959 | 612-248862 | 612 | 248862 | Other (See Comments) | Commonwealth |  | 0 |  | 2014 | 340000 |  | 2014-05-08 |  | FALSE | FALSE | Kamalia | Commonwealth Associates, Inc. | Roth Electrical, LLC |  | 2014-05-08 | -3699.51 | 2014
1925 | Kamalia | Hudson Webber UPS Electrical Reliability Upgrade | 771953 | 655-248863 | 655 | 248863 | Other (See Comments) | Commonwealth |  | 0 |  | 2014 | 68000 |  | 2014-04-29 |  | FALSE | FALSE | McVea | Commonwealth Associates, Inc. |  |  | 2014-04-29 | -24684.44 | 2014
1922 | Brazen | Alumni Emergency Generator | 771952 | 042-247540 | 042 | 247540 | Petition to Close | Berbiglia 248.489.3100 |  | 0 | 2015-08-15 | 2014 | 25000 |  | 2014-04-22 |  | FALSE | FALSE | Rooks | Berbiglia Associates, Inc. |  |  | 2014-04-22 | 4222.78 | 2014
1916 | Kamalia | KCI - Relocation Planning | 771947 | 629-247637 | 629 | 247637 | Under Construction |  |  | 0 | 2016-03-18 | 2014 | 8940000 |  | 2014-03-14 | 25000 | FALSE | TRUE | Flintoff | SmithGroup Inc. | DeMaria Building Company, Inc. |  | 2014-03-14 | 1911361.42 | 2014
1912 | Azar | Community Arts Building - Loading Dock Renovation | 771941 | 039-246190 | 039 | 246190 | In Design |  |  | 0 | 2015-04-21 | 2014 | 160000 |  | 2014-04-08 | 50000 | TRUE | FALSE | Azar | Hamilton Anderson Associates |  |  | 2014-03-05 | 30006.93 | 2014
1903 | Vandenbussche | Shapero Hall Electical Reliability Upgrade | 771939 | 050-245285 | 050 | 245285 | On Hold |  |  | 0 | 2015-10-18 | 2014 | 50000 |  | 2014-03-07 | 50000 | FALSE | FALSE |  | MEP Engineers LLC |  |  | 2014-03-11 | 24114.49 | 2014
1891 | Edwards | Pharmacy Building-Electrical Reliability Upgrade | 771938 | 603-243264 | 603 | 243264 | Substantially Complete | PBA |  | 0 |  | 2014 | 2545000 |  | 2014-03-06 | 100000 | FALSE | FALSE | Vandenbussche | Peter Basso Associates | Brencal Contractors |  | 2015-01-07 | 218122.48 | 2014
1902 | Edwards | Engineering Building Electrical Reliability Upgrade | 771937 | 090-245186 | 090 | 245186 | Substantially Complete | Commonwealth Associates, Inc. |  | 0 | 2015-08-10 | 2014 | 2588000 |  | 2014-03-06 | 100000 | FALSE | FALSE |  | Commonwealth Associates, Inc. | Brencal Contractors |  | 2014-03-11 | 138664.3 | 2014
1898 | Albaari | Campus Wide Facilities Assessment | 771933 | 999-244448 | 999 | 244448 | Planned |  |  | 0 |  | 2014 | 200000 |  | 2014-02-17 | 100000 | TRUE | FALSE | Azar | Turner Construction Company |  |  | 2014-02-17 | 18256.96 | 2014
1887 | Moore | Science Hall - Third Floor Renovation for Nutrition and Food Science | 771929 | 005-242336 | 005 | 242336 | Substantially Complete | Lord, Aeck & Sargent |  | 0 | 2016-08-04 | 2014 | 3250000 |  | 2014-02-10 | 340000 | FALSE | FALSE | Flintoff | Lord, Aeck & Sargent, Inc. (LAS) | Phoenix Contractors, Inc. dba: PHX Construction Inc. |  | 2014-02-10 | 165262.66 | 2014
1897 | Moore | Undergraduate Library - Honors College Offices and Reception | 771926 | 096-235942 | 096 | 235942 | Construction Complete | Design Services |  | 0 | 2016-11-02 | 2014 | 180979 |  | 2014-01-29 | 180979 | FALSE | TRUE | Padilla | D&CS |  |  | 2014-01-29 | 62515.7 | 2014
1885 | Moore | Campus Wide Classroom Technology Upgrades FY2014 | 771916 | 999-236664 | 999 | 236664 | Under Construction | NSA | Roth Electrical | 0 | 2017-02-15 | 2014 | 1000000 |  | 2013-11-21 | 1000000 | FALSE | FALSE | Padilla | NSA Architects, Engineers, Planners dba: Nordstrom-Samson & Associates Inc. | Roth Electrical, LLC |  | 2013-11-21 | 247835.27 | 2014
1878 | Gibbons | Campus Wide General Classroom Improvement | 771915 | 999-242207 | 999 | 242207 | Under Construction | D&CS | Various | 0 |  | 2014 | 250000 |  | 2013-11-21 | 250000 | TRUE | FALSE | Padilla | D&CS |  |  | 2013-11-21 | 119641.74 | 2014
1875 | Camilleri | Biological Sciences - Green House Renovations | 771911 | 089-241040 | 089 | 241040 | Under Construction | Multiple |  | 0 | 2017-05-12 | 2014 | 1550000 |  | 2013-11-21 | 1550000 | TRUE | FALSE | Flintoff | Ghafari Associates, L.L.C. | Phoenix Contractors, Inc. dba: PHX Construction Inc. |  | 2013-11-21 | 142126.61 | 2014
1877 | Edwards | Freezer Protection Devices | 771906 | 999-242179 | 999 | 242179 | Substantially Complete | WSU | Delta Temp | 236128.65 | 2014-07-31 | 2014 | 200000 |  | 2014-03-11 | 200000 | FALSE | FALSE |  | D&CS | Delta Temp Inc. |  | 2013-10-22 | -36128.65 | 2014
1860 | Edwards | Campus - Site Concrete Repairs FY14-15 | 771900 | 999-240933 | 999 | 240933 | Under Construction | WSU D&CS |  | 0 | 2016-07-15 | 2014 | 750000 |  | 2013-10-17 | 150000 | TRUE | FALSE | Brazen | D&CS | Akins Construction Inc. |  | 2013-10-17 | 200765.3 | 2014
1836 | SiKora | Old Main - Geology and Planetarium Renovation | 771872 | 001-233124 | 001 | 233124 | Construction Complete |  |  | 0 | 2015-09-01 | 2013 | 42120 |  | 2013-08-20 | 42120 | FALSE | TRUE | Rooks | Dokes Design & Architecture LLC | Electronic Security Systems, Inc. (ESS) |  | 2013-08-20 | 1169.79 | 2013
1818 | Camilleri | 5447 Woodward for Social Work Renovation | 771871 | 063-233732 | 063 | 233732 | Construction Complete | Hamilton Anderson with PBA |  | 0 | 2016-09-15 | 2013 | 5750000 |  | 2013-06-27 | 15000 | FALSE | TRUE | Rooks | Hamilton Anderson Associates | Brencal Contractors |  | 2013-06-27 | 252529.57 | 2013
1817 | Edwards | Community Arts Gallery Lighting | 771857 | 039-231828 | 039 | 231828 | Substantially Complete | SES |  | 0 | 2015-01-29 | 2013 | 375000 |  | 2013-06-10 | 375000 | TRUE | FALSE | Azar | Strategic Energy Solutions, Inc (SES) | Motor City Electric |  | 2013-06-10 | 31961.92 | 2013
1813 | Brazen | Classroom Improvements 2013 | 771846 | 999-219932 | 999 | 219932 | Petition to Close |  |  | 0 |  | 2013 | 250000 |  | 2013-05-10 | 250000 | TRUE | FALSE | Brazen |  |  |  | 2013-05-13 | 47498.06 | 2013
1798 | Camilleri | SCB Passenger Elevator Renovation | 771836 | 034-230594 | 034 | 230594 | Substantially Complete | 1199 |  | 0 | 2016-10-27 | 2013 | 551000 |  | 2013-04-05 | 75000 | FALSE | TRUE | Azar | Ann Arbor Architects Collaborative (A3C) | Schindler Elevator Corporation |  | 2013-04-05 | 14678.4 | 2013
1796 | Gibbons | Matthaei Baseball Stadium Renovation - Harwell Field | 771830 | 080-232104 | 080 | 232104 | Under Construction | Silveri |  | 0 | 2017-05-23 | 2013 | 1740000 |  | 2013-03-12 | 1685000 | FALSE | TRUE | Rooks | Silveri Architects | Brencal Contractors |  | 2013-03-12 | 160543.98 | 2013
1778 | Edwards | Computer Service Center - Design 1600A Switchboard | 771825 | 193-228859 | 193 | 228859 | On Hold | PBA |  | 0 | 2015-01-01 | 2013 | 21000 |  | 2013-03-08 | 0 | TRUE | FALSE |  | Peter Basso Associates |  |  | 2013-03-08 | 8600 | 2013
1769 | Vandenbussche | Advanced Technology Education Center (ATEC) | 771813 | 556-195246 | 556 | 195246 | Construction Complete | 1357 | Christman | 0 | 2015-01-26 | 2013 | 12270000 |  |  |  | FALSE | FALSE | Azar | NORR, LLC dba: Giffels Holdings America Inc | Christman Company (The) |  | 2013-01-03 | 94670.08 | 2013
1812 | Crist | Campus Wide Equipment Moves | 225580 | 999-234312 | 999 | 234312 | On Going | D&CS | Blanket PO with Stevens | 0 |  | 2013 | 75000 |  | 2013-07-01 | 75000 | FALSE | FALSE | Brazen | D&CS | Stevens Van Lines |  | 2013-07-01 | 40600.28 | 2013
1754 | Camilleri | Campus - Fountain Court Design | 771799 | 999-222859 | 999 | 222859 | Construction Complete | Silveri |  | 0 | 2015-11-30 | 2012 | 600000 |  | 2014-06-11 | 600000 | TRUE | FALSE | Azar | Hamilton Anderson Associates | LaSalle Group (The) |  | 2012-10-25 | 31750.14 | 2012
1728 | Camilleri | Student Center Building Renovation 2013 | 771768 | 034-216815 | 034 | 216815 | Substantially Complete | Neumann Smith | Turner Construction | 0 | 2016-11-10 | 2012 | 26449000 |  | 2013-02-25 | 1300000 | FALSE | TRUE | Azar | Neumann Smith & Associates | Turner Construction Company |  | 2012-07-20 | 87524.71 | 2012
1608 | Ahern | Multiple Building Steam Safety Relief Valve Installation | 771665 | 999-205475 | 999 | 205475 | On Going | 1046 | Marble Mechanical LLC | 0 |  | 2011 | 375000 |  | 2012-10-24 | 375000 | TRUE | FALSE | Alhyari | Sellinger Associates | T&M |  | 2011-07-12 | 110482.5 | 2011
1565 | Vandenbussche | Trumball Landscape/Gateway Study | 771628 | 999-186725 | 999 | 186725 | On Hold | Corbin / Silveri |  | 0 |  | 2011 | 20000 |  |  |  | FALSE | FALSE |  | Corbin Design, Inc. |  |  | 2011-01-10 | 5457.41 | 2011
1546 | Ahern | Multi Building Comprehensive Asbestos Inspection Testing | 771609 | 999-227223 | 999 | 227223 | On Going | D&CS | ETC Environmental Services | 0 | 2016-01-01 | 2011 | 150000 |  | 2012-12-21 | 50000 | TRUE | FALSE |  | D&CS | ETC Environmental Services dba: ETC Leaders LLC |  | 2010-11-30 | 250.47 | 2011
*Unassigned - Project has not yet been assigned to a Project Manager