## Curb Appeal I & II
Date | Curb Appeal Project % complete per week | Goal | Date | Curb Appeal Project % complete per week | Goal
2011-10-02 | 16 | 0 | 2012-08-12 | 3 | 0
2011-10-09 | 16 |  | 2012-08-19 | 6
2011-10-16 | 17 |  | 2012-08-26 | 9
2011-10-23 | 17 |  | 2012-09-02 | 14
2011-10-30 | 20 |  | 2012-09-09 | 16
2011-11-06 | 20 |  | 2012-09-16 | 20
2011-11-13 | 21 |  | 2012-09-23 | 21
2011-11-20 | 21 |  | 2012-09-30 | 22
2011-11-27 | 22 |  | 2012-10-07 | 30
2011-12-04 | 25 |  | 2012-10-14 | 33
2011-12-11 | 28 |  | 2012-10-21 | 37
2011-12-18 | 29 |  | 2012-10-28 | 40
2011-12-25 | 29 |  | 2012-11-04 | 45
2012-01-01 | 33 |  | 2012-11-11 | 46
2012-01-08 | 37 |  | 2012-11-18 | 52
2012-01-15 | 40 |  | 2012-11-25 | 54 | 50
2012-01-22 | 41 |  | 2012-12-02 | 55
2012-01-29 | 42 |  | 2012-12-09 | 57
2012-02-05 | 45 |  | 2012-12-16 | 60
2012-02-12 | 49 |  | 2012-12-23 | 63
2012-02-19 | 53 |  | 2012-12-30 | 63
2012-02-26 | 56 |  | 2013-01-06 | 66
2012-03-04 | 60 | 50 | 2013-01-13 | 68
2012-03-11 | 62 |  | 2013-01-20 | 69
2012-03-18 | 65 |  | 2013-01-27 | 71
2012-03-25 | 67 | 65 | 2013-02-03 | 72
2012-04-01 | 71 |  | 2013-02-10 | 73
2012-04-08 | 73 |  | 2013-02-17 | 74
2012-04-15 | 75 |  | 2013-02-24 | 74 | 65
2012-04-22 | 77 |  | 2013-03-03 | 74
2012-04-29 | 79 |  | 2013-03-10 | 75
2012-05-06 | 81 |  | 2013-03-17
2012-05-13 | 82 |  | 2013-03-24
2012-05-20 | 84 |  | 2013-03-31
2012-05-27 | 91 |  | 2013-04-07
2012-06-03 | 94 |  | 2013-04-14
2012-06-10 | 95 |  | 2013-04-21
2012-06-17 | 95 |  | 2013-04-28
2012-06-24 | 97 |  | 2013-05-05
2012-07-01 | 97 |  | 2013-05-12
2012-07-08 | 97 |  | 2013-05-19
2012-07-16 | 98 | 95 | 2013-05-26 |  | 95
2012-07-22 | 98 |  | 2013-06-02
2012-07-29 | 99 |  | 2013-06-09
2012-08-05 | 99 |  | 2013-06-16
2012-08-12 | 99 |  | 2013-06-23
2012-08-19 | 99 | 100 | 2013-06-30 |  | 100
Formulas:
Date = [Date, row above]+7

## Curb Appeal III & IV
Date | Curb Appeal III Project % complete per week | Goal | Date | Curb Appeal IV Project % complete per week | Goal
2013-11-05 | 0% | 4% | 2014-08-25 | 0%
2013-11-12 | 0% | 8% | 2014-09-01 | 9%
2013-11-19 | 0% | 12% | 2014-09-08 | 19%
2013-11-26 | 20% | 16% | 2014-09-15 | 19%
2013-12-03 | 26% | 20% | 2014-09-22
2013-12-10 | 26% | 24% | 2014-09-29
2013-12-17 | 26% | 28% | 2014-10-06
2013-12-24 | 26% | 32% | 2014-10-13
2013-12-31 | 26% | 36% | 2014-10-20
2014-01-07 | 38% | 40% | 2014-10-27
2014-01-14 | 38% | 44% | 2014-11-03 |  | 25%
2014-01-21 | 38% | 48% | 2014-11-10
2014-01-28 | 38% | 52% | 2014-11-17
2014-02-04 | 38% | 56% | 2014-11-24
2014-02-11 | 38% | 60% | 2014-12-01
2014-02-18 | 38% | 64% | 2014-12-08
2014-02-25 | 38% | 68% | 2014-12-15
2014-03-04 | 47% | 72% | 2014-12-22
2014-03-11 | 49% | 76% | 2014-12-29
2014-03-18 | 58% | 80% | 2015-01-05 |  | 50%
2014-03-25 | 62% | 84% | 2015-01-12
2014-04-01 | 66% | 88% | 2015-01-19
2014-04-08 | 71% | 92% | 2015-01-26
2014-04-15 | 71% | 96% | 2015-02-02
2014-04-22 | 73% | 99% | 2015-02-09
2014-04-29 | 74% | 100% | 2015-02-16
2014-05-06 | 76% | 100% | 2015-02-23
2014-05-13 | 78% | 100% | 2015-03-02 |  | 75%
2014-05-20 | 79% | 100% | 2015-03-09
2014-05-27 | 82% | 100% | 2015-03-16
2014-06-03 | 83% | 100% | 2015-03-23
2014-06-10 | 85% | 100% | 2015-03-30
2014-06-17 | 86% | 100% | 2015-04-06
2014-06-24 | 87% | 100% | 2015-04-13
2014-07-01 | 91% | 100% | 2015-04-20
2014-07-08 | 91% | 100% | 2015-04-27
2014-07-15 | 91% | 100% | 2015-05-04 |  | 100%
2014-07-22 | 92% | 100%
2014-07-29 | 92% | 100%
2014-08-05 | 93% | 100%
2014-08-12 | 94% | 100%
2014-08-19 | 94% | 100%
2014-08-26 | 95% | 100%

## Survey Projects
Average Project Survey Scores |  |  | 1=strongly disagree | 5=strongly agree
total # responses
2014-03-01 | 4.2 | 4
2014-04-01 |  | 0
2014-05-01 |  | 0
2014-06-01 | 4.08 | 2
2014-07-01 | 5 | 2
2014-08-01 | 5 | 1
2014-09-01

## Survey Work Orders
Average Work Order Survey Scores |  |  | 1=strongly disagree | 5=strongly agree
total # responses
2012-01-01 | 4.16 | 6
2012-02-01 | 3.65 | 23
2012-03-01 | 4.14 | 14
2012-04-01 | 4.48 | 15
2012-05-01 | 3.81 | 9
2012-06-01 | 4.1 | 8
2012-07-01 | 4 | Calculated the average- module didn't work month of July
2012-08-01 | 4.28 | 7
2012-09-01 | 4.14 | 39
2012-10-01 | 4.01 | 97
2012-11-01 | 4.16 | 79
2012-12-01 | 4.15 | 74
2013-01-01 | 4.08 | 69
2013-02-01 | 4.12 | 69
2013-03-01 | 4.16 | 92
2013-04-01 | 4.565 | 89
2013-05-01 | 4.42 | 91
2013-06-01 | 4.23 | 58
2013-07-01 | 4.14 | 123
2013-08-01 | 4.37 | 98
2013-09-01 | 4.51 | 89
2013-10-01 | 4.26 | 105
2013-11-01 | 4.62 | 106
2013-12-01 | 4.53 | 98
2014-01-01 | 4.47 | 83
2014-02-01 | 4.41 | 106
2014-03-01 | 4.73 | 88
2014-04-01 | 4.81 | 81
2014-05-01 | 4.48 | 91
2014-06-01 | 4.34 | 81
2014-07-01 | 4.58 | 72
2014-08-01 | 4.45 | 93

## Custodial
Month | Goal | Total # |  | > 30 Days Old
2012-01-01 |  | 247 |  | 146 | 59.11%
2012-02-01 |  | 130 |  | 54 | 41.54%
2012-03-01 |  | 78 |  | 13 | 16.67%
2012-04-01 |  | 116 |  | 33 | 28.45%
2012-05-01 |  | 77 |  | 46 | 59.74%
2012-06-01 |  | 150 |  | 34 | 22.67%
2012-07-01 |  | 113 |  | 43 | 38.05%
2012-08-01 |  | 158 |  | 32 | 20.25%
2012-09-01 |  | 98 |  | 48 | 48.98%
2012-10-01 |  | 46 |  | 0 | 0%
2012-11-01 |  | 49 |  | 2 | 4.082%
2012-12-01 |  | 30 |  | 0 | 0%
2013-01-01 |  | 100 |  | 0 | 0%
2013-02-01 |  | 67 |  | 7 | 10.45%
2013-03-01 |  | 56 |  | 1 | 1.786%
2013-04-01 |  | 102 |  | 2 | 1.961%
2013-05-01 |  | 81 |  | 9 | 11.11%
2013-06-01 |  | 90 |  | 18 | 20%
2013-07-01 |  | 77 |  | 27 | 35.06%
2013-08-01 |  | 120 |  | 21 | 17.5%
2013-09-01 |  | 83 |  | 30 | 36.14%
2013-10-01 |  | 83 |  | 19 | 22.89%
2013-11-01 |  | 80 |  | 14 | 17.5%
2013-12-01 |  | 72 |  | 37 | 51.39%
2014-01-01 |  | 109 |  | 39 | 35.78%
2014-02-01 |  | 99 |  | 39 | 39.39%
2014-03-01 |  | 105 |  | 49 | 46.67%
2014-04-01 |  | 133 |  | 63 | 47.37%
2014-05-01 |  | 105 |  | 58 | 55.24%
2014-06-01 |  | 116 |  | 63 | 54.31%
2014-07-01 |  | 99 |  | 58 | 58.59%
2014-08-01 |  | 123 |  | 56 | 45.53%
Month | Goal | Total completed | Total completed on time | Actual | Total completed | Total completed on time | Emergency | Total completed | Total completed on time | High | Total completed | Total completed on time | Medium | Total completed | Total completed on time | Low | Routine
2011-10-01 | 90% | 220 | 171 | 77.73% |  |  | - |  |  | 10% |  |  | 53% |  |  | 84%
2011-11-01 | 90% | 203 | 153 | 75.37% |  |  | - |  |  | 20% |  |  | 69% |  |  | 77%
2011-12-01 | 90% | 251 | 163 | 64.94% |  |  | - |  |  | 33% |  |  | 10% |  |  | 69%
2012-01-01 | 90% | 185 | 103 | 55.68% |  |  | - |  |  | 66% |  |  | 50% |  |  | 57%
2012-02-01 | 90% | 206 | 132 | 64.08% |  |  | - |  |  | 17% |  |  | 47% |  |  | 67%
2012-03-01 | 90% | 173 | 162 | 93.64% | 1 | 1 | 100% | 5 | 3 | 60% | 14 | 11 | 78.57% | 153 | 147 | 96.08%
2012-04-01 | 90% | 174 | 135 | 77.59% | 4 | 2 | 50% | 4 | 1 | 25% | 10 | 4 | 40% | 156 | 128 | 82.05%
2012-05-01 | 90% | 201 | 191 | 95.02% | 2 | 1 | 50% | 9 | 5 | 55.56% | 18 | 16 | 88.89% | 172 | 169 | 98.26%
2012-06-01 | 90% | 178 | 151 | 84.83% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 14 | 10 | 71.43% | 163 | 141 | 86.5% | 7
2012-07-01 | 90% | 92 | 76 | 82.61% | 1 | 1 | 100% | 3 | 2 | 66.67% | 22 | 17 | 77.27% | 66 | 56 | 84.85% | 60
2012-08-01 | 90% | 198 | 179 | 90.4% | 1 | 1 | 100% | 7 | 5 | 71.43% | 27 | 21 | 77.78% | 163 | 152 | 93.25% | 29
2012-09-01 | 90% | 166 | 135 | 81.33% | 2 | 1 | 50% | 6 | 3 | 50% | 33 | 28 | 84.85% | 125 | 102 | 81.6% | 3
2012-10-01 | 90% | 307 | 277 | 90.23% | 1 | 1 | 100% | 10 | 6 | 60% | 45 | 36 | 80% | 251 | 234 | 93.23% | 11
2012-11-01 | 90% | 210 | 205 | 97.62% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 19 | 18 | 94.74% | 190 | 186 | 97.89% | 5
2012-12-01 | 90% | 157 | 151 | 96.18% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 12 | 9 | 75% | 144 | 141 | 97.92% | 2
2013-01-01 | 90% | 196 | 187 | 95.41% | 0 | 0 | #DIV/0! | 2 | 2 | 100% | 3 | 3 | 100% | 191 | 182 | 95.29% | 4
2013-02-01 | 90% | 201 | 191 | 95.02% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 3 | 2 | 66.67% | 198 | 189 | 95.45% | 0
2013-03-01 | 90% | 250 | 237 | 94.8% | 0 | 0 | #DIV/0! | 3 | 1 | 33.33% | 9 | 9 | 100% | 238 | 227 | 95.38% | 0
2013-04-01 | 90% | 191 | 182 | 95.29% | 1 | 1 | 100% | 1 | 1 | 100% | 2 | 1 | 50% | 187 | 179 | 95.72% | 2
2013-05-01 | 90% | 234 | 220 | 94.02% | 1 | 1 | 100% | 1 | 1 | 100% | 11 | 10 | 90.91% | 221 | 208 | 94.12% | 33
2013-06-01 | 90% | 195 | 189 | 96.92% | 3 | 3 | 100% | 4 | 4 | 100% | 4 | 4 | 100% | 184 | 178 | 96.74% | 3
2013-07-01 | 90% | 232 | 211 | 90.95% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 231 | 210 | 90.91% | 14
2013-08-01 | 90% | 266 | 246 | 92.48% | 2 | 2 | 100% | 0 | 0 | #DIV/0! | 9 | 7 | 77.78% | 255 | 237 | 92.94% | 16
2013-09-01 | 90% | 206 | 195 | 94.66% | 0 | 0 | #DIV/0! | 2 | 1 | 50% | 4 | 2 | 50% | 200 | 192 | 96% | 19
2013-10-01 | 90% | 307 | 296 | 96.42% | 2 | 2 | 100% | 2 | 2 | 100% | 6 | 5 | 83.33% | 297 | 287 | 96.63% | 4
2013-11-01 | 90% | 233 | 229 | 98.28% | 1 | 0 | 0% | 1 | 1 | 100% | 5 | 3 | 60% | 226 | 225 | 99.56% | 20
2013-12-01 | 90% | 163 | 152 | 93.25% | 3 | 3 | 100% | 0 | 0 | #DIV/0! | 10 | 6 | 60% | 150 | 143 | 95.33% | 1
2014-01-01 | 90% | 162 | 162 | 100% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 2 | 2 | 100% | 159 | 159 | 100% | 2
2014-02-01 | 90% | 216 | 205 | 94.91% | 3 | 2 | 66.67% | 6 | 6 | 100% | 5 | 5 | 100% | 202 | 192 | 95.05% | 1
2014-03-01 | 90% | 239 | 226 | 94.56% | 0 | 0 | #DIV/0! | 2 | 2 | 100% | 7 | 5 | 71.43% | 230 | 219 | 95.22% | 1
2014-04-01 | 90% | 172 | 151 | 87.79% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 2 | 1 | 50% | 169 | 149 | 88.17% | 0
2014-05-01 | 90% | 257 | 237 | 92.22% | 0 | 0 | #DIV/0! | 2 | 2 | 100% | 3 | 2 | 66.67% | 252 | 233 | 92.46% | 0
2014-06-01 | 90% | 231 | 213 | 92.21% | 3 | 3 | 100% | 3 | 2 | 66.67% | 9 | 9 | 100% | 216 | 199 | 92.13% | 0
2014-07-01 | 90% | 260 | 236 | 90.77% | 1 | 0 | 0% | 2 | 2 | 100% | 9 | 7 | 77.78% | 248 | 227 | 91.53% | 0
2014-08-01 | 90% | 219 | 205 | 93.61% | 0 | 0 | #DIV/0! | 1 | 0 | 0% | 3 | 3 | 100% | 215 | 202 | 93.95% | 0
Custodial
Month | Total # | < 30 Days | 31-60 Days | 61-90 Days | 91-180 Days | 181-365 Days | >365 Days
2012-06-01 | 150 | 116 | 21 | 7 | 6 | 0 | 0
2012-07-01 | 113 | 70 | 31 | 7 | 4 | 0 | 1
2012-08-01 | 158 | 126 | 16 | 10 | 6 | 0 | 0
2012-09-01 | 98 | 50 | 39 | 9 | 0 | 0 | 0
2012-10-01 | 46 | 46 | 0 | 0 | 0 | 0 | 0
2012-11-01 | 49 | 47 | 1 | 0 | 1 | 0 | 0
2012-12-01 | 30 | 30 | 0 | 0 | 0 | 0 | 0
2013-01-01 | 100 | 100 | 0 | 0 | 0 | 0 | 0
2013-02-01 | 67 | 60 | 7 | 0 | 0 | 0 | 0
2013-03-01 | 56 | 55 | 1 | 0 | 0 | 0 | 0
2013-04-01 | 102 | 100 | 2 | 0 | 0 | 0 | 0
2013-05-01 | 81 | 72 | 9 | 0 | 0 | 0 | 0
2013-06-01 | 90 | 72 | 10 | 8 | 0 | 0 | 0
2013-07-01 | 77 | 50 | 12 | 8 | 7 | 0 | 0
2013-08-01 | 120 | 99 | 6 | 1 | 14 | 0 | 0
2013-09-01 | 83 | 53 | 12 | 3 | 15 | 0 | 0
2013-10-01 | 83 | 64 | 1 | 2 | 9 | 7 | 0
2013-11-01 | 80 | 66 | 3 | 1 | 3 | 7 | 0
2013-12-01 | 72 | 35 | 26 | 1 | 3 | 7 | 0
2014-01-01 | 109 | 70 | 3 | 25 | 2 | 9 | 0
2014-02-01 | 99 | 60 | 4 | 0 | 26 | 9 | 0
2014-03-01 | 105 | 56 | 13 | 1 | 25 | 10 | 0
2014-04-01 | 133 | 70 | 23 | 4 | 26 | 7 | 3
2014-05-01 | 105 | 47 | 7 | 14 | 2 | 28 | 7
2014-06-01 | 116 | 53 | 19 | 6 | 3 | 28 | 7
2014-07-01 | 99 | 41 | 13 | 3 | 7 | 27 | 8
2014-08-01 | 123 | 67 | 9 | 5 | 7 | 26 | 9

## Engineering
Month | Goal | Total # | > 30 Days Old
2012-01-01 | 300 | 774 | 415 | 53.62%
2012-02-01 | 300 | 395 | 81 | 20.51%
2012-03-01 | 300 | 262 | 108 | 41.22%
2012-04-01 | 300 | 341 | 164 | 48.09%
2012-05-01 | 300 | 509 | 386 | 75.83%
2012-06-01 | 300 | 615 | 257 | 41.79%
2012-07-01 | 300 | 700 | 320 | 45.71%
2012-08-01 | 300 | 697 | 358 | 51.36%
2012-09-01 | 300 | 611 | 332 | 54.34%
2012-10-01 | 300 | 299 | 47 | 15.72%
2012-11-12 | 300 | 311 | 120 | 38.59%
2012-12-12 | 300 | 290 | 124 | 42.76%
2013-01-12 | 300 | 346 | 121 | 34.97%
2013-02-12 | 300 | 377 | 179 | 47.48%
2013-03-12 | 300 | 286 | 123 | 43.01%
2013-04-12 | 300 | 285 | 59 | 20.7%
2013-05-12 | 300 | 533 | 95 | 17.82%
2013-06-12 | 300 | 461 | 220 | 47.72%
2013-07-12 | 300 | 531 | 181 | 34.09%
2013-08-12 | 300 | 644 | 194 | 30.12%
2013-09-12 | 300 | 502 | 201 | 40.04%
2013-10-12 | 300 | 342 | 29 | 8.48%
2013-11-12 | 300 | 279 | 97 | 34.77%
2013-12-12 | 300 | 285 | 93 | 32.63%
2014-01-12 | 300 | 395 | 150 | 37.97%
2014-02-12 | 300 | 309 | 142 | 45.95%
2014-03-12 | 300 | 322 | 187 | 58.07%
2014-04-12 | 300 | 369 | 141 | 38.21%
2014-05-12 | 300 | 346 | 89 | 25.72%
2014-06-12 | 300 | 248 | 50 | 20.16%
2014-07-12 | 300 | 232 | 104 | 44.83%
2014-08-12 | 300 | 333 | 97 | 29.13%
Month | Goal | Total completed | Total completed on time | Actual | Total completed | Total completed on time | Emergency | Total completed | Total completed on time | High | Total completed | Total completed on time | Medium | Total completed | Total completed on time | Low | Routine
2011-10-01 | 90% | 1066 | 878 | 82.36% |  |  | 79% |  |  | 77% |  |  | 87% |  |  | 76%
2011-11-01 | 90% | 1014 | 933 | 92.01% |  |  | 77% |  |  | 88% |  |  | 95% |  |  | 94%
2011-12-01 | 90% | 763 | 667 | 87.42% |  |  | 94% |  |  | 82% |  |  | 91% |  |  | 87%
2012-01-01 | 90% | 810 | 607 | 74.94% |  |  | 92% |  |  | 82% |  |  | 73% |  |  | 70%
2012-02-01 | 90% | 709 | 670 | 94.5% |  |  | 96% |  |  | 92% |  |  | 97% |  |  | 92%
2012-03-01 | 90% | 888 | 862 | 97.07% | 26 | 26 | 100% | 292 | 282 | 96.58% | 428 | 421 | 98.36% | 142 | 133 | 93.66%
2012-04-01 | 90% | 698 | 571 | 81.81% | 14 | 11 | 78.57% | 209 | 171 | 81.82% | 297 | 241 | 81.14% | 178 | 148 | 83.15%
2012-05-01 | 90% | 678 | 638 | 94.1% | 11 | 10 | 90.91% | 180 | 167 | 92.78% | 343 | 331 | 96.5% | 144 | 131 | 90.97%
2012-06-01 | 90% | 546 | 522 | 95.6% | 16 | 15 | 93.75% | 177 | 164 | 92.66% | 263 | 256 | 97.34% | 90 | 87 | 96.67% | 16
2012-07-01 | 90% | 722 | 482 | 66.76% | 23 | 16 | 69.57% | 295 | 187 | 63.39% | 312 | 248 | 79.49% | 92 | 31 | 33.7% | 61
2012-08-01 | 90% | 537 | 491 | 91.43% | 16 | 14 | 87.5% | 184 | 169 | 91.85% | 258 | 239 | 92.64% | 79 | 69 | 87.34% | 12
2012-09-01 | 90% | 687 | 641 | 93.3% | 12 | 12 | 100% | 181 | 151 | 83.43% | 329 | 318 | 96.66% | 165 | 160 | 96.97% | 14
2012-10-01 | 90% | 671 | 647 | 96.42% | 14 | 13 | 92.86% | 221 | 207 | 93.67% | 339 | 335 | 98.82% | 97 | 94 | 96.91% | 4
2012-11-01 | 90% | 645 | 611 | 94.73% | 24 | 22 | 91.67% | 172 | 152 | 88.37% | 330 | 323 | 97.88% | 119 | 107 | 89.92% | 7
2012-12-01 | 90% | 435 | 399 | 91.72% | 10 | 8 | 80% | 177 | 160 | 90.4% | 167 | 158 | 94.61% | 81 | 73 | 90.12% | 4
2013-01-01 | 90% | 676 | 630 | 93.2% | 16 | 14 | 87.5% | 163 | 152 | 93.25% | 355 | 342 | 96.34% | 142 | 122 | 85.92% | 2
2013-02-01 | 90% | 373 | 347 | 93.03% | 5 | 5 | 100% | 99 | 94 | 94.95% | 166 | 155 | 93.37% | 103 | 93 | 90.29% | 1
2013-03-01 | 90% | 482 | 423 | 87.76% | 6 | 6 | 100% | 146 | 134 | 91.78% | 245 | 218 | 88.98% | 85 | 65 | 76.47% | 22
2013-04-01 | 90% | 446 | 391 | 87.67% | 11 | 10 | 90.91% | 119 | 104 | 87.39% | 189 | 179 | 94.71% | 127 | 98 | 77.17% | 9
2013-05-01 | 90% | 475 | 442 | 93.05% | 9 | 9 | 100% | 95 | 81 | 85.26% | 242 | 233 | 96.28% | 129 | 119 | 92.25% | 1
2013-06-01 | 90% | 342 | 305 | 89.18% | 21 | 20 | 95.24% | 64 | 54 | 84.38% | 148 | 140 | 94.59% | 109 | 91 | 83.49% | 1
2013-07-01 | 90% | 559 | 467 | 83.54% | 12 | 11 | 91.67% | 150 | 129 | 86% | 250 | 232 | 92.8% | 147 | 95 | 64.63% | 4
2013-08-01 | 90% | 307 | 286 | 93.16% | 20 | 20 | 100% | 84 | 76 | 90.48% | 135 | 127 | 94.07% | 68 | 63 | 92.65% | 2
2013-09-01 | 90% | 404 | 350 | 86.63% | 18 | 16 | 88.89% | 114 | 92 | 80.7% | 170 | 157 | 92.35% | 102 | 85 | 83.33% | 1
2013-10-01 | 90% | 440 | 419 | 95.23% | 23 | 22 | 95.65% | 116 | 106 | 91.38% | 197 | 193 | 97.97% | 104 | 98 | 94.23% | 1
2013-11-01 | 90% | 575 | 537 | 93.39% | 27 | 25 | 92.59% | 163 | 143 | 87.73% | 260 | 249 | 95.77% | 125 | 119 | 95.2% | 1
2013-12-01 | 90% | 524 | 411 | 78.44% | 37 | 34 | 91.89% | 117 | 90 | 76.92% | 229 | 186 | 81.22% | 141 | 101 | 71.63% | 6
2014-01-01 | 90% | 728 | 677 | 92.99% | 23 | 13 | 56.52% | 138 | 116 | 84.06% | 394 | 380 | 96.45% | 173 | 168 | 97.11% | 0
2014-02-01 | 90% | 593 | 500 | 84.32% | 10 | 5 | 50% | 146 | 117 | 80.14% | 245 | 218 | 88.98% | 192 | 160 | 83.33% | 0
2014-03-01 | 90% | 514 | 459 | 89.3% | 33 | 31 | 93.94% | 111 | 99 | 89.19% | 197 | 181 | 91.88% | 173 | 148 | 85.55% | 1
2014-04-01 | 90% | 585 | 495 | 84.62% | 32 | 28 | 87.5% | 128 | 117 | 91.41% | 252 | 227 | 90.08% | 173 | 123 | 71.1% | 0
2014-05-01 | 90% | 616 | 511 | 82.95% | 19 | 15 | 78.95% | 184 | 142 | 77.17% | 265 | 239 | 90.19% | 148 | 115 | 77.7% | 1
2014-06-01 | 90% | 665 | 578 | 86.92% | 36 | 34 | 94.44% | 141 | 117 | 82.98% | 278 | 238 | 85.61% | 210 | 189 | 90% | 0
2014-07-01 | 90% | 547 | 514 | 93.97% | 20 | 17 | 85% | 134 | 126 | 94.03% | 194 | 186 | 95.88% | 199 | 185 | 92.96% | 0
2014-08-01 | 90% | 633 | 585 | 92.42% | 34 | 32 | 94.12% | 127 | 116 | 91.34% | 209 | 191 | 91.39% | 263 | 246 | 93.54% | 1
Engineering - Maintenance
Month | Total # | < 30 Days | 31-60 Days | 61-90 Days | 91-180 Days | 181-365 Days | >365 Days
2012-06-01 | 615 | 358 | 83 | 76 | 48 | 44 | 6
2012-07-01 | 700 | 380 | 165 | 53 | 43 | 53 | 6
2012-08-01 | 697 | 339 | 107 | 154 | 41 | 50 | 6
2012-09-01 | 611 | 279 | 60 | 36 | 175 | 46 | 15
2012-10-01 | 299 | 252 | 34 | 7 | 5 | 1 | 0
2012-11-01 | 311 | 191 | 90 | 21 | 9 | 0 | 0
2012-12-01 | 290 | 166 | 57 | 47 | 20 | 0 | 0
2013-01-01 | 346 | 225 | 52 | 18 | 49 | 2 | 0
2013-02-01 | 377 | 198 | 81 | 37 | 57 | 2 | 2
2013-03-01 | 286 | 163 | 53 | 31 | 32 | 5 | 2
2013-04-01 | 285 | 226 | 27 | 24 | 4 | 2 | 2
2013-05-01 | 533 | 438 | 52 | 19 | 20 | 2 | 2
2013-06-01 | 461 | 241 | 150 | 34 | 30 | 3 | 3
2013-07-01 | 531 | 350 | 60 | 86 | 31 | 3 | 1
2013-08-01 | 644 | 450 | 130 | 18 | 42 | 3 | 1
2013-09-01 | 502 | 301 | 152 | 46 | 2 | 1 | 0
2013-10-01 | 342 | 313 | 18 | 6 | 4 | 1 | 0
2013-11-01 | 279 | 182 | 72 | 16 | 8 | 1 | 0
2013-12-01 | 285 | 192 | 48 | 40 | 5 | 0 | 0
2014-01-01 | 395 | 245 | 73 | 38 | 39 | 0 | 0
2014-02-01 | 309 | 167 | 59 | 27 | 55 | 1 | 0
2014-03-01 | 322 | 135 | 74 | 47 | 63 | 3 | 0
2014-04-01 | 369 | 228 | 26 | 41 | 44 | 30 | 0
2014-05-01 | 346 | 257 | 34 | 13 | 18 | 24 | 0
2014-06-01 | 248 | 198 | 43 | 3 | 2 | 2 | 0
2014-07-01 | 232 | 128 | 78 | 19 | 5 | 2 | 0
2014-08-01 | 333 | 236 | 32 | 49 | 14 | 2 | 0

## Grounds
Grounds Maintenance | Goal | Total # |  | > 30 Days Old
2012-01-01 |  | 12 |  | 11 | 91.67%
2012-02-01 |  | 14 |  | 13 | 92.86%
2012-03-01 |  | 10 |  | 6 | 60%
2012-04-01 |  | 7 |  | 6 | 85.71%
2012-05-01 |  | 7 |  | 3 | 42.86%
2012-06-01 |  | 7 |  | 2 | 28.57%
2012-07-01 |  | 6 |  | 0 | 0%
2012-08-01 |  | 7 |  | 4 | 57.14%
2012-09-01 |  | 2 |  | 1 | 50%
2012-10-01 |  | 5 |  | 1 | 20%
2012-11-01 |  | 2 |  | 1 | 50%
2012-12-01 |  | 1 |  | 1 | 100%
2013-01-01 |  | 0 |  | 0 | 0%
2013-02-01 |  | 4 |  | 1 | 25%
2013-03-01 |  | 11 |  | 4 | 36.36%
2013-04-01 |  | 3 |  | 0 | 0%
2013-05-01 |  | 4 |  | 1 | 25%
2013-06-01 |  | 7 |  | 0 | 0%
2013-07-01 |  | 1 |  | 1 | 100%
2013-08-01 |  | 6 |  | 1 | 16.67%
2013-09-01 |  | 1 |  | 0 | 0%
2013-10-01 |  | 4 |  | 0 | 0%
2013-11-01 |  | 1 |  | 0 | 0%
2013-12-01 |  | 1 |  | 0 | 0%
2014-01-01 |  | 0 |  | 0 | #DIV/0!
2014-02-01 |  | 1 |  | 0 | 0%
2014-03-01 |  | 0 |  | 0 | #DIV/0!
2014-04-01 |  | 2 |  | 0 | 0%
2014-05-01 |  | 0 |  | 0 | #DIV/0!
2014-06-01 |  | 1 |  | 0 | 0%
2014-07-01 |  | 3 |  | 0 | 0%
2014-08-01 |  | 4 |  | 1 | 25%
| Goal | Total completed | Total completed on time | Actual | Total completed | Total completed on time | Emergency | Total completed | Total completed on time | High | Total completed | Total completed on time | Medium | Total completed | Total completed on time | Low | Routine
2011-10-01 | 90% | 15 | 8 | 53.33% |  |  | - |  |  | 0% |  |  | 40% |  |  | 70%
2011-11-01 | 90% | 8 | 4 | 50% |  |  | - |  |  | 0% |  |  | 35% |  |  | 57%
2011-12-01 | 90% | 10 | 6 | 60% |  |  | - |  |  | 0% |  |  | 45% |  |  | 60%
2012-01-01 | 90% | 1 | 1 | 100% |  |  | - |  |  | - |  |  | - |  |  | 100%
2012-02-01 | 90% | 0 | 0 | 0% |  |  | - |  |  | - |  |  | - |  |  | -
2012-03-01 | 90% | 0 | 0 | 0% |  |  | - |  |  | - |  |  | - |  |  | -
2012-04-01 | 90% | 12 | 8 | 66.67% | 1 | 0 | 0% | 2 | 1 | 50% | 1 | 1 | 100% | 8 | 6 | 75%
2012-05-01 | 90% | 11 | 2 | 18.18% | 0 | 0 | 0% | 1 | 0 | 0% | 0 | 0 | 0% | 10 | 2 | 20%
2012-06-01 | 90% | 6 | 4 | 66.67% | 0 | 0 | 0% | 1 | 0 | 0% | 0 | 0 | 0% | 5 | 4 | 80% | 0
2012-07-01 | 90% | 7 | 4 | 57.14% | 0 | 0 | 0% | 2 | 0 | 0% | 2 | 2 | 0% | 3 | 2 | 66.67% | 10
2012-08-01 | 90% | 9 | 7 | 77.78% | 0 | 0 | 0% | 0 | 0 | 0% | 1 | 0 | 0% | 8 | 7 | 87.5% | 2
2012-09-01 | 90% | 12 | 8 | 66.67% | 1 | 0 | 0% | 0 | 0 | 0% | 1 | 1 | 0% | 10 | 7 | 70% | 0
2012-10-01 | 90% | 7 | 5 | 71.43% | 0 | 0 | 0% | 1 | 1 | 100% | 0 | 0 | 0% | 6 | 4 | 66.67% | 0
2012-11-01 | 90% | 12 | 8 | 66.67% | 0 | 0 | 0% | 0 | 0 | 0% | 1 | 0 | 0% | 11 | 8 | 72.73% | 0
2012-12-01 | 90% | 6 | 5 | 83.33% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 6 | 5 | 83.33% | 0
2013-01-01 | 90% | 9 | 8 | 88.89% | 0 | 0 | 0% | 1 | 1 | 100% | 0 | 0 | 0% | 8 | 7 | 87.5% | 0
2013-02-01 | 90% | 5 | 4 | 80% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 5 | 4 | 80% | 0
2013-03-01 | 90% | 47 | 7 | 14.89% | 1 | 0 | 0% | 1 | 0 | 0% | 1 | 1 | 100% | 44 | 6 | 13.64% | 1
2013-04-01 | 90% | 17 | 14 | 82.35% | 0 | 0 | 0% | 1 | 1 | 0% | 1 | 1 | 100% | 15 | 12 | 80% | 3
2013-05-01 | 90% | 14 | 12 | 85.71% | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 100% | 12 | 10 | 83.33% | 9
2013-06-01 | 90% | 37 | 35 | 94.59% | 1 | 1 | 100% | 1 | 1 | 100% | 1 | 1 | 100% | 34 | 32 | 94.12% | 23
2013-07-01 | 90% | 28 | 28 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 27 | 27 | 100% | 1
2013-08-01 | 90% | 16 | 13 | 81.25% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 5 | 5 | 100% | 11 | 8 | 72.73% | 0
2013-09-01 | 90% | 12 | 6 | 50% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 3 | 0 | 0% | 8 | 5 | 62.5% | 0
2013-10-01 | 90% | 5 | 5 | 100% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 1 | 1 | 100% | 3 | 3 | 100% | 1
2013-11-01 | 90% | 6 | 3 | 50% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 6 | 3 | 50% | 5
2013-12-01 | 90% | 2 | 2 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 2 | 2 | 100% | 1
2014-01-01 | 90% | 4 | 4 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 4 | 4 | 100% | 0
2014-02-01 | 90% | 2 | 1 | 50% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 2 | 1 | 50% | 1
2014-03-01 | 90% | 2 | 1 | 50% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 2 | 1 | 50% | 0
2014-04-01 | 90% | 2 | 2 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 1 | 1 | 100% | 0
2014-05-01 | 90% | 1 | 1 | 100% | 1 | 1 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0
2014-06-01 | 90% | 4 | 4 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 3 | 3 | 100% | 1
2014-07-01 | 90% | 4 | 4 | 100% | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 3 | 3 | 100% | 0
2014-08-01 | 90% | 11 | 10 | 90.91% | 0 | 0 | #DIV/0! | 1 | 1 | 100% | 0 | 0 | #DIV/0! | 10 | 9 | 90% | 0
Grounds
| Month | Total # | < 30 Days | 31-60 Days | 61-90 Days | 91-180 Days | 181-365 Days | >365 Days
| 2012-06-01 | 7 | 5 | 0 | 1 | 0 | 1 | 0
| 2012-07-01 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 2012-08-01 | 7 | 3 | 3 | 1 | 0 | 0 | 0
| 2012-09-01 | 2 | 1 | 1 | 0 | 0 | 0 | 1
| 2012-10-01 | 5 | 4 | 0 | 1 | 0 | 0 | 0
| 2012-11-01 | 2 | 1 | 1 | 0 | 0 | 0 | 0
| 2012-12-01 | 1 | 0 | 0 | 0 | 1 | 0 | 0
| 2013-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2013-02-01 | 4 | 3 | 1 | 0 | 0 | 0 | 0
| 2013-03-01 | 11 | 7 | 3 | 1 | 0 | 0 | 0
| 2013-04-01 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 2013-05-01 | 4 | 3 | 0 | 1 | 0 | 0 | 0
| 2013-06-01 | 7 | 7 | 0 | 0 | 0 | 0 | 0
| 2013-07-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2013-08-01 | 6 | 5 | 0 | 1 | 0 | 0 | 0
| 2013-09-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2013-10-01 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| 2013-11-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2013-12-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2014-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2014-02-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2014-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2014-04-01 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| 2014-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2014-06-01 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| 2014-07-01 | 3 | 3 | 0 | 0 | 0 | 0 | 0
| 2014-08-01 | 4 | 3 | 1 | 0 | 0 | 0 | 0

## Trades
Month | Goal | Total # |  | > 30 Days Old
2012-01-01 | 300 | 632 |  | 244 | 38.61%
2012-02-01 | 300 | 641 |  | 197 | 30.73%
2012-03-01 | 300 | 653 |  | 248 | 37.98%
2012-04-01 | 300 | 541 |  | 173 | 31.98%
2012-05-01 | 300 | 437 |  | 298 | 68.19%
2012-06-01 | 300 | 559 |  | 205 | 36.67%
2012-07-01 | 300 | 640 |  | 241 | 37.66%
2012-08-01 | 300 | 722 |  | 348 | 48.2%
2012-09-01 | 300 | 569 |  | 259 | 45.52%
2012-10-01 | 300 | 402 |  | 106 | 26.37%
2012-11-01 | 300 | 451 |  | 111 | 24.61%
2012-12-01 | 300 | 341 |  | 133 | 39%
2013-01-01 | 300 | 545 |  | 123 | 22.57%
2013-02-01 | 300 | 460 |  | 107 | 23.26%
2013-03-01 | 300 | 468 |  | 87 | 18.59%
2013-04-01 | 300 | 388 |  | 86 | 22.16%
2013-05-01 | 300 | 410 |  | 58 | 14.15%
2013-06-01 | 300 | 453 |  | 86 | 18.98%
2013-07-01 | 300 | 384 |  | 72 | 18.75%
2013-08-01 | 300 | 350 |  | 60 | 17.14%
2013-09-01 | 300 | 356 |  | 79 | 22.19%
2013-10-01 | 300 | 469 |  | 78 | 16.63%
2013-11-01 | 300 | 472 |  | 101 | 21.4%
2013-12-01 | 300 | 350 |  | 148 | 42.29%
2014-01-01 | 300 | 593 |  | 164 | 27.66%
2014-02-01 | 300 | 637 |  | 216 | 33.91%
2014-03-01 | 300 | 580 |  | 231 | 39.83%
2014-04-01 | 300 | 621 |  | 244 | 39.29%
2014-05-01 | 300 | 501 |  | 181 | 36.13%
2014-06-01 | 300 | 480 |  | 169 | 35.21%
2014-07-01 | 300 | 573 |  | 257 | 44.85%
2014-08-01 | 300 | 682 |  | 309 | 45.31%
Month | Goal | Total completed | Total completed on time | Actual | Total completed | Total completed on time | Emergency | Total completed | Total completed on time | High | Total completed | Total completed on time | Medium | Total completed | Total completed on time | Low | Routine
2011-10-01 | 90% | 807 | 598 | 74.1% | 36 | 28 | 77.78% | 143 | 91 | 63.64% | 167 | 125 | 74.85% | 461 | 354 | 76.79%
2011-11-01 | 90% | 773 | 588 | 76.07% | 50 | 39 | 78% | 116 | 60 | 51.72% | 139 | 110 | 79.14% | 468 | 379 | 80.98%
2011-12-01 | 90% | 775 | 584 | 75.35% | 47 | 34 | 72.34% | 146 | 86 | 58.9% | 131 | 96 | 73.28% | 451 | 368 | 81.6%
2012-01-01 | 90% | 951 | 700 | 73.61% | 62 | 50 | 80.65% | 165 | 96 | 58.18% | 172 | 121 | 70.35% | 552 | 433 | 78.44%
2012-02-01 | 90% | 957 | 813 | 84.95% |  |  | 85% |  |  | 65% |  |  | 87% |  |  | 89%
2012-03-01 | 90% | 826 | 615 | 74.46% | 56 | 45 | 80.36% | 159 | 98 | 61.64% | 161 | 107 | 66.46% | 450 | 365 | 81.11%
2012-04-01 | 90% | 816 | 600 | 73.53% | 45 | 32 | 71.11% | 173 | 99 | 57.23% | 150 | 102 | 68% | 448 | 367 | 81.92%
2012-05-01 | 90% | 716 | 551 | 76.96% | 57 | 46 | 80.7% | 116 | 71 | 61.21% | 152 | 102 | 67.11% | 391 | 332 | 84.91%
2012-06-01 | 90% | 657 | 539 | 82.04% | 50 | 44 | 88% | 101 | 73 | 72.28% | 120 | 88 | 73.33% | 386 | 334 | 86.53% | 7
2012-07-01 | 90% | 480 | 358 | 74.58% | 34 | 24 | 70.59% | 112 | 76 | 67.86% | 101 | 85 | 84.16% | 233 | 173 | 74.25% | 96
2012-08-01 | 90% | 819 | 679 | 82.91% | 44 | 40 | 90.91% | 163 | 116 | 71.17% | 159 | 121 | 76.1% | 453 | 402 | 88.74% | 29
2012-09-01 | 90% | 956 | 621 | 64.96% | 49 | 30 | 61.22% | 233 | 122 | 52.36% | 246 | 141 | 57.32% | 428 | 328 | 76.64% | 31
2012-10-01 | 90% | 1081 | 707 | 65.4% | 55 | 25 | 45.45% | 231 | 125 | 54.11% | 263 | 178 | 67.68% | 532 | 379 | 71.24% | 22
2012-11-01 | 90% | 923 | 689 | 74.65% | 48 | 28 | 58.33% | 181 | 114 | 62.98% | 208 | 152 | 73.08% | 486 | 395 | 81.28% | 29
2012-12-01 | 90% | 697 | 505 | 72.45% | 20 | 12 | 60% | 164 | 83 | 50.61% | 147 | 104 | 70.75% | 366 | 306 | 83.61% | 28
2013-01-01 | 90% | 850 | 677 | 79.65% | 88 | 67 | 76.14% | 212 | 165 | 77.83% | 188 | 143 | 76.06% | 362 | 302 | 83.43% | 32
2013-02-01 | 90% | 918 | 735 | 80.07% | 50 | 50 | 100% | 221 | 171 | 77.38% | 188 | 143 | 76.06% | 459 | 371 | 80.83% | 24
2013-03-01 | 90% | 931 | 785 | 84.32% | 66 | 65 | 98.48% | 191 | 162 | 84.82% | 214 | 176 | 82.24% | 460 | 382 | 83.04% | 29
2013-04-01 | 90% | 985 | 818 | 83.05% | 71 | 69 | 97.18% | 176 | 136 | 77.27% | 198 | 170 | 85.86% | 540 | 443 | 82.04% | 30
2013-05-01 | 90% | 911 | 804 | 88.25% | 59 | 55 | 93.22% | 181 | 144 | 79.56% | 178 | 158 | 88.76% | 493 | 447 | 90.67% | 27
2013-06-01 | 90% | 835 | 730 | 87.43% | 47 | 45 | 95.74% | 148 | 124 | 83.78% | 142 | 125 | 88.03% | 498 | 436 | 87.55% | 23
2013-07-01 | 90% | 942 | 801 | 85.03% | 71 | 68 | 95.77% | 213 | 165 | 77.46% | 221 | 195 | 88.24% | 437 | 373 | 85.35% | 36
2013-08-01 | 90% | 922 | 784 | 85.03% | 52 | 47 | 90.38% | 189 | 158 | 83.6% | 197 | 168 | 85.28% | 484 | 411 | 84.92% | 32
2013-09-01 | 90% | 839 | 727 | 86.65% | 73 | 68 | 93.15% | 194 | 159 | 81.96% | 190 | 167 | 87.89% | 382 | 333 | 87.17% | 29
2013-10-01 | 90% | 943 | 819 | 86.85% | 86 | 80 | 93.02% | 251 | 209 | 83.27% | 176 | 154 | 87.5% | 430 | 376 | 87.44% | 35
2013-11-01 | 90% | 848 | 711 | 83.84% | 84 | 73 | 86.9% | 190 | 137 | 72.11% | 189 | 157 | 83.07% | 385 | 344 | 89.35% | 46
2013-12-01 | 90% | 895 | 709 | 79.22% | 109 | 95 | 87.16% | 213 | 144 | 67.61% | 164 | 129 | 78.66% | 409 | 341 | 83.37% | 28
2014-01-01 | 90% | 857 | 671 | 78.3% | 164 | 140 | 85.37% | 209 | 146 | 69.86% | 167 | 125 | 74.85% | 317 | 260 | 82.02% | 28
2014-02-01 | 90% | 847 | 666 | 78.63% | 101 | 68 | 67.33% | 215 | 147 | 68.37% | 173 | 132 | 76.3% | 358 | 319 | 89.11% | 24
2014-03-01 | 90% | 1039 | 823 | 79.21% | 86 | 72 | 83.72% | 232 | 156 | 67.24% | 189 | 156 | 82.54% | 532 | 473 | 88.91% | 22
2014-04-01 | 90% | 1017 | 784 | 77.09% | 96 | 82 | 85.42% | 259 | 185 | 71.43% | 165 | 109 | 66.06% | 497 | 408 | 82.09% | 37
2014-05-01 | 90% | 1012 | 792 | 78.26% | 91 | 81 | 89.01% | 244 | 172 | 70.49% | 176 | 121 | 68.75% | 501 | 418 | 83.43% | 39
2014-06-01 | 90% | 963 | 791 | 82.14% | 81 | 73 | 90.12% | 182 | 112 | 61.54% | 173 | 135 | 78.03% | 527 | 471 | 89.37% | 28
2014-07-01 | 90% | 799 | 664 | 83.1% | 82 | 70 | 85.37% | 149 | 112 | 75.17% | 137 | 109 | 79.56% | 431 | 373 | 86.54% | 28
2014-08-01 | 90% | 943 | 794 | 84.2% | 62 | 55 | 88.71% | 186 | 135 | 72.58% | 154 | 120 | 77.92% | 541 | 484 | 89.46% | 28
| Month | Trades
|  | Total # | < 30 Days | 31-60 Days | 61-90 Days | 91-180 Days | 181-365 Days | >365 Days
| 2012-06-01 | 559 | 210 | 0 | 25 | 22 | 5 | 4
| 2012-07-01 | 640 | 339 | 114 | 47 | 47 | 19 | 14
| 2012-08-01 | 722 | 374 | 169 | 84 | 67 | 26 | 2
| 2012-09-01 | 569 | 310 | 150 | 73 | 35 | 1 | 0
| 2012-10-01 | 402 | 296 | 66 | 29 | 11 | 0 | 0
| 2012-11-01 | 451 | 340 | 85 | 26 | 0 | 0 | 0
| 2012-12-01 | 341 | 208 | 93 | 34 | 6 | 0 | 0
| 2013-01-01 | 545 | 422 | 89 | 34 | 0 | 0 | 0
| 2013-02-01 | 460 | 353 | 107 | 0 | 0 | 0 | 0
| 2013-03-01 | 468 | 381 | 87 | 0 | 0 | 0 | 0
| 2013-04-01 | 388 | 302 | 86 | 0 | 0 | 0 | 0
| 2013-05-01 | 410 | 352 | 57 | 1 | 0 | 0 | 0
| 2013-06-01 | 453 | 367 | 85 | 1 | 0 | 0 | 0
| 2013-07-01 | 384 | 312 | 71 | 1 | 0 | 0 | 0
| 2013-08-01 | 350 | 290 | 60 | 0 | 0 | 0 | 0
| 2013-09-01 | 356 | 277 | 79 | 0 | 0 | 0 | 0
| 2013-10-01 | 469 | 391 | 69 | 9 | 0 | 0 | 0
| 2013-11-01 | 472 | 371 | 92 | 8 | 1 | 0 | 0
| 2013-12-01 | 350 | 202 | 113 | 31 | 4 | 0 | 0
| 2014-01-01 | 593 | 429 | 98 | 49 | 17 | 0 | 0
| 2014-02-01 | 637 | 421 | 132 | 43 | 40 | 1 | 0
| 2014-03-01 | 580 | 349 | 141 | 60 | 29 | 1 | 0
| 2014-04-01 | 621 | 377 | 134 | 61 | 46 | 3 | 0
| 2014-05-01 | 501 | 320 | 117 | 41 | 14 | 9 | 0
| 2014-06-01 | 480 | 311 | 98 | 28 | 38 | 5 | 0
| 2014-07-01 | 573 | 316 | 109 | 84 | 55 | 9 | 0
| 2014-08-01 | 682 | 373 | 119 | 88 | 91 | 10 | 1

## PM3
Month | 80% | 95% | 100% | Work Not Done
2014-06-14 | 76 | 81 |  | 21
2014-07-14 | 71 | 91 |  | 18
2014-08-14 | 82 |  |  | 5
Engineering PM
Month | Total # |  | < 30 Days | 30-60 Days | 61- 90 Days | 91-180 Days | 181-365 Days | >365 Days
June 2012 | 678 |  | 520 | 101 | 29 | 22 | 0 | 6
July | 435 |  | 231 | 121 | 35 | 44 | 0 | 4
Aug | 915 |  | 614 | 116 | 113 | 66 | 1 | 5
Sept | 973 |  | 628 | 90 | 105 | 133 | 12 | 5
Oct | 772 |  | 606 | 74 | 16 | 58 | 18 | 0
Nov | 603 |  | 341 | 197 | 20 | 30 | 15 | 0
Dec | 711 |  | 454 | 75 | 102 | 66 | 8 | 6
Jan 2013 | 209 |  | 131 | 32 | 15 | 39 | 0 | 8
Feb | 149 |  | 112 | 20 | 9 | 7 | 0 | 1
Mar | 243 |  | 234 | 10 | 1 | 1 | 0 | 0
April | 395 |  | 268 | 125 | 2 | 0 | 0 | 0
May | 512 |  | 268 | 148 | 95 | 1 | 0 | 0
June | 588 |  | 284 | 140 | 97 | 67 | 0 | 0
July | 491 |  | 287 | 137 | 67 | 0 | 0 | 0
Aug | 591 |  | 279 | 118 | 130 | 64 | 0 | 0
Sept | 563 |  | 272 | 162 | 91 | 38 | 0 | 0
Oct | 410 |  | 361 | 49 | 0 | 0 | 0 | 0
Nov | 304 |  | 131 | 173 | 0 | 0 | 0 | 0
Dec | 834 |  | 239 | 318 | 225 | 52 | 0 | 0
Jan 2014 | 733 |  | 241 | 125 | 219 | 148 | 0 | 0
Feb | 519 |  | 77 | 79 | 119 | 244 | 0 | 0
March | 474 |  | 187 | 43 | 57 | 181 | 6 | 0
April | 648 |  | 273 | 128 | 32 | 155 | 60 | 0
May | 730 |  | 189 | 192 | 86 | 121 | 142 | 0
June | 245 |  | 106 | 79 | 49 | 11 | 0 | 0
July | 280 |  | 144 | 56 | 15 | 64 | 1 | 0
August | 162 |  | 70 | 13 | 26 | 52 | 1 | 0

## PM2
Engineering Preventive Maintenance | Goal | Total # |  | > 30 Days Old
2012-01-01 |  | 223 |  | 86 | 38.57%
2012-02-01 |  | 104 |  | 40 | 38.46%
2012-03-01 |  | 1152 |  | 814 | 70.66%
2012-04-01 |  | 1397 |  | 836 | 59.84%
2012-05-01 |  | 448 |  | 381 | 85.04%
2012-06-01 |  | 678 |  | 158 | 23.3%
2012-07-01 |  | 435 |  | 204 | 46.9%
2012-08-01 |  | 915 |  | 301 | 32.9%
2012-09-01 |  | 973 |  | 345 | 35.46%
2012-10-01 |  | 722 |  | 166 | 22.99%
2012-11-01 |  | 603 |  | 262 | 43.45%
2012-12-01 |  | 711 |  | 257 | 36.15%
2013-01-01 |  | 209 |  | 94 | 44.98%
2013-02-01 |  | 149 |  | 37 | 24.83%
2013-03-01 |  | 243 |  | 12 | 4.938%
2013-04-01 |  | 395 |  | 127 | 32.15%
2013-05-01 |  | 512 |  | 244 | 47.66%
2013-06-01 |  | 588 |  | 304 | 51.7%
2013-07-01 |  | 491 |  | 204 | 41.55%
2013-08-01 |  | 591 |  | 312 | 52.79%
2013-09-01 |  | 563 |  | 291 | 51.69%
2013-10-01 |  | 410 |  | 49 | 11.95%
2013-11-01 |  | 304 |  | 173 | 56.91%
2013-12-01 |  | 834 |  | 595 | 71.34%
2014-01-01 |  | 734 |  | 493 | 67.17%
2014-02-01 |  | 519 |  | 442 | 85.16%
2014-03-01 |  | 474 |  | 287 | 60.55%
2014-04-01 |  | 648 |  | 389 | 60.03%
2014-05-01 |  | 730 |  | 541 | 74.11%
2014-06-01 |  | 245 |  | 139 | 56.73%
| Goal | Total completed | Total completed on time | Actual
2011-10-01 | 90% | 231 |  | 23%
2011-11-01 | 90% | 133 |  | 45%
2011-12-01 | 90% | 177 |  | 5%
2012-01-01 | 90% | 223 |  | 42%
2012-02-01 | 90% | 213 |  | 89%
2012-03-01 | 90% | 565 |  | 59%
2012-04-01 | 90% | 496 |  | 91%
2012-05-01 | 90% | 166 |  | 61%
2012-06-01 | 90% | 458 |  | 62%
2012-07-01 | 90% | 301 |  | 78%
2012-08-01 | 90% | 379 |  | 82%
2012-09-01 | 90% | 330 |  | 78%
2012-10-01 | 90% | 492 | 415 | 84.35%
2012-11-01 | 90% | 428 | 308 | 71.96%
2012-12-01 | 90% | 289 | 220 | 76.12%
2013-01-01 | 90% | 330 | 245 | 74.24%
2013-02-01 | 90% | 426 | 268 | 62.91%
2013-03-01 | 90% | 452 | 326 | 72.12%
2013-04-01 | 90% | 506 | 439 | 86.76%
2013-05-01 | 90% | 618 | 534 | 86.41%
2013-06-01 | 90% | 435 | 289 | 66.44%
2013-07-01 | 90% | 415 | 348 | 83.86%
2013-08-01 | 90% | 470 | 403 | 85.74%
2013-09-01 | 90% | 322 | 236 | 73.29%
2013-10-01 | 90% | 359 | 277 | 77.16%
2013-11-01 | 90% | 309 | 199 | 64.4%
2013-12-01 | 90% | 252 | 125 | 49.6%
2014-01-01 | 90% | 302 | 88 | 29.14%
2014-02-01 | 90% | 283 | 118 | 41.7%
2014-03-01 | 90% | 473 | 224 | 47.36%
2014-04-01 | 90% | 238 | 117 | 49.16%
2014-05-01 | 90% | 720 | 467 | 64.86%
2014-06-01 | 90% | 542 | 413 | 76.2%
Engineering PM
Month | Total # | < 30 Days | 30-60 Days | 61- 90 Days | 91-180 Days | 181-365 Days | >365 Days
June 2012 | 678 | 520 | 101 | 29 | 22 | 0 | 6
July | 435 | 231 | 121 | 35 | 44 | 0 | 4
Aug | 915 | 614 | 116 | 113 | 66 | 1 | 5
Sept | 973 | 628 | 90 | 105 | 133 | 12 | 5
Oct | 772 | 606 | 74 | 16 | 58 | 18 | 0
Nov | 603 | 341 | 197 | 20 | 30 | 15 | 0
Dec | 711 | 454 | 75 | 102 | 66 | 8 | 6
Jan 2013 | 209 | 131 | 32 | 15 | 39 | 0 | 8
Feb | 149 | 112 | 20 | 9 | 7 | 0 | 1
Mar | 243 | 234 | 10 | 1 | 1 | 0 | 0
April | 395 | 268 | 125 | 2 | 0 | 0 | 0
May | 512 | 268 | 148 | 95 | 1 | 0 | 0
June | 588 | 284 | 140 | 97 | 67 | 0 | 0
July | 491 | 287 | 137 | 67 | 0 | 0 | 0
Aug | 591 | 279 | 118 | 130 | 64 | 0 | 0
Sept | 563 | 272 | 162 | 91 | 38 | 0 | 0
Oct | 410 | 361 | 49 | 0 | 0 | 0 | 0
Nov | 304 | 131 | 173 | 0 | 0 | 0 | 0
Dec | 834 | 239 | 318 | 225 | 52 | 0 | 0
Jan 2014 | 733 | 241 | 125 | 219 | 148 | 0 | 0
Feb | 519 | 77 | 79 | 119 | 244 | 0 | 0
March | 474 | 187 | 43 | 57 | 181 | 6 | 0
April | 648 | 273 | 128 | 32 | 155 | 60 | 0
May | 730 | 189 | 192 | 86 | 121 | 142 | 0
June | 245 | 106 | 79 | 49 | 11 | 0 | 0

## PM
Engineering Preventive Maintenance | Goal | Total # |  | > 30 Days Old
2012-01-01 |  | 223 |  | 86 | 38.57%
2012-02-01 |  | 104 |  | 40 | 38.46%
2012-03-01 |  | 1152 |  | 814 | 70.66%
2012-04-01 |  | 1397 |  | 836 | 59.84%
2012-05-01 |  | 448 |  | 381 | 85.04%
2012-06-01 |  | 678 |  | 158 | 23.3%
2012-07-01 |  | 435 |  | 204 | 46.9%
2012-08-01 |  | 915 |  | 301 | 32.9%
2012-09-01 |  | 973 |  | 345 | 35.46%
2012-10-01 |  | 722 |  | 166 | 22.99%
2012-11-01 |  | 603 |  | 262 | 43.45%
2012-12-01 |  | 711 |  | 257 | 36.15%
2013-01-01 |  | 807 |  | 204 | 25.28%
2013-02-01 |  | 761 |  | 139 | 18.27%
2013-03-01 |  | 882 |  | 116 | 13.15%
2013-04-01 |  | 1033 |  | 199 | 19.26%
2013-05-01 |  | 1075 |  | 309 | 28.74%
2013-06-01 |  | 588 |  | 304 | 51.7%
Yellow highlight indicates new KPI measurement based on DUE DATE
| Goal | Total completed | Total completed on time | Actual
2011-10-01 | 90% | 231 |  | 23%
2011-11-01 | 90% | 133 |  | 45%
2011-12-01 | 90% | 177 |  | 5%
2012-01-01 | 90% | 223 |  | 42%
2012-02-01 | 90% | 213 |  | 89%
2012-03-01 | 90% | 565 |  | 59%
2012-04-01 | 90% | 496 |  | 91%
2012-05-01 | 90% | 166 |  | 61%
2012-06-01 | 90% | 458 |  | 62%
2012-07-01 | 90% | 301 |  | 78%
2012-08-01 | 90% | 379 |  | 82%
2012-09-01 | 90% | 330 |  | 78%
2012-10-01 | 90% | 492 | 415 | 84.35%
2012-11-01 | 90% | 428 | 308 | 71.96%
2012-12-01 | 90% | 289 | 220 | 76.12%
2013-01-01 | 90% | 308 | 226 | 73.38%
2013-02-01 | 90% | 378 | 223 | 58.99%
2013-03-01 | 90% | 453 | 333 | 73.51%
2013-04-01 | 90% | 452 | 411 | 90.93%
2013-05-01 | 90% | 590 | 534 | 90.51%
2013-06-01 | 90% | 542 | 413 | 76%
2013-07-01 | 90% | 547 | 444 | 81%
Engineering PM
Month | Total # | < 30 Days | 30-60 Days | 61- 90 Days | 91-180 Days | 181-365 Days | >365 Days
June 2012 | 678 | 520 | 101 | 29 | 22 | 0 | 6
July | 435 | 231 | 121 | 35 | 44 | 0 | 4
Aug | 915 | 614 | 116 | 113 | 66 | 1 | 5
Sept | 973 | 628 | 90 | 105 | 133 | 12 | 5
Oct | 772 | 606 | 74 | 16 | 58 | 18 | 0
Nov | 603 | 341 | 197 | 20 | 30 | 15 | 0
Dec | 711 | 454 | 75 | 102 | 66 | 8 | 6
Jan 2013 | 807 | 603 | 47 | 50 | 107 | 0 | 0
Feb | 761 | 622 | 90 | 35 | 14 | 0 | 0
Mar | 882 | 766 | 37 | 47 | 32 | 0 | 0
April | 1033 | 834 | 143 | 28 | 25 | 3 | 0
May | 1075 | 766 | 156 | 109 | 44 | 0 | 0
June | 588 | 284 | 140 | 97 | 67 | 0 | 0

## D&CS P&E (2)
Planning and Estimating
Month | % complete on time (estimates, planning) | Goal
2014-01-01 | 78.6% | 90%
2014-02-01 | 100% | 90%
2014-03-01 | 87% | 90%
2014-04-01 | 52.9% | 90%
2014-05-01 | 52.9% | 90%
2014-06-01 | 76% | 90%
2014-07-01 | 54.8% | 90%
2014-08-01 | 54.8% | 90%
2014-09-01 | 80.1% | 90%

## D&CS P&E
Age distribution - number of days estimate to customer
Cost Estimates to Customer | % in 30 days or less | Goal | Avg # of Days to Customer | # of Estimates to customer | Estimates that took 30 days or less to customer | 1-10 days | 11-20 days | 21-30 days | 31-60 days | 61-90 days | >91
2011-11-01 |  | 90% | 0 | 0
2011-12-01 |  | 90% | 0 | 0
2012-01-01 |  | 90% | 0 | 0
2012-02-01 | 75% | 90% | 32.3 | 5
2012-03-01 | 83% | 90% | 27 | 12
2012-04-01 | 50% | 90% | 26 | 2
2012-05-01 | 55.6% | 90% | 28.2 | 5
2012-06-01 | 60% | 90% | 18 | 3
2012-07-01 | 22% | 90% | 66 | 9 | 2 | 0 | 6 | 8 | 8 | 3 | 2
2012-08-01 | 25% | 90% | 48 | 12 | 3 | 0 | 0 | 3 | 8 | 0 | 1
2012-09-01 | 27.3% | 90% | 68 | 11 | 3 | 0 | 0 | 3 | 3 | 2 | 3
2012-10-01 | 90.9% | 90% | 34 | 11 | 10 | 0 | 1 | 9 | 0 | 0 | 1
2012-11-01 | 85.7% | 90% | 28 | 7 | 6 | 1 | 0 | 5 | 1 | 0 | 0
2012-12-01 | 100% | 90% | 9 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
2013-01-01 | 20% | 90% | 61 | 5 | 1 | 1 | 0 | 0 | 1 | 2 | 1
2013-02-01 |  | 90% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2013-03-01 | 42.9% | 90% | 86 | 7 | 3 | 0 | 0 | 3 | 1 | 1 | 2
2013-04-01 | 55.6% | 90% | 39 | 9 | 5 | 2 | 1 | 2 | 1 | 3 | 0
2013-05-01 | 57.1% | 90% | 44 | 7 | 4 | 0 | 0 | 4 | 1 | 2 | 0
2013-06-01 |  | 90% |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2013-07-01 | 13.3% | 90% | 52 | 15 | 2 | 0 | 0 | 2 | 8 | 4 | 1
2013-08-01 | 20% | 90% | 64 | 5 | 1 | 0 | 0 | 1 | 1 | 2 | 1
2013-09-01 | 33% | 90% | 34 | 6 | 2 | 1 | 0 | 1 | 4 | 0 | 0
2013-10-01 | 25% | 90% | 62 | 8 | 2 | 0 | 0 | 2 | 2 | 2 | 2
2013-11-01 | 100% | 90% | 14 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
Month | Total backlog | 1-10 days | 11-20 days | 21-30 days | 31-60 days | 61-90 days | >91
June 2012 | 24 | 0 | 5 | 2 | 9 | 6 | 2
July | 27 | 0 | 6 | 8 | 8 | 3 | 2
Aug | 22 | 0 | 4 | 1 | 7 | 6 | 4
Sept | 15 | 4 | 4 | 2 | 1 | 0 | 4
Oct | 16 | 6 | 7 | 0 | 1 | 0 | 2
Nov | 15 | 7 | 1 | 2 | 3 | 0 | 2
Dec | 13 | 0 | 2 | 2 | 7 | 1 | 1
Jan 2013 | 14 | 4 | 2 | 2 | 2 | 2 | 2
Feb | 22 | 5 | 3 | 4 | 6 | 2 | 2
March | 21 | 14 | 0 | 0 | 7 | 0 | 0
April | 21 | 4 | 7 | 2 | 1 | 7 | 0
May | 26 | 10 | 5 | 3 | 6 | 0 | 2
June | 28 | 0 | 3 | 3 | 14 | 6 | 2
July | 21 | 0 | 1 | 3 | 6 | 6 | 5
Aug | 22 | 3 | 4 | 4 | 4 | 2 | 5
Sept | 8 | 2 | 1 | 1 | 3 | 0 | 1
Oct | 8 | 0 | 2 | 0 | 2 | 3 | 1
Nov | 18 | 1 | 6 | 6 | 1 | 1 | 3
Age distribution - number of days to estimate to customer
Cost Estimates to Customer | % in 10 days or less | Goal | Avg # of Days to Customer | # of Estimates | Estimates that took 10 days or less to customer | 1-10 days | 11-20 days | 21-30 days | 31-60 days | 61-90 days | >91
2011-11-01 | 12% | 90% | 27.4 | 14
2011-12-01 | 30% | 90% | 37.2 | 5
2012-01-01 | 14% | 90% | 31.4 | 14
2012-02-01 | 64% | 90% | 20.2 | 10
2012-03-01 | 63% | 90% | 12.6 | 16
2012-04-01 | 100% | 90% | 5.67 | 3
2012-05-01 |  | 90% | 0 | 0
2012-06-01 |  | 90% | Changed methodology, no estimator on staff. Conversation to web TMA. New estimator started July 16th.
2012-07-01 | 16.7% | 90% | 17 | 6 | 1 | 1 | 4 | 0 | 1 | 0 | 0
2012-08-01 | 12.5% | 90% | 15 | 8 | 1 | 1 | 6 | 1 | 0 | 0 | 0
2012-09-01 |  | 90% | 50 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0
2012-10-01 | 75% | 90% | 16 | 4 | 3 | 3 | 0 | 0 | 1 | 0 | 0
2012-11-01 | 50% | 90% | 29 | 4 | 2 | 2 | 1 | 0 | 0 | 1 | 0
2012-12-01 | 100% | 90% | 9 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2013-01-01 | 50% | 90% | 68 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 2
2013-02-01 | 50% | 90% | 11 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0
2013-03-01 | 75% | 90% | 24 | 4 | 3 | 3 | 0 | 0 | 0 | 1 | 0
2013-04-01 | 50% | 90% | 23 | 4 | 2 | 2 | 0 | 1 | 1 | 0 | 0
2013-05-01 | 37.5% | 90% | 21 | 8 | 3 | 3 | 3 | 0 | 2 | 0 | 0
2013-06-01 | 20% | 90% | 16 | 5 | 1 | 1 | 3 | 1 | 0 | 0 | 0
2013-07-01 | 40% | 90% | 17 | 5 | 2 | 2 | 1 | 1 | 1 | 0 | 0
2013-08-01 |  | 90% | 22 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
2013-09-01 | 20% | 90% | 18 | 5 | 1 | 1 | 3 | 0 | 1 | 0 | 0
2013-10-01 | 57% | 90% | 15 | 7 | 4 | 4 | 1 | 1 | 1 | 0 | 0
2013-11-01 |  | 90% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
age distribution
Month | Total backlog | 1-10 days | 11-20 days | 21-30 days | 31-60 days | 61-90 days | >91
June 2012 | 14 | 3 | 7 | 1 | 0 | 3 | 0
July | 15 | 4 | 3 | 5 | 1 | 2 | 0
Aug | 14 | 1 | 2 | 1 | 9 | 0 | 1
Sept | 7 | 0 | 0 | 1 | 5 | 1 | 0
Oct | 6 | 1 | 0 | 0 | 1 | 4 | 0
Nov | 5 | 0 | 1 | 0 | 0 | 1 | 3
Dec | 10 | 2 | 3 | 1 | 1 | 0 | 3
Jan 2013 | 12 | 2 | 2 | 1 | 6 | 0 | 1
Feb | 4 | 2 | 1 | 0 | 0 | 1 | 0
March | 7 | 2 | 4 | 1 | 0 | 0 | 0
April | 7 | 3 | 2 | 0 | 2 | 0 | 0
May | 6 | 1 | 1 | 0 | 0 | 0 | 0
June | 3 | 0 | 3 | 0 | 0 | 0 | 0
July | 2 | 1 | 1 | 0 | 0 | 0 | 0
Aug | 3 | 1 | 1 | 1 | 0 | 0 | 0
Sept | 1 | 0 | 1 | 0 | 0 | 0 | 0
Oct | 1 | 0 | 0 | 0 | 0 | 0 | 0
Nov | 6 | 4 | 1 | 1 | 0 | 0 | 0

## D&CS Admin
D&CS
Petition to Close Measurable (Substantial Completion date-Petition to Close date)
Month | % in 150 days or less | Goal | No of Petition to Close | No of Projects processed on time (<150 days) | Average age (days) | Target
2012-11-01 | 28.57% | 90% | 7 | 2 | 390.85 | 90
2012-12-01 | 5.882% | 90% | 17 | 1 | 417.21 | 90
2013-01-01 | 0% | 90% | 18 | 0 | 507 | 90
2013-02-01 | 0% | 90% | 38 | 0 | 473.7 | 90
2013-03-01 | 0% | 90% | 9 | 0 | 462.2 | 90
2013-04-01 | 14.29% | 90% | 7 | 1 | 251.6 | 90
2013-05-01 | 4.167% | 90% | 24 | 1 | 274.2 | 90
2013-06-01 | 7.407% | 90% | 27 | 2 | 309.4 | 90
2013-07-01 | 20% | 90% | 10 | 2 | 220.7 | 90
2013-08-01 | 27.78% | 90% | 18 | 5 | 203.7 | 90
2013-09-01 | 8.333% | 90% | 12 | 1 | 324 | 90
2013-10-01 | 0% | 90% | 6 | 0 | 425.3 | 90
2013-11-01 | 0% | 90% | 4 | 0 | 433.3 | 90
2013-12-01 | 0% | 90% | 2 | 0 | 391 | 90
2014-01-01 | 37.5% | 90% | 8 | 3 | 239.5 | 150
2014-02-01 | 0% | 90% | 2 | 0 | 429.5 | 150
2014-03-01 | 0% | 90% | 14 | 0 | 304.8 | 150
2014-04-01 | 0% | 90% | 3 | 0 | 251.3 | 150
2014-05-01 | 0% | 90% | 1 | 0 | 153 | 150
2014-06-01 | 0% | 90% | 1 | 0 | 471 | 150
2014-07-01 | 0% | 90% | 1 | 0 | 202 | 150
2014-08-01 | 0% | 90% | 0 | 0 | 0 | 150
Business Services
Plant Fund Closure Measurable (Petition to Close date -Plant Fund Closure date)
| % in 30 days or less | Goal | No of PFA Closed | No of PFA's processed on time (<30 days) | Average age (days) | Target
2012-11-01 | 6.667% | 90% | 15 | 1 | 0 | 30
2012-12-01 | 45.83% | 90% | 24 | 11 | 26.7 | 30
2013-01-01 | 69.57% | 90% | 23 | 16 | 29.3 | 30
2013-02-01 | 90.62% | 90% | 32 | 29 | 6.7 | 30
2013-03-01 | 93.33% | 90% | 15 | 14 | 13 | 30
2013-04-01 | 100% | 90% | 4 | 4 | 6.75 | 30
2013-05-01 | 95.65% | 90% | 23 | 22 | 7.31 | 30
2013-06-01 | 100% | 90% | 30 | 30 | 5.6 | 30
2013-07-01 |  | 90% |  |  |  | 30
2013-08-01 | 100% | 90% | 10 | 10 | 10.4 | 30
2013-09-01 | 65% | 90% | 20 | 13 | 28.4 | 30
2013-10-01 | 0% | 90% | 3 | 0 | 59.5 | 30
2013-11-01 | 40% | 90% | 10 | 4 | 101.6 | 30
2013-12-01 |  | 90% |  |  |  | 30
2014-01-01 | 87.5% | 90% | 8 | 7 | 11.25 | 30
2014-02-01 | 100% | 90% | 12 | 12 | 5.66 | 30
2014-03-01 | 100% | 90% | 15 | 15 | 6.8 | 30
2014-04-01 | 87.5% | 90% | 8 | 7 | 20.63 | 30
2014-05-01 | 100% | 90% | 9 | 9 | 11.78 | 30
2014-06-01 | 100% | 90% | 2 | 2 | 2 | 30
2014-07-01 | 100% | 90% | 3 | 3 | 16.33 | 30
2014-08-01 | 100% | 90% | 9 | 9 | 6.889 | 30
Whole Process
Closure Measurable (Substantial Completion date-PFA Closure date)
Month | % in 180 days or less | Goal | No of PFA's Closed | No of Projects processed on time (<180 days) | Average age (days) | Target
2012-11-01 | 13.33% | 90% | 15 | 2 | 581.5 | 120
2012-12-01 | 16.67% | 90% | 24 | 4 | 421.5 | 120
2013-01-01 | 4.348% | 90% | 23 | 1 | 568.5 | 120
2013-02-01 | 0% | 90% | 32 | 0 | 523.1 | 120
2013-03-01 | 0% | 90% | 15 | 0 | 323 | 120
2013-04-01 | 0% | 90% | 4 | 0 | 235.7 | 120
2013-05-01 | 13.04% | 90% | 23 | 3 | 293 | 120
2013-06-01 | 6.667% | 90% | 30 | 2 | 315.2 | 120
2013-07-01 |  | 90% | 0 | 0 |  | 120
2013-08-01 | 20% | 90% | 10 | 2 | 214.8 | 120
2013-09-01 | 20% | 90% | 20 | 4 | 231.9 | 120
2013-10-01 | 0% | 90% | 3 | 0 | 511.5 | 120
2013-11-01 | 0% | 90% | 10 | 0 | 440.1 | 120
2013-12-01 |  | 90% | 0 | 0 |  | 120
2014-01-01 | 25% | 90% | 8 | 2 | 309.1 | 180
2014-02-01 | 8.333% | 90% | 12 | 1 | 395.6 | 180
2014-03-01 | 0% | 90% | 15 | 0 | 317.1 | 180
2014-04-01 | 0% | 90% | 8 | 0 | 278.6 | 180
2014-05-01 | 22.22% | 90% | 9 | 2 | 264.4 | 180
2014-06-01 | 0% | 90% | 2 | 0 | 245 | 180
2014-07-01 | 0% | 90% | 3 | 0 | 288.7 | 180
2014-08-01 | 33.33% | 90% | 9 | 3 | 225 | 180
D&CS
Execution of Change order per month
Month | % in 45 days or less | Goal | No of Change Orders | No of Change Orders processed on time (<45 days) | Average age (days) | Target
2013-03-01 | 100% | 90% | 10 | 10 | 28.5 | 45
2013-04-01 | 62.5% | 90% | 16 | 10 | 46.6 | 45
2013-05-01 | 80% | 90% | 5 | 4 | 53 | 45
2013-06-01 | 60% | 90% | 10 | 6 | 54 | 45
2013-07-01 | 33.33% | 90% | 9 | 3 | 89 | 45
2013-08-01 | 43.75% | 90% | 16 | 7 | 95 | 45
2013-09-01 | 66.67% | 90% | 9 | 6 | 41 | 45
2013-10-01 | 50% | 90% | 6 | 3 | 74 | 45
2013-11-01 | 72.73% | 90% | 11 | 8 | 42 | 45
2013-12-01 | 25% | 90% | 4 | 1 | 62 | 45
2014-01-01 | 37.5% | 90% | 8 | 3 | 81 | 45
2014-02-01 | 63.64% | 90% | 11 | 7 | 50 | 45
2014-03-01 | 66.67% | 90% | 9 | 6 | 58 | 45
2014-04-01 | 77.78% | 90% | 9 | 7 | 28 | 45
2014-05-01 | 85.71% | 90% | 7 | 6 | 38 | 45
2014-06-01 | 75% | 90% | 8 | 6 | 34 | 45
2014-07-01 | 57.14% | 90% | 7 | 4 | 50 | 45
2014-08-01 | 45.45% | 90% | 11 | 5 | 50 | 45

## Business Services
Process Requisitions
| % in 2 days or less | Goal | % of Days processed > 2 days | No of Trans processed | No of Trans processed on time
2011-12-01 | 83% | 90% | 17% | 40 | 33.2
2012-01-01 | 75.56% | 90% | 24.44% | 45 | 34
2012-02-01 | 93.85% | 90% | 6.154% | 130 | 122
2012-03-01 | 88.52% | 90% | 11.48% | 122 | 108
2012-04-01 | 97.22% | 90% | 2.778% | 72 | 70
2012-05-01 | 66.67% | 90% | 33.33% | 135 | 90
2012-06-01 | 89.11% | 90% | 10.89% | 101 | 90
2012-07-01 | 94.74% | 90% | 5.263% | 114 | 108
2012-08-01 | 74.58% | 90% | 25.42% | 177 | 132
2012-09-01 | 88% | 90% | 12% | 50 | 44
2012-10-01 | 91.54% | 90% | 8.462% | 260 | 238
2012-11-01 | 83.9% | 90% | 16.1% | 236 | 198
2012-12-01 | 96.63% | 90% | 3.371% | 178 | 172
2013-01-01 | 97.64% | 90% | 2.362% | 127 | 124
2013-02-01 | 77.22% | 90% | 22.78% | 180 | 139
2013-03-01 | 64.66% | 90% | 35.34% | 133 | 86
2013-04-01 | 57.4% | 90% | 42.6% | 169 | 97
2013-05-01 | 89.57% | 90% | 10.43% | 163 | 146
2013-06-01 | 88.28% | 90% | 11.72% | 128 | 113
2013-07-01 | 77.03% | 90% | 22.97% | 148 | 114
2013-08-01 | 69.43% | 90% | 30.57% | 157 | 109
2013-09-01 | 66.67% | 90% | 33.33% | 69 | 46
2013-10-01 | 64.81% | 90% | 35.19% | 162 | 105
2013-11-01 | 85.56% | 90% | 14.44% | 90 | 77
2013-12-01 | 68.48% | 90% | 31.52% | 165 | 113
2014-01-01 | 72.27% | 90% | 27.73% | 119 | 86
2014-02-01 | 96.77% | 90% | 3.226% | 217 | 210
2014-03-01 | 82.91% | 90% | 17.09% | 199 | 165
2014-04-01 | 91.72% | 90% | 8.28% | 157 | 144
2014-05-01 | 87.62% | 90% | 12.38% | 210 | 184
2014-06-01 | 87.13% | 90% | 12.87% | 202 | 176
2014-07-01 | 88.06% | 90% | 11.94% | 201 | 177
2014-08-01 | 81.5% | 90% | 18.5% | 200 | 163
Process Invoices
| % in 2 days or less | Goal | % Processed > 2 days | No of Trans processed | No of Trans processed on time
2012-02-01 | 100% | 90% | 0% | 515 | 515
2012-03-01 | 99.53% | 90% | 0.4724% | 635 | 632
2012-04-01 | 100% | 90% | 0% | 691 | 691
2012-05-01 | 100% | 90% | 0% | 759 | 759
2012-06-01 | 100% | 90% | 0% | 649 | 649
2012-07-01 | 99.28% | 90% | 0.7246% | 690 | 685
2012-08-01 | 98.02% | 90% | 1.976% | 658 | 645
2012-09-01 | 98.96% | 90% | 1.042% | 480 | 475
2012-10-01 | 99.77% | 90% | 0.2347% | 426 | 425
2012-11-01 | 98.4% | 90% | 1.603% | 624 | 614
2012-12-01 | 98.33% | 90% | 1.675% | 418 | 411
2013-01-01 | 98.74% | 90% | 1.258% | 795 | 785
2013-02-01 | 98.43% | 90% | 1.571% | 700 | 689
2013-03-01 | 99.66% | 90% | 0.3436% | 582 | 580
2013-04-01 | 96.93% | 90% | 3.066% | 587 | 569
2013-05-01 | 99.48% | 90% | 0.5155% | 776 | 772
2013-06-01 | 99.72% | 90% | 0.2825% | 354 | 353
2013-07-01 | 99.57% | 90% | 0.4329% | 693 | 690
2013-08-01 | 99.28% | 90% | 0.7233% | 553 | 549
2013-09-01 | 97.9% | 90% | 2.103% | 428 | 419
2013-10-01 | 96.99% | 90% | 3.009% | 432 | 419
2013-11-01 | 100% | 90% | 0% | 308 | 308
2013-12-01 | 93.92% | 90% | 6.077% | 362 | 340
2014-01-01 | 100% | 90% | 0% | 297 | 297
2014-02-01 | 97.62% | 90% | 2.381% | 336 | 328
2014-03-01 | 98.19% | 90% | 1.805% | 554 | 544
2014-04-01 | 100% | 90% | 0% | 614 | 614
2014-05-01 | 99.44% | 90% | 0.5626% | 711 | 707
2014-06-01 | 100% | 90% | 0% | 598 | 598
2014-07-01 | 100% | 90% | 0% | 317 | 317
2014-08-01 | 100% | 90% | 0% | 558 | 558

## FY14 Utilities
FY2014
|  |  | Budget |  | Actual
|  | Month | Budget Current Month | Budget YTD | Actual Current Month | Actual YTD | Over/Under Budget
1262105.7767 | 6.515% | October | 1335809.0504 | 1335809.0504 | 1636959.8333 | 1636959.8333 | -301150.7829
1372854.3167 | 7.086% | November | 1453024.9801 | 2788834.0305 | 1561126.625 | 3198086.4583 | -409252.4278
1600219.0217 | 8.26% | December | 1693667.1167 | 4482501.1473 | 1737250.775 | 4935337.2333 | -452836.0861
1771438.0017 | 9.144% | January | 1874884.7827 | 6357385.93 | 2273933.6067 | 7209270.84 | -851884.91
1699426.0267 | 8.772% | February | 1798667.5197 | 8156053.4497 | 2035592.4367 | 9244863.2767 | -1088809.827
1629901.4617 | 8.413% | March | 1725082.9241 | 9881136.3738 | 2197900.8767 | 11442764.1533 | -1561627.7796
1556468.375 | 8.034% | April | 1647361.5607 | 11528497.9345 | 1626166.69 | 13068930.8433 | -1540432.9089
1574875.01 | 8.129% | May | 1666843.0891 | 13195341.0236 | 1644664.35 | 14713595.1933 | -1518254.1697
1604200.6 | 8.281% | June | 1697881.2075 | 14893222.2311 | 1696704.83 | 16410300.0233 | -1517077.7922
1925202.35 | 9.938% | July | 2037628.5178 | 16930850.7489 | 1850341.27 | 18260641.2933 | -1329790.5444
1782273.46 | 9.2% | August | 1886353 | 18817203.7489 | 1853730 | 20114371.2933 | -1297167.5444
1594057 | 8.228% | September | 1687145.2511 | 20504349 |  | 20114371.2933 | 389977.7067
19373021.4 | 100%
|  |  | 20504349 | INCLUDES Cohn, Law & Engineering
Accruals for FY13
Electric
Gas
|  |  | Steam | 28750
Water
28750
NOTES:
July PLD Bldgs are now on DTE, also being CHALLENDGED
MichCon estimated for July & August
All Utilities estimated for August
DWSD estimated for August
Scott Hall & Pharmacy are now of Detroit Thermal Steam

## FY13 Utilities
| FY2012 | [5 empty] | FY2013
| Budget |  | Actual |  |  |  | Budget |  | Actual
Month | Current Month | YTD | Current Month | % | YTD | Month | Budget Current Month | Budget YTD | Actual Current Month | Actual YTD | Over/Under Budget
October |  |  | 1347960.0533 | 7.385% | 1347960.0533 | October | 1425739.7102 | 1425739.7102 | 1262105.7767 | 1262105.7767 | 163633.9336
November |  |  | 1493468.53 | 8.182% | 2806574.1067 | November | 1579644.2809 | 3005383.9912 | 1372854.3167 | 2634960.0933 | 370423.8978
December |  |  | 1684623.94 | 9.229% | 4426203.65 | December | 1781829.693 | 4787213.6842 | 1600219.0217 | 4235179.115 | 552034.5692
January |  |  | 1708492.04 | 9.36% | 6049969.18 | January | 1807075.0242 | 6594288.7084 | 1771438.0017 | 6006617.1167 | 587671.5917
February |  |  | 1566531.46 | 8.582% | 7640323.54 | February | 1656923.07 | 8251211.7784 | 1699426.0267 | 7706043.1433 | 545168.6351
March |  |  | 1659539.87 | 9.092% | 9248432.26 | March | 1755298.2282 | 10006510.0067 | 1629901.4617 | 9335944.605 | 670565.4017
April |  |  | 1309764.87 | 7.176% | 10603195.92 | April | 1385340.5979 | 11391850.6046 | 1556468.375 | 10892412.98 | 499437.6246
May |  |  | 1436752.77 | 7.871% | 12046408.27 | May | 1519655.9222 | 12911506.5268 | 1574875.01 | 12467287.99 | 444218.5368
June |  |  | 1459204.62 | 7.994% | 13580413.95 | June | 1543403.2833 | 14454909.8101 | 1604200.6 | 14071488.59 | 383421.2201
July |  |  | 1605753.03 | 8.797% | 15070197.95 | July | 1698407.7933 | 16153317.6034 | 1929807.18 | 16001295.77 | 152021.8334
August |  |  | 1562596.23 | 8.561% | 16484279.95 | August | 1652760.7704 | 17806078.3737 | 1883654.6233 | 17884950.3933 | -78872.0196
September |  |  | 1418345.6 | 7.77% | 18873098.95 | September | 1500186.6263 | 19306265 | 1457021.7333 | 19341972.1267 | -35707.1267
Total |  |  | 18253033.0133 | 100% |  |  | 19306265 | INCLUDES Cohn, Law & Engineering
Banner Total | [6 empty] | Accruals for FY12
[7 empty] | Electric | -103911.9
[7 empty] | Gas | -57913.7
[7 empty] | Steam | 0
[7 empty] | Water | -773272.89
[7 empty] | Over Accrual | -935098.49 | (applied equally Oct - June)
NOTES:
New PLD Rates are in effect starting in January 2013
MichCon estimated for August & September
All Utilities estimated for September
PLD estimated for August & September
Scott Hall & Pharmacy are now of Detroit Thermal Steam

## FY12 Utilities
| FY2011 | [6 empty] | FY2012
| Budget |  | Actual |  |  |  |  | Budget |  | Actual
Month | Current Month | YTD | Current Month | % | YTD |  | Month | Budget Current Month | Budget YTD | Actual Current Month | Actual YTD |  | Over/Under Budget
October |  |  | 1462625.79 | 7.963% | 1462625.79 |  | October | 1537364.0443 | 1537364.0443 | 1347960.0533 | 1347960.0533 |  | 189403.991
November |  |  | 1493468.53 | 8.131% | 2956094.32 |  | November | 1569782.8078 | 3107146.8521 | 1458614.0533 | 2806574.1067 |  | 300572.7454
December |  |  | 1684623.94 | 9.172% | 4640718.26 |  | December | 1770706.0078 | 4877852.8599 | 1619629.5433 | 4426203.65 |  | 451649.2099
January |  |  | 1708492.04 | 9.302% | 6349210.3 |  | January | 1795793.7363 | 6673646.5962 | 1623765.53 | 6049969.18 |  | 623677.4162
February |  |  | 1566531.46 | 8.529% | 7915741.76 |  | February | 1646579.1574 | 8320225.7536 | 1590354.36 | 7640323.54 |  | 679902.2136
March |  |  | 1659539.87 | 9.035% | 9575281.63 |  | March | 1744340.1748 | 10064565.9284 | 1608108.72 | 9248432.26 |  | 816133.6684
April |  |  | 1309764.87 | 7.131% | 10885046.5 |  | April | 1376692.1323 | 11441258.0608 | 1354763.66 | 10603195.92 |  | 838062.1408
May |  |  | 1436752.77 | 7.822% | 12321799.27 |  | May | 1510168.947 | 12951427.0078 | 1443212.35 | 12046408.27 |  | 905018.7378
June |  |  | 1459204.62 | 7.944% | 13781003.89 |  | June | 1533768.057 | 14485195.0648 | 1534005.68 | 13580413.95 |  | 904781.1148
July |  |  | 1605753.03 | 8.742% | 15386756.92 |  | July | 1687804.898 | 16172999.9628 | 1489784 | 15070197.95 |  | 1102802.0128
August |  |  | 1562596.23 | 8.507% | 16949353.15 |  | August | 1642442.8423 | 17815442.8052 | 1414082 | 16484279.95 |  | 1331162.8552
September |  |  | 1418345.6 | 7.722% | 18367698.75 |  | September | 1490821.1948 | 19306264 | 2388819 | 18873098.95 | * | 433165.05
Total |  | 20781460 | 18367698.75 | 100% |  |  |  | 19306264 | 19306264
Banner Total |  |  | 19305615.75 | [6 empty] | = With some accruals
[9 empty] | 800000 | = Accrued for Matthaei water leak
[5 empty] | *NOTE: | 1) Includes Energy Management costs WHICH HAD NOT BEEN INCLUDED IN PREVIOUS REPORTS
2) Does not include accurals
[6 empty] | 3) | Water Leak in the Matthaei Field could result in a $800,000 water charge
which has NOT BEEN INCLUDED in the year end estimates.