XI.	State Reviews

- Joint Capital Outlay

- Bureau of Fire Safety

- Retail Projects Rob

- What is it -

- Design and Construction Services provides Project Management to Business Operations for Tenant Construction in Wayne State Owned buildings. (form 1).

- The State of Michigan is the Authority Having Jurisdiction in Classroom Buildings and Residence Halls.  These retail projects require plan submissions by the Tenant’s designer to the SOM Bureau of Fire Services and Bureau of Construction Codes.  (form 2)

- In other buildings (non-residence hall, or classroom buildings) where WSU Office of Risk Management is the AHJ, the State of Michigan is invited to provide Trade Specific permitting for the MEP portions of the project work.  Contractors are required to pull permits, using the Tenant’s design documents.

- A request to participate in the project goes to State of Michigan Bureau of Construction Codes.  (form 3).  Greg Calme may be scheduled alternately for smaller projects where minimum Tenant remodeling is to occur.  (form 4)

- Health Department inspection is handled by WSU Office of Environmental Health and Safety (Mr. Scott Browne) in all WSU buildings.

- Who is involved –

- Business Operations is involved with lease of space to Tenants.

- The Tenant is responsible to retain design services and provide design documents for their build out of the space.  .

- Design & Construction Services provides Project Management.

- Drawing review is completed with the assist of D&CS, ORM and OEH&S.  (form 3)

- Final construction drawings are completed by the tenant’s designer based upon these review comments and are then sent to the State of Michigan BCC and BFS for Residence Halls and Classroom Buildings for plan review and permitting. (form 4).

- Projects where WSU is the AHJ.  Design documents are reviewed by SOM BCC with permit application for trade specific permitting.

- Final Certificate of Occupancy is either provided by SOM BFS (form 5) or by WSU ORM (form 6).

- How/ Process –

- Write a letter to SOM Bureau of Construction codes to assist with plan review and inspection for buildings where WSU is the AHJ.

- Write a letter to SOM Bureau of Construction codes to alert that a project is forthcoming, and proposed submission and construction schedule.

- Identify potential pull ahead work, demolition and minor construction ahead of plan review.  Note; Tenant is responsible for incorporation of any review comments into the work/ re-work cost if necessary.

- Checklist –

- (To be filled in).

- Timeline Considerations:

- Look at construction schedule.  Allow 6 -8 weeks for plan review/ submission to State of MI.  Initial 95% review allow another 2 -3 weeks depending on complexity of the work.

- Forms –

- Form 1 – Tenant Construction in WSU Owned buildings.

- Form 2 -  SOM BCC and BFS project announcement.

- Form 3 -  SOM BCC request for assistance.

- Form 4 – Plan review forms, DCS/ ORM/ OEH&S

- Form 5 – BFS Final Occupancy.

- Form 6 – ORM Final Occupancy.

- Filing – Follow D&CS filing protocol.

- File according to WSU protocol.