## Slide 1: Application for Payment
Reviewing Pay Apps
And remaining employed

## Slide 2: Timing is Everything
Maximum of 5 calendar days to turn around and approve for payment.

## Slide 3: Pay Application Checklist

## Slide 4: Clerical review
All applications to start with clerical support initial review.

## Slide 5: Clerical review
Check and confirm the following:
  a. WSU Project Number
  b. WSU P.O.Number (if applicable)
  c. Project Name
  e. Notarized
  f. Contractor’s signature

## Slide 6: Pencil copy meeting
Monthly pencil copy meetings
Note if there is an architect

## Slide 7: Unit Price contracts and JOC

## Slide 8: Sworn Statement

## Slide 9: Schedule of Values – Sworn Statement
$94,650

## Slide 10: Waivers
All subcontractors or suppliers who submit a
  Notice of Furnishing
  Claim against Bond
Advise contractor when one
is received.

## Slide 11: Waiver Logic
 | Partial Conditional Waiver |  |  |  |  |  |  | Partial Unconditional Waiver |  |  |  |  |  |  | Full Conditional Waiver |  |  |  |  |  |  | Full Unconditional Waiver |  |  |  | 
 | Requests $ |  |  |  |  |  |  | Some $ Paid |  |  |  |  |  |  | Requests All $$$ |  |  |  |  |  |  | All $$ Paid |  |  |  | 
 | Subcontractor requests progress payment |  |  |  |  |  |  | Subcontractor has received a partial payment |  |  |  |  |  |  | Contractor requests final payment |  |  |  |  |  |  | Suppliers Subcontractors have received final payment |  |  |  | 

## Slide 12: Partial Conditional Waivers
From
all
tier subcontractors when there is
no
materials and labor payment
bond
on the project.

## Slide 13: Schedule of Values

## Slide 14: Retention

## Slide 15: Waiver Matrix

## Slide 16: Tracking SS and CP

## Slide 17: Certified Payroll WH-347
Work classification
Rate Schedule
Boots on the floor

## Slide 18: Prevailing Wage
Bid – Front end document
Procurement and Strategic Sourcing web site

## Slide 19: Incomplete Pay Application
Pay Application
Retention reduction to 2%
Sworn Statement
Partial Unconditional waivers
Close out documents
Full unconditional waivers
From the subcontractors
and suppliers

## Slide 20: Incomplete Pay Application
Pay application
  Does not match final copy

## Slide 21: Incomplete Pay Application
Pay application
  General conditions % are ahead of over all completion.

## Slide 22: Incomplete Pay Application
Pay application
  Proper stored material
  documentation
  incomplete.

## Slide 23: Incomplete Pay Application
Change order is not executed but billed for.

## Slide 24: Incomplete Pay Application
Retention reduction to 2%

## Slide 25: Incomplete Pay Application
Architect’s signature

## Slide 26: Incomplete Pay Application
Sworn Statement

## Slide 27: Incomplete Pay Application
Partial Unconditional waivers

## Slide 28: Incomplete Pay Application
Close out
documents

## Slide 29: Incomplete Pay Application
Full unconditional waivers
From the subcontractors
and suppliers

## Slide 30: Incomplete Pay Apps:
Copy of the email to the
contractor of
what is missing.
Give to Clerical to file.

## Slide 31: Complete Pay Apps:
Approved for payment
Full signature
Date
Payment date tag