Facilities Planning and Management

Process Description and Policy Requirements

Contracting for Design and Construction Services

This process policy statement replaces and supersedes the Design and Construction Milestone Sequencing Policy last amended November 30, 2005.

The purpose of this documentis to ensure that FPM directors, trades managers, and project managers know of and consistently perform the tasks and activities noted herein in their necessary sequence while leading the development and implementation of capital construction projects for our various University customers.  This process description and policy statement does not present performance requirements for all possible project milestones, but rather those that are critical to the execution of related contracts, the processing of purchase orders, and the commencement of design and construction activities.  Additionally, this document will assist FPM customers in understanding essential project contracting and purchasing practices , as this will have a significant impact on anticipating and effectively planning project requests so work is completed when needed.  This document also presents requirements and expectations for projects that will use preferred designer, and time and material construction vendors.  Refer also to the Preferred Design Vendor Procedural Policy for related details.

- Establishing Needs – Customer Project Request:  All requests for capital projects, whether implemented or not, must be submitted via the FPM website or by calling the service center using a General Improvements Request Form (GIRF).  Customer are required to thoroughly prepare and submit a GIRF before FPM will recognize and begin implementing any project.  Examples of projects include signage, hiring new faculty that require facility set-up, creating teaching labs, office or lab renovations, or athletic facility improvements.

- Soliciting A/E Proposals:  Once a customer’s GIRF is accepted and after the scope of the project is understood, FPM will solicit proposal(s) from qualified architectural and engineering (A/E) firm(s) as needed to design the project.  FPM maintains contractual relationships with many A/E firms on a preferred design vendor basis.  Such relationships were established through a competitively solicited process, were fees are based on a percentage of final construction costs.

- Establishing a Plant Fund Account (PFA):  All projects having an expected cost that will exceed $25,000 must have a PFA to accept related charges.  Under no circumstance shall work of any kind be authorized and commenced without having a PFA in place and loaded with necessary funds.  A PFA can be requested at any time following FPM’s acceptance of a customer’s GIRF.  However, doing so before receiving an A/E (or other professional services) proposal will cause the initial budget load to be based on an estimate.  It shall be the FPM project manager’s responsibility to request a PFA.  Such requests shall be submitted to FPM’s Director of Business Services and shall include a brief project description, the funding source and dollar amount.  For those projects not requiring a PFA, project costs may be billed directly to the customer’s account or the customer may transfer funds to FPM, allowing the project costs to be charged directly to FPM instead.

- A/E Contract or Purchase Order Execution:  After receiving a formal written proposal for services from an A/E firm, and after acceptance of the proposed scope of services and fee, FPM shall prepare and submit either a Contract for Professional Services or a Purchase Order for execution.  Under the Preferred Design Vendor relationship established as noted in item no. 2 above, zero sum Contracts for Profession Services have already been executed.  For those projects that will be designed by a preferred design vendor, FPM shall issue a standard purchase requisition that references the applicable contract, project proposal and fee.  Such purchase requisitions will be authorized by FPM’s Senior Director of Design and Construction Services who will then forward copies of the purchase requisition to FPM’s Associate Vice President.  The AVP will provide a report to the Vice President of Finance and Business Operations on a bi-weekly basis to keep the VP apprised of newly initiated design phase activities.  For those projects that do not intend to use a preferred design vendor, FPM shall prepare a Contract for Professional Services for execution.

When submitting a design contract, purchase order, or change order for execution, it shall be accompanied by a “Design and Construction Project Milestone Checklist for Design Contracts”.  The Checklist must acknowledge all milestones listed ahead of A/E Contract or Purchase Order Execution by providing a sign-off and the date that the milestone was completed.  The Checklist shall become part of the project records, and shall be available for review upon request.

- A/E Contract Purchase Order:  After execution of the Contract for Professional Services by both the A/E firm and the Vice President for Finance and Business Operations, a copy of the executed Contract and a related purchase requisition shall be submitted to Purchasing for processing.

The A/E firm shall not be authorized to proceed until the project’s PFA has been established and funded (or other acceptable accounting has been established), until the Contract for Professional Services has been fully executed (assuming one does not exist and is required), a purchase requisition has been issued and a project specific Certificate of Insurance from the A/E firm is filed with Risk Management.  Then, and only then, shall the A/E firm be authorized to provide its services.

- Establish Final Scope and Project Budget Approval:  Working with the customer and A/E firm, the project scope will normally be established during programming and schematic design phase.  As needed, design development and construction documents may be created to understand the project’s scope of work and budget requirements.  Regardless of the level of effort required to establish the scope of work and project budget, a project budget will be developed in appropriate detail and submitted to the customer and / or administration for review and approval.

  - All projects whose budget exceeds $500,000 shall be submitted to the University’s Board of Governors for final approval.  Board Papers will be developed accordingly.

  - All projects whose budget exceeds $1,000,000 but are less than $3,000,000 shall also be reported to the State’s Joint Capital Outlay Subcommittee (JCOS) quarterly, or when Use and Finance Statements are being submitted.

  - All projects whose budget exceeds $3,000,000 shall also be submitted in the form of a Use and Finance Statement to the State’s JCOS for approval immediately following approval by the University’s Board of Governors.

  - For State or federally funded projects, refer to related Design and Construction Services department practices for further details.

Under no circumstance shall construction commence until appropriate authorization(s) have been granted.

- Load PFA with Remaining Funds:  Following final approval of the project’s budget, funds from the approved source shall be loaded into the PFA to equal the project budget.

- Construction Contract or Purchase Order Execution:  For small projects, where an individual contract sum will be under $20,000, use of FPM contractual relationships with time and material (T&M) construction vendors is encouraged if our project customer is willing to permit this remuneration method over a quoted lump-sum price.  When a T&M contractor is to be used, FPM shall initiate a standard purchase requisition for each sub-trade which is unique and exclusively associated with each particular project.  For larger projects, where the aggregate of construction activities is expected to exceed $50,000 FPM shall prepare and submit a Contract for Construction for execution following a competitive bidding and qualification process that yields a determination of the lowest qualified competitive bidder.  .  The Senior Director will provide the AVP with a weekly summary of purchase requisitions issued whose value exceeds $10,000.

When submitting a construction contract, purchase order, or change order for execution, it shall be accompanied by a “Design and Construction Project Milestone Checklist for Construction Contracts”.  The Checklist must acknowledge all milestones listed ahead of Construction Contract or Purchase Order Execution by providing a sign-off and the date that the milestone was completed.  The Checklist shall become part of the project records, and shall be available for review upon request.

- Construction Contract Purchase Order:  After execution of the Contract for Construction by both the constructor and the University , a copy of the Contract and a related purchase requisition shall be submitted to Purchasing for processing.  The constructor shall not be authorized to proceed until a purchase order number is issued.

- Pre-construction Conference:  Prior to issuing an authorization to proceed notice to the contractor, the FPM project manager shall hold a pre-construction conference.  Attendance at this meeting must include the FPM project manager and representative(s) of the construction firm.  Invitations to attend this meeting shall be offered to the A/E firm, a primary customer representative, and the building engineer and custodial supervisor responsible for the building where the project will be implemented.  At or before the pre-construction conference, the FPM project manager must obtain emergency contact information from the contractor and sub-contractors.  Additionally, project coordination and logistical information should be communicated to the customer, building engineer and custodial supervisor to enhance their understanding of probable impacts during construction.  Refer to related Design and Construction Services department practices for further details regarding the pre-construction conference.

- Issue Authorization to Proceed:  The Associate Vice President for Facilities Planning and Management, and / or the Vice President for Finance and Business Operations, and / or the Vice President of Governmental Affairs will always be in attendance at Board of Governors and JCOS meetings when construction projects are approved.  Accordingly, one of these individuals will be able to represent that final project approval has or has not been granted.  A Contract for Construction shall not be executed until appropriate final approval(s) have been granted.  When the Contract for Construction is submitted to the Vice President for Finance and Business Operations for execution, the Contract shall be submitted with all of its supporting documentation, including an Authorization to Proceed letter that shall be signed by the Vice President.  This standard form letter shall be modified as needed to address the specific details related to the project.

The constructor shall not be authorized to proceed until the project’s PFA has been established and fully funded, until the Contract has been fully executed, a purchase order number has been issued, a project specific Certificate of Insurance and performance and payment bond is filed with Risk Management, and a signed Authorization to Proceed letter is received from the Vice President.  Then, and only then, shall the constructor be authorized to proceed with construction.

- Construction Phase and Change Orders:  During construction and with respect to the Contract’s initial scope of work, change is often experienced.  When changes in the scope of work impact the contract sum or contract time, an executed Change Order is required to amend these obligations.  Using the Preliminary Project Cost and Schedule Impact Report, it shall be the FPM project manager’s responsibility to secure acknowledgements of the anticipated change, and to submit an applicable Change Order for execution within the next 30 day payment application cycle of the project.  This Change Order processing requirement applies to both A/E firms and constructors.

- Punchlist Phase:  When substantial completion is achieved, the project team shall work diligently to address all project punchlist items within 45 days.

- Close – Documents:  When all punchlist items have been addressed and final completion is achieved, the project team shall work diligently to secure project close-out documents within 30 days.

- Reconcile and Close PFA:  When all project close-out documents have been received and accepted, the FP&M project manager shall reconcile all PFA transactions and request PFA closure within 45 days.

Failure to comply with this policy may result in formal disciplinary action, up to and including termination of employment.

This Design and Construction Project Milestone Sequencing Policy was reviewed and approved by:

James R. Sears	John L. Davis

Associate Vice President	Vice President

Facilities Planning and Management	Finance and Facilities Management

_____________________________	_____________________________

signature	signature

_____________________________	_____________________________

date	date

FPM is working to develop a new on-line eGIRF initiation process that will allow the discontinued use of the paper GIRF.