## Implementation Workplan
HURON / FP&M IMPLEMENTATION WORKPLAN - DRAFT | [5 empty] | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
[6 empty] | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02
Steering Committee Meeting | Will likely taper to bi-weekly meetings | [6 empty] | 2011-08-16 | 2011-08-23 | 2011-08-30 | 2011-09-06 | 2011-09-13 | 2011-09-20 | 2011-09-27 | 2011-10-04 | - | - | 2011-10-25 | - | 2011-11-08 | - | 2011-11-22 | - | 2011-12-06 | - | 2011-12-20 | - | 2012-01-03 | - | 2012-01-17 | - | 2012-01-31 | - | 2012-02-14 | - | 2012-02-28 | - | 2012-03-13 | - | 2012-03-27 | -
Board of Governors Meetings: http://bog.wayne.edu/meetings/index.php | February 1st ¦ March 21st ¦ May 2nd ¦ June 27th |  |  |  |  | 2011-10-24: 2011-10-26; 2011-12-05: 2011-12-07
Tasks/Activities | Primary Owner | Secondary Owner | Status | Start | End
I. General | Huron | FP&M | Underway | - | -
A. Review Huron Recommendations with FP&M Leadership | Huron | Jim Sears | Complete | 2011-08-04 | 2011-08-05 | bar: 2011-08-01
B. Status updates with FP&M area leaders | Huron | FP&M | Complete | 2011-08-04 | 2011-08-05 | bar: 2011-08-01
C. Complete Responsibilities Matrix | Huron | Jim Sears | Complete | 2011-08-08 | 2011-08-12 | bar: 2011-08-08
D. Complete Workplan | Huron | Jim Sears | Complete | 2011-08-08 | 2011-08-12 | bar: 2011-08-08
E. Submit draft Matrix and Workplan to FP&M | Huron | Jim Sears | Complete | 2011-08-10 | 2011-08-12 | bar: 2011-08-08
F. Prepare and send weekly/bi-weekly updates to PMO | Huron | FP&M | Underway | Ongoing | bar: 2011-08-15 to 2012-01-30
G. Prepare Steering Committee materials | Huron | FP&M | Underway | Ongoing | bar: 2011-08-15 to 2012-01-30
II. Performance Contracting - Phase 1 | Huron | FP&M | Underway | - | -
A. Initial conversations with Siemens Representatives | Huron | Larry Fodor/ Jim Sears | Complete | 2011-08-01 | 2011-08-26 | bar: 2011-08-01 to 2011-08-22
B. Interim draft proposal due from Siemens | Huron | Larry Fodor | Complete | 2011-08-08 | 2011-08-18 | bar: 2011-08-08 to 2011-08-15
C. Review, modify proposal; pose additional questions to Siemens | Huron | Larry Fodor | Complete | 2011-08-29 | 2011-09-30 | bar: 2011-08-29 to 2011-09-26
D. Obtain boiler plate Letter of Understanding and Letter of Intent | Huron | Larry Fodor | Complete | 2011-09-07 | 2011-09-09 | bar: 2011-09-05
E. Decide on and get Jim's sign off on prioritized target buildings and desired payback period range for Phase 1 | Larry Fodor | Jim Sears | Complete | 2011-09-12 | 2011-09-12 | bar: 2011-09-12
F. Provide Siemens with WSU data, incl. prioritized target buildings and desired payback period range for Phase 1 | Larry Fodor | Huron | Complete | 2011-09-12 | 2011-09-12 | bar: 2011-09-12
G. Provide Siemens outline of desired executive summary including validatation of sole source approach | Larry Fodor | Huron | Complete | 2011-09-07 | 2011-09-14 | bar: 2011-09-05 to 2011-09-12
H. Siemens site visit | Huron | FP&M | Complete | 2011-09-14 | 2011-09-14 | bar: 2011-09-12
I. Final draft proposal due from Siemens - incl. executive summary and proposed costs of Preliminary Analysis (distinct document) | Huron | Larry Fodor | Complete | 2011-09-14 | 2011-10-31 | bar: 2011-09-12 to 2011-10-31
J. Present proposal to Rick Nork | Huron | Larry Fodor/ Jim Sears | Complete | 2011-09-13 | TBD
K. Siemens Performs Preliminary Analysis | Huron | Larry Fodor | Complete | 2011-09-21 | 2011-10-31 | 2011-09-19: X; 2011-09-26: X; 2011-10-03: xx; 2011-10-10: x; 2011-10-17: x; 2011-10-24: x; 2011-10-31: x
L. WSU General Cousel to review and approve Project Development Agreement | Larry Fodor/ Jim Sears | Huron | Complete | 2011-09-27 | 2011-10-31 | 2011-09-26: X; 2011-10-03: xx; 2011-10-10: X; 2011-10-17: X; 2011-10-24: X; 2011-10-31: x
M. WSU/Huron reviews and approves preliminary ECMs | Larry Fodor/ Jim Sears | Mike Colburn | Complete | 2011-10-31 | 2011-11-15 | bar: 2011-10-31 to 2011-11-14
N. Siemens Performs Detailed Analysis & proposes final ECM's | Huron | Larry Fodor | Underway | 2012-12-01 | 2012-03-01 | bar: 2011-12-05 to 2012-02-27
O. Final Scope Selection | Huron | Larry Fodor | Not Started | 2012-03-05 | 2012-03-16 | bar: 2012-03-05 to 2012-03-12
P. Negotiate and finalize contract with Siemens incl. financing, measurement and verification (M&V), and inclusion of Huron recommendations (i.e. building sub-metering) | Huron | Larry Fodor | Not Started | 2012-03-19 | 2012-04-06 | bar: 2012-03-19 to 2012-04-02
Q. OGC to review terms and conditions of Performance Contract | Larry Fodor/ Jim Sears | Huron | Not Started | 2012-04-09 | 2012-04-09
R. Presentation to BOG and approval by the board | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-05-02 | 2012-05-02
S. Begin Phase 1 Construction | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-05-15 | 2012-10-31
T. Phase 1 Evaluation/Guarantee | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-10-31 | 2012-11-30
U. Begin planning for Phase 2 - incl. building selection | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-04-01 | TBD
V. Siemens performs Preliminary Analysis for Phase 2 | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-05-01 | 2012-06-15
W. Preliminary scope selection for Phase 2 | FP&M | Larry Fodor/ Jim Sears | Not Started | 2012-06-15 | 2012-06-30
III. Job Order Contracting (JOC) | Huron | FP&M | Underway | - | -
A. Initial conversations with The Gordian Group representatives | Huron | Randy Paquette | Complete | 2011-08-05 | 2011-08-19 | bar: 2011-08-01 to 2011-08-15
B. Provide Gordian with WSU data | Randy Paquette | Huron | Complete | 2011-08-22 | 2011-09-02 | bar: 2011-08-22 to 2011-08-29
D. Technology Demo by Gordian | Huron | Randy Paquette | Complete | 2011-08-25 | 2011-08-25 | bar: 2011-08-22
E. Test-run Project with Cashier's Office - Phase I | Randy Paquette | FP&M | Complete | 2011-08-01 | 2011-10-07 | bar: 2011-08-01 to 2011-10-03
1. Receive Casher Project Cost Proposal | Randy Paquette | FP&M | Complete | 2011-09-09 | 2011-09-09 | bar: 2011-09-05
2. Meet with Gordian Group on Proposal | Randy Paquette | FP&M | Complete | 2011-09-13 | 2011-09-13 | bar: 2011-09-12
3. Prepare and Send Contract to S/G | Randy Paquette | FP&M | Complete | 2011-09-23 | 2011-09-23 | bar: 2011-09-19
4. Construction (true end date is #5 end date) | Randy Paquette | FP&M | Complete | TBD | 2011-12-18 | bar: 2011-10-03 to 2011-12-12
5. Complete Cashier's Project (Confirm data with Customer) | Randy Paquette | FP&M | Complete | 2011-11-18 | 2011-12-18 | bar: 2011-11-21 to 2011-12-12
6. Post Project Review (Post Mortem ) | Randy Paquette | FP&M | Not Started | 2011-12-05 | 2011-12-22 | bar: 2011-12-05 to 2011-12-19
F. Test-run Maintenance Projects | Randy Paquette | FP&M | Underway | 2012-09-26 | 2012-01-27
G. Test-run Customer Initiated Projects (Devine, Colburn, Fornier, Michaels, Yee) | Randy Paquette | FP&M | Underway | 2011-09-26 | 2011-01-27 | bar: 2011-09-26 to 2012-01-23
1. Confirm Phase II with Customers | Randy Paquette | FP&M | Complete | 2011-09-26 | 2011-10-14 | bar: 2011-09-26 to 2011-10-10
2. Preliminary List of Phase II Projects (Matthei tennis scoreboard, UGL electrical rework, DeRoy cabinets, ??) | Randy Paquette | FP&M | Underway | 2011-09-22 | 2011-09-29 | bar: 2011-09-19 to 2011-09-26
3. Finalize PowerPoint Marketing Tool | Randy Paquette | FP&M | Complete | 2011-09-23 | 2011-09-29 | bar: 2011-09-19 to 2011-09-26
4. Meet with Customers (Powerpoint) Confirm Phase II Projects (~6) | Randy Paquette | FP&M | Not Started | 2011-09-26 | 2011-10-07 | bar: 2011-09-26 to 2011-10-03
5. Begin Scope Development of Selected Projects | Randy Paquette | FP&M | Complete | 2011-09-26 | bar: 2011-09-26
6. Selected Project Scopes to Gordian Group | Randy Paquette | FP&M | Complete | 2011-10-21 | bar: 2011-10-17
7. Confirm with Gordian/ Delivery of Projects Cost Proposal | Randy Paquette | FP&M | Underway | 2011-11-04 | bar: 2011-10-31
8. WSU Final Review and Confirm with Customer | Randy Paquette | FP&M | Underway | 2011-11-09 | bar: 2011-11-07
9. Prepare and Send Contracts | Randy Paquette | FP&M | Underway | 2011-11-11 | bar: 2011-11-07
10. Implement Work | Randy Paquette | FP&M | Underway
11. Post Project Review (Post Mortem ) | Randy Paquette | FP&M | Not Started
H. Send out RFI for Customized and Standard Offerings | Huron | Randy Paquette | Underway | 2012-02-01 | 2012-03-01 | bar: 2011-08-29 to 2012-02-27
I. Evaluate Responses | Huron | Randy Paquette | Not Started | 2013-03-01 | 2013-03-22 | bar: 2012-03-05 to 2012-03-19
J. Select Company and Sign Contract | Huron | Randy Paquette | Not Started | 2013-03-22 | 2013-04-04 | bar: 2012-03-19 to 2012-04-02
K. Orientation | Huron | Randy Paquette | Not Started | TBD | TBD
L. Technology Setup (configure system) | Huron | Randy Paquette | Not Started | TBD | TBD
M. Construction Task Catalog (CTC) Development | Huron | Randy Paquette | Not Started | TBD | TBD
N. Technical Specifications Development | Huron | Randy Paquette | Not Started | TBD | TBD
O. JOC Documents Development -Custom JOC Program (Construction?) MGR. Relationship (WSU Program) | Huron | Randy Paquette | Not Started | TBD | TBD
O. 1. RFP for JOC Program Mgr. to Purchase |  | Randy Paquette |  | TBD | TBD
O. 2. Replies Due From RFP |  | Randy Paquette |  | TBD | TBD
O. 3. Contract Complete with JOC Program Mgr. |  | Randy Paquette |  | TBD | TBD
O. 4. Begin RFI Development Contracts (confirm with Mgr.) |  | Randy Paquette |  | TBD | TBD
P. Market JOC Program | Huron | Randy Paquette | Not Started | TBD | TBD
Q. Workshops and Training | Huron | Randy Paquette | Not Started | TBD | TBD
R. Implement Use of JOC | Huron | Randy Paquette | Not Started | TBD | TBD
IV. Pilot Project - TMA | FP&M | Huron | Underway | - | -
A. DEVELOP WORK ORDER MANAGEMENT PROCESS - Facilities Operations | Mike Colburn | Piyush Panhale | Complete | 2011-10-15 | 2011-11-01 | bar: 2011-10-17 to 2011-10-31
B. DEVELOP WORK ORDER MANAGEMENT PROCESS - Service Center | Mike Colburn | Angela Strickland | Underway | 2011-10-15 | 2011-11-01 | bar: 2011-10-17 to 2011-10-31
C. DEVELOP PREVENTIVE MAINTENANCE WORK ORDER MANAGEMENT PROCESS | Mike Colburn | Piyush Panhale | Underway | 2011-12-01 | 2012-03-01 | bar: 2011-11-28 to 2012-02-27
D. DEVELOP TMA INVENTORY CONTROL PROCESS - Equipment's/parts/chemicals | Mike Colburn | Angela Strickland | Underway | 2011-12-01 | 2012-02-01 | bar: 2011-11-28 to 2012-01-30
E. DEVELOP TMA INVENTORY CONTROL PROCESS - Keys | Mike Colburn | Mike Pines | Complete | 2011-11-01 | 2012-02-01 | bar: 2011-10-31 to 2012-01-30
F. DEVELOP TMA INVENTORY CONTROL PROCESS - Invoices | Mike Colburn | Angela Strickland | Complete | 2011-11-01 | 2012-02-01 | bar: 2011-10-31 to 2012-01-30
G. DEVELOP IT INTERFACE PROCESS FOR TMA - Authorization | Mike Colburn | Jason Sepanak | Complete | 2011-11-01 | 2012-01-02 | bar: 2011-10-31 to 2012-01-02
H. DEVELOP IT INTERFACE PROCESS FOR TMA - TMA Hardware Installation | Mike Colburn | Jason Sepanak | Complete | 2011-11-01 | 2012-01-02 | bar: 2011-10-31 to 2012-01-02
I. DEVELOP IT INTERFACE PROCESS FOR TMA - Develop TMA Software improvement process | Mike Colburn | Jason Sepanak | Complete | 2012-01-03 | 2012-03-01 | bar: 2012-01-02 to 2012-02-27
J. Develop plan to train employees in Facilities Operations group | Mike Colburn | Piyush Panhale | Underway | 2011-11-01 | 2012-01-02 | bar: 2011-10-31 to 2012-01-02
K. Develop plan for Using Mobile TMA in pilot buildings | Mike Colburn | Piyush Panhale | Underway | 2011-12-01 | 2012-03-01 | bar: 2011-11-28 to 2012-02-27
L. Develop evaluation Tracking Methodology - work order completion time | Mike Colburn | Piyush Panhale | Complete | 2011-12-01 | 2012-03-01 | bar: 2011-11-28 to 2012-02-27
M. Develop evaluation Tracking Methodology - PM completion time | Mike Colburn | Piyush Panhale | Complete | 2011-12-15 | 2012-03-01 | bar: 2011-12-12 to 2012-02-27
N. Develop evaluation Tracking Methodology - Evaluate Mobile TMA Vs. Computer use | Mike Colburn | Piyush Panhale | Underway | 2012-02-01 | 2012-03-01 | bar: 2012-01-30 to 2012-02-27
O. Pilot Program result - Develop measurements for pilot buildings TMA evaluation | Mike Colburn | Piyush Panhale | Underway | 2011-12-01 | 2012-04-01 | bar: 2011-11-28 to 2012-03-26
P. Pilot Program result - Record evaluation status | Mike Colburn | Piyush Panhale | Underway | 2012-01-03 | 2012-04-01 | bar: 2012-01-02 to 2012-03-26
Q. Pilot Program result - Develop recommendation for improved process | Mike Colburn | Piyush Panhale | Not Started | 2012-02-15 | 2012-04-01 | bar: 2012-02-13 to 2012-03-26
V. Pilot Project - Utilities Budgeting | FP&M | Huron | Underway | - | -
A. Review Huron recommendation with Rick Nork & gain sign-off | Jim Sears | Huron | Complete | 2011-08-15 | 2011-08-26 | bar: 2011-08-15 to 2011-08-22
B. Meet with Budgeting Office to discuss implementation | Jim Sears | Huron | Complete | 2011-08-22 | 2011-08-26 | bar: 2011-08-22
C. Gain Provost Sign off | Budgeting Office | Huron | Complete | 2011-08-29 | 2011-08-30 | bar: 2011-08-29
D. Develop High level terms of Pilot Project | Larry Fodor | Huron | Complete | 2011-08-29 | 2011-09-22 | bar: 2011-08-29 to 2011-09-19
E. Develop Communications Materials for Deans (PPT) | Larry Fodor | Huron | Complete | 2011-09-07 | 2011-09-21 | bar: 2011-09-05 to 2011-09-19
F. Communicate Pilot Project to Deans | Larry Fodor | Huron | Complete | 2011-09-22 | 2011-09-22 | bar: 2011-09-19
G. Implement Pilot Project | Larry Fodor | Huron | Complete | 2011-10-01 | 2011-10-01 | bar: 2011-10-03
H. Project Planning | Ricardo Kisner | Huron | Complete | 2011-09-23 | TBD
I. Benchmarking | Ricardo Kisner | Huron | Complete | 2011-09-27 | TBD
J. Rates Analysis | Ricardo Kisner | Huron | Underway | 2011-09-27 | TBD
K. Organizational Structure | Ricardo Kisner | Huron | Underway | TBD | TBD
L. Fiscal | Ricardo Kisner | Huron | Underway | TBD | TBD
M. Technology | Ricardo Kisner | Huron | Underway | 2011-10-05 | TBD
N. Communications | Ricardo Kisner | Huron | Underway | TBD | TBD
VI. Create a GIRF customer brochure (to be included in the Guide to Services instead of developing a 2nd document) | Huron | FP&M | Underway | - | -
A. Meet with WSU Marketing to assess potential for collaboration | Huron | FP&M | Complete | 2011-08-22 | 2011-09-02 | bar: 2011-08-22 to 2011-08-29
B. Finalize customer-funded work process map (w/ Ricardo Kisner) - confirm with Ricardo | Huron | FP&M | Underway | 2011-10-15 | 2011-11-15 | bar: 2011-10-17 to 2011-11-14
C. Collect samples from other universities and/or WSU areas | Huron | FP&M | Complete | 2011-10-15 | 2011-11-15 | bar: 2011-10-17 to 2011-11-14
D. Develop customer brochure | Huron | FP&M | Not Started | 2011-11-15 | 2011-12-31 | bar: 2011-11-14 to 2011-12-26
E. Send to Marketing for final review | Huron | FP&M | Not Started | 2012-01-01 | 2012-01-15 | bar: 2012-01-02 to 2012-01-09
F. Publish and begin utilizing customer brochure | FP&M | - | Not Started | 2012-01-16 | 2012-01-16 | bar: 2012-01-16
VII. Establish a Guide to Services | Huron | Megan Etue | Underway | - | -
A. Obtain example Guide to Services as templates | Huron | Megan Etue | Complete | 2011-10-24 | 2011-11-15 | bar: 2011-10-24 to 2011-11-14
B. Identify desired sections for the Guide | Huron | Megan Etue | Complete | 2011-11-15 | 2011-11-30 | bar: 2011-11-14 to 2011-11-28
C. Identify area owners for each section | Huron | Megan Etue | Complete | 2011-11-15 | 2011-11-30 | bar: 2011-11-14 to 2011-11-28
D. Meet with area owners to document processes, what is/is not covered in each area, and customer steps | Huron | Megan Etue | Complete | 2011-12-01 | 2011-12-30 | bar: 2011-11-28 to 2011-12-26
E. Meet with select customers to identify what processes customers need to better understand | Huron | Megan Etue | Complete | 2011-12-01 | 2011-12-30 | bar: 2011-11-28 to 2011-12-26
F. Write guide | Huron | Megan Etue | Complete | 2012-01-02 | 2012-01-09 | bar: 2012-01-02 to 2012-01-09
G. Vet guide with FP&M directors and AVP | Huron | Megan Etue | Underway | 2012-01-16 | 2012-01-16 | bar: 2012-01-16
H. Draft sent to Rick Nork for Review | Megan Etue | FP&M | Not Started | 2012-01-23 | 2012-02-06 | bar: 2012-01-23 to 2012-02-06
I. Draft sent to Marketing for design work | Megan Etue | FP&M | Not Started | 2012-01-23 | 2012-02-06 | bar: 2012-01-23 to 2012-02-06
J. Develop marketing plan for Guide launch | Megan Etue | FP&M | Complete | 2012-02-06 | 2012-02-06 | bar: 2012-02-06
K. Vet final draft with select customer focus group | Megan Etue | FP&M | Not Started | 2012-02-06 | 2012-02-13 | bar: 2012-02-06 to 2012-02-13
L. Vet final draft with Steering Committee | Megan Etue | FP&M | Not Started | 2012-02-06 | 2012-02-13 | bar: 2012-02-06 to 2012-02-13
M. Approve final draft for printing | Megan Etue | FP&M | Not Started | 2012-02-20 | 2012-02-20 | bar: 2012-02-20
N. Publish Guide | Megan Etue | FP&M | Not Started | 2012-02-27 | 2012-03-05 | bar: 2012-02-27 to 2012-03-05
O. Launch marketing strategy | Megan Etue | FP&M | Not Started | 2012-03-05 | 2012-03-05 | bar: 2012-03-05
VIII. Implement Customer Survey |  |  | Complete | - | -
A. Analyze TMA system survey capabilities | Jason Sepanak | Huron | Complete | 2011-10-15 | 2011-11-15 | bar: 2011-10-17 to 2011-11-14
B. Determine survey questions | Huron | Megan Etue | Complete | 2011-10-30 | 2011-11-15 | bar: 2011-10-31 to 2011-11-14
C. Determine roll-out plan - which group, phased, etc. | Huron | Megan Etue | Complete | 2011-10-30 | 2011-11-15 | bar: 2011-10-31 to 2011-11-14
D. Determine plan for analyzing and reporting results | Huron | Megan Etue | Complete | 2012-11-14 | 2011-12-15 | bar: 2011-11-14 to 2011-12-12
E. Plan for reporting back to the community | Huron | Megan Etue | Complete | 2012-11-14 | 2011-12-15 | bar: 2011-11-14 to 2011-12-12
F. Develop marketing plan/messaging for Survey Launch | Huron | Megan Etue | Complete | 2012-11-14 | 2011-12-15 | bar: 2011-11-14 to 2011-12-12
G. Launch Survey DELAYED DUE TO ISSUES WITH TECHNICAL REQUIREMENTS IN TMA. NEW TARGET DATE: 1/23 | Huron | Megan Etue | Complete | 2012-01-23 | 2012-01-23 | bar: 2012-01-16
IX. Update Campus Design Standards | Huron | FP&M | Underway | - | -
A. Meet with Mike C. and Randy P. to nominate Update Team | Huron | Mike Colburn/Randy Paquette | Complete | 2011-11-21 | 2011-11-23 | bar: 2011-11-21
B. Meet with group to discuss charge & expected completion date | Mike Colburn/Randy Paquette | Huron | Complete | 2011-11-21 | 2011-11-23 | bar: 2011-11-21
C. Establish process & system for updating standards | Huron | Mike Colburn/Randy Paquette | Complete | 2011-11-21 | 2011-11-23 | bar: 2011-11-21
D. Begin updating standards | Randy Paquette | FP&M | Underway | 2012-11-23 | 2012-01-31 | bar: 2011-11-21 to 2012-01-30
E. Provide draft of updated standards to stakeholders for comments (Faciltiies Operations Group, Energy Mgmt, OEHS, Office of Risk Mgmt, Sustainability Office) | Randy Paquette | FP&M | Not Started | 2012-01-31 | 2012-02-29 | bar: 2012-01-30 to 2012-02-27
F. Finalize Draft | Randy Paquette | FP&M | Not Started | 2012-03-01 | 2012-03-31 | bar: 2012-03-05 to 2012-03-26
G. Publish updated Standards to the web | Huron | FP&M | Not Started | 2012-04-01 | 2012-04-01 | bar: 2012-04-02
X. Grounds Assessment - Quality, Staffing, Effectiveness | Huron | FP&M | Complete | 2011-11-01 | 2011-11-30 | bar: 2011-11-07 to 2011-11-28
XI. Negotiate rates where possible (irrigation water and cooling tower makeup water exempted from campus sewer charges) | FP&M | Huron | Underway | - | -
A. Meet with WSU Gov't Affairs office to review the request DELAYED DUE TO LACK OF RESPONSE FROM OGCA | Larry Fodor | Huron | Complete | 2012-01-01 | 2012-01-01 | bar: 2012-01-02
B. Document water currently used for irrigation/cooling tower | Larry Fodor | Mike Colburn | Underway | 2012-01-01 | 2012-01-20 | bar: 2012-01-09 to 2012-01-23
C. Initiate discussions with water/sewer utility provider | Larry Fodor | Huron | Underway | 2012-01-20 | 2012-01-20 | bar: 2012-01-23
D. Negotiate removal of irrigation and make up water from campus sewer rates | Larry Fodor | Huron | Not Started | 2012-01-20 | 2012-01-31 | bar: 2012-01-23 to 2012-01-30

## Responsibilities Matrix Rev.
|  | Roles |  |  | Urgency
HURON RECOMMENDATIONS - IMPLEMENTATION RESPONSIBILITIES - DRAFT |  | Huron | FP&M | Other WSU Units | 1, 2, 3 |  |  | ? = bob checked, need to understand how he envisions us being able to help
Organizational Alignment - Custodial | [5 empty] | Role Key
| Redefine current custodial zone boundaries - geographically contiguous | A | P |  | 1 | P | Primary
| Redefine current custodial responsibilities - balanced supervisor responsibilities | A | P |  | 1 | S | Secondary
| Move majority of daytime custodial shifts to PM shifts to allow for fewer distractions | A | P |  | 1 | A | Advisory
| Maintain a special projects team (evening shift) to address issues (e.g. floor stripping, waxing, buffing) | A | P |  | 1
| Set supplies budgets and raise purchasing limits for supervisors | A | P |  | 3 | Urgency Key
Assist with audit process development?
Organizational Alignment - Engineering | [5 empty] | 1 | High Priority
| Redefine engineering organziational structure and responsibility centers | A | P |  | 1 | 2 | Medium Priority
| Define roles and responsibilities between trades and engineers | A | P |  | 2 | 3 | Long-term
| Add a PM shift to engineering focused on preventive maintenance, and add trades in time if needed and if possible | A | P |  | 1
| Set supplies budgets and raise purchasing limits for supervisors | A | P |  | 3
Job Training and Leadership Development
| Perform a training needs assessment |  | P |  | 3 |  |  | Help Megan review/get these rolls filled out - with HR's help -- we could try to sit down with leadership staff and make a list of what the training needs are, set priorities | Bob and I should offer to sit down and ask the right questions, Megan could come with us -- start w area leaders, Randy, Mike etc. (Jim's direct reports)
| Set internal performance expectations and standards |  | P |  | 2 |  |  | starting to establish expectations for staff in dept, in relation to KPIs… -- org needs to have performance expectations and standards established in each area -- | Get an update from Ricardo on where they are with KPIs, that's the starting point for setting expectations… can we take one area and use that as an example to set performance expectations -- maybe custodial… -- offering to assist Ricardo with developing KPIs
| Ensure adequate training is provided to staff |  | P |  | 3 |  |  | Can use free training available… after we know the needs, explore what free options exist… -- after the assessment
Technology & TMA
| Assess current and build TMA capabilities | S | P |  | 1
| Review task codes, prioritize preventive maintenance schedules and populate the TMA system | S | P |  | 1
| Mobile TMA pilot | S | P |  | 1
| Train staff |  | P |  | 1
| Mandate TMA's use across FP&M |  | P |  | 1 |  |  | we need to have a conversation with Jim… Mike C is working on the pilot buildings but we need a top down declaration that says we're going to start using this as a tool…we need everyone to be using it -- be clear that Jim starts getting on a soap box about this
| Replace pager system | S | P |  | 1 |  |  | we need to pin down a vision for technology for the organization, we've heard this loud and clear,… understand mike's vision about this… and when is he planning to do this -- put a field communication plan in place.. -- Our role is to facilitiate that this is a reported problem and we want to help mike put the strategy together
| Bring work order assignment process fully online | S | P |  | 1 |  |  | we need to understand what the flow is today vs. when we did our assessment… looking at the process and seeking opportunitites for improvement - fine if limited to the 3 pilot buildings, start with Angela… to understand if changes have been put in place...
Transparency and Trust
| Create a GIRF customer brochure | S | P | S-Marketing | 1 |  |  | Work with Ricardo and Megan to document the GIRF process and write this up, even if it will change with JOC - does Megan have Emory's? | talk to rick pettit -- describing the GIRF process as it is today and will JOC replace the GIRF process -- confirm with him that they can do small projects as well, should have a contractor on campus -- and if he concurs with that | maybe we need to help people understand the process… | revisit with megan the process ---
| Give customers visibility into budgeting | S | P | S-Budgeting | 1
| Establish a Guide to Services and Service Level Agreements | A | P |  | 1 |  |  | Megan has a draft; work w/ her to identify the are owners, sit with them to sketch out the processes (rather than assign them to write it) | start with 3 pilot buildings… sending out to them first
| Set KPIs | A | P |  | 2 |  |  | Ricardo is doing this… we need to add input
| Perform regular customer surveys | A | P | S-Multiple | 2 |  |  | Start in Oct, full roll out in November
DCS Process Improvements
| Job Order Contracting (JOC) | P | S |  | 1
| Perform Construction Audits | A | P |  | 2 |  |  | Bob wants to meet with the internal audit people and understand what that was… Touch base with Andrew and understand what they're doing
| CM at Risk | A | P |  | 1
| Update Campus Design Standards | A | P |  | 1 |  |  | Bob could work with assigned representatives from various depts assigned by Mike and Randy to get a draft going? -- several examples of these, Randy should put together a group of Project managers, appoint a few people from Mike… -- Bob can walk throuhg and make changes to it...
| Bring Rigor to Change Order Record-Keeping | A | P |  | 1 |  |  | ?
| Raise signatory authority levels for AVP FP&M | P | S | S-Board | 1
Energy Management
| Implement Performance Contracting | P | S |  | 1
| Sub-metering - to enable unit level-budgeting, sub-meter each building | P | S |  | 1 |  |  | Work with Larry to clearly map which buildings are not yet sub-metered, work with Siemens to make sure they look at this, we need a plan for submetering to be developed espec with regards to pilot roll out
| Shift utilities budgeting to units | S | P | S-Budgeting | 1
| Implement robust marketing plan | A | P | S-Marketing | 2 |  |  | Part of pilot -- work with sustainability guy to meet with individual deans and identify areas for development to underpin the larger efforts --- do we also need to meet with the marketing dept?
| Create a central monitoring and control station | A | P |  | 1 |  |  | ?
| Develop a plan to consolidate distributed boilers and chillers (long-term strategy) | A | P |  | 3
| Establish a Long-Term Energy Conservation Strategy | A | P |  | 1 |  |  | Bob works with Larry - maybe we need to draft the plan
| Establish a plan for LEED Certification | A | P |  | 3 |  |  | ?
| Negotiate rates where possible (irrigation water and cooling tower makeup water exempted from campus sewer charges) | S | P |  | 3 |  |  | Larry and Bob to talk about this
Darryl -- Megan, me and Bob
Grounds assessment
Look at those 2 processes/projects to see if there isnt a better way to do this?
may be a site visit… -- to take a day or so…
Set up a conversation with Jim for next week --
cust survye
1) systems analysis
2) decide on questions - and group of people
3) who to roll out to -- phased or not
4) reporting -- back…
5) message for

## Utilities Pilot Detail
HIGH-LEVEL PROJECT WORK PLAN
Huron Consulting's Recommendation: |  | SHIFT UTILITIES BUDGET TO UNITS |  |  | PROJECT CHAMPION | Larry Fodor, Director Utilities and Energy Management
Remaining Project Phases
Phase I Project: |  | Implement Pilot Utility Project with Law, Engineering, and Nursing |  |  | Phase 2 - Representative selection of buildings
Project Objective: |  | Successfully implement an "off-the-books" transfer of utilities budgets and costs to the three pilot schools while formulating the approach for the eventual university-wide roll-out |  |  | Phase 3 - Complete Roll-out
Project Implications
Task # | Primary Area | Task | Primary Responsibility | Secondary Responsibility | Status | Start | End | Phase I | Phase II | Phase III
1 |  | PROJECT PLANNING
1.1 | Project Planning | Develop project charter |  |  | Not Started |  |  | X
1.2 | Project Planning | Develop detailed project workplan |  |  | In Process | 2011-09-28 |  | X
1.3 | Project Planning | Establish project team |  |  | In Process | 2011-09-23 |  | X
1.4 | Project Planning | Establish team meeting guidelines |  |  | In Process | 2011-09-27 |  | X
1.5 | Project Planning | Define appropriate timelines for the three project phases (initial pilot, second pilot, and complete roll-out) |  |  | Not Started |  |  | X | X | X
2 |  | BENCHMARKING
2.1 | Benchmarking | Conduct initial meeting with Emory University |  |  | Completed | 2011-09-27 | 2011-09-27 | X | X | X
2.2 | Benchmarking | Set up meeting with University of Michigan to discuss its allocation of utilities costs to the units |  |  | Not Started |  |  | X | X | X
2.3 | Benchmarking | Set up follow up meeting with Emory University for further discussions, if necessary |  |  | Not Started |  |  | X | X | X
3 |  | RATE ANALYSIS
3.1 | Rates Analysis | Review Emory University's rate calculations and assignment of fixed costs |  |  | In Process | 2011-09-27 |  | X | X | X
3.2 | Rates Analysis | Develop base usage and rates for the initial pilot project locations |  |  | Completed |  |  | X
3.3 | Rates Analysis | Define space categories, calculate rates for the pilot, determine the "off books" budgets. |  |  | Completed? | by Larry Fodor |  | X
4 |  | ORGANIZATIONAL STRUCTURE
4.1 | Organizational Structure | Recommend the organizational structure and staffing for Wayne's utility management unit |  |  | Not Started |  |  |  |  | X
4.2 | Organizational Structure | Develop and recommend options for incentives for schools and units |  |  | Not Started |  |  |  |  | X
4.3 | Organizational Structure | Identify and recommend phase 2 buildings which would be representative of all categories of buildings within the University |  |  | Not Started |  |  |  | X | X
5 |  | FISCAL
5.1 | Fiscal | Develop pilot budget for the three schools |  |  | Not Started |  |  |  | X
5.2 | Fiscal | Begin budget development process for phase 2 and phase 3 |  |  | Not Started |  |  |  | X | X
5.3 | Fiscal | Determine whether Phase 2 projects are "on" or "off" the books |  |  | Not Started |  |  |  |  | X
5.4 | Fiscal | Define the accounting and budgeting methods for "on" and "off" the books. |  |  | Not Started |  |  | X | X | X
6 |  | TECHNOLOGY
6.1 | Technology | Analyze the feasibility of using TMA and other in-house systems to determine capabilities for each of the three project phases |  |  | Not Started |  |  | X | X | X
7 |  | COMMUNCATIONS
7.1 | Communications | Convene information and project status meetings with customers (Law, Engineering, and Nursing) after completion of each primary area (e.g., planning, benchmarking, rate analysis, organizational, fiscal, and technology). |  |  | Not Started |  |  | X
7.2 | Communications | Develop communications and change management plan |  |  | Not Started |  |  | X
7.3 | Communications | Develop promotional materials |  |  | Not Started |  |  | X

## TMA Pilot Detail
FP&M- TMA- PILOT PROGRAM(COHN, LAW, ENGINEERING)
No. | Tasks | Activities | Sub-Activities | Details | Primary Owner | Secondary Owner | Status | Start Date | Target End Date
1 | DEVELOP WORK ORDER MANAGEMENT PROCESS |  |  |  | M.Colburn | P.Panhale
| 1.1. | Facilities Operations |  |  | M.Colburn | P.Panhale
|  | 1.1.1. | Develop "Open/Edit/Close "Work order process |  | M.Colburn | P.Panhale |  | 2011-10-15 | 2011-11-01
|  | 1.1.2. | Develop transfer and follow up process with other departments |  | M.Colburn | P.Panhale |  | 2011-10-15 | 2011-11-01
|  | 1.1.3. | Develop formal reporting structure |  | M.Colburn | P.Panhale |  | 2011-11-01 | 2011-12-01
| 1.2. | Service Center |  |  | M.Colburn | A. Strickland
|  | 1.2.1. | Develop "Open/Edit/Close "Work order process |  | M.Colburn | A. Strickland |  | 2011-10-15 | 2011-11-08
|  | 1.2.2. | Assign work orders to specific department |  | M.Colburn | A. Strickland |  | 2011-11-01 | 2011-11-08
|  | 1.2.3. | Develop communication/notification process |  | M.Colburn | A. Strickland |  | 2011-11-01 | 2011-12-08
2 | DEVELOP PREVENTIVE MAINTENANCE WORK ORDER MANAGEMENT PROCESS |  |  |  | M.Colburn | P.Panhale
| 2.1. | Facilities Operations |  |  | M.Colburn | P.Panhale
|  | 2.1.1. | Review and update P.M. Task codes and schedules |  | M.Colburn | P.Panhale |  | 2011-12-01 | 2012-03-01
|  | 2.1.2. | Create ,modify Schedules for pilot buildings |  | M.Colburn | P.Panhale |  | 2011-12-15 | 2012-03-01
|  | 2.1.3. | Assign P.M.'s to designated shift and engineer |  | M.Colburn | P.Panhale |  | 2011-12-15 | 2012-03-01
|  | 2.1.4. | Develop process for distributing /scheduling P.M.'s |  | M.Colburn | P.Panhale |  | 2011-12-20 | 2012-03-01
|  | 2.1.5. | Update P.M. timeline Process |  | M.Colburn | P.Panhale |  | 2012-01-03 | 2012-03-01
3 | DEVELOP TMA INVENTORY CONTROL PROCESS |  |  |  | M.Colburn | A. Strickland
| 3.1. | Equipment's/parts/chemicals |  |  | M.Colburn | A. Strickland
|  | 3.1.1. | Review and update Equipment Inventory |  | M.Colburn | A. Strickland |  | 2011-12-01 | 2012-02-01
|  | 3.1.2. | Develop recommended spare parts list |  | M.Colburn | A. Strickland |  | 2011-12-01 | 2012-02-01
|  | 3.1.3. | Develop required chemicals list |  | M.Colburn | A. Strickland |  | 2011-12-01 | 2012-02-01
| 3.2 | Keys |  |  | M.Colburn | M.Pines
|  | 3.2.1. | Develop master key list for pilot buildings |  | M.Colburn | M.Pines |  | 2011-11-01 | 2011-12-15
|  | 3.2.2. | Update Database for key inventory control |  | M.Colburn | M.Pines |  | 2011-12-20 | 2012-02-01
|  | 3.2.3. | Develop standard process for key requests |  | M.Colburn | M.Pines |  | 2011-12-20 | 2012-02-01
| 3.3. | Invoices |  |  | M.Colburn | A. Strickland
|  | 3.3.1. | Develop improved invoice process for TMA project |  | M.Colburn | A. Strickland |  | 2011-11-01 | 2012-01-02
4 | DEVELOP IT INTERFACE PROCESS FOR TMA |  |  |  | M.Colburn | J. Sepanak
| 4.1. | Authorization Process |  |  | M.Colburn | J. Sepanak
|  | 4.1.1. | Develop standard request form for all employees |  | M.Colburn | J. Sepanak |  | 2011-11-01 | 2012-01-02
|  | 4.1.2. | Create user groups and authorize specific authority levels |  | M.Colburn | J. Sepanak |  | 2011-11-05 | 2012-01-02
|  |  | 4.1.2.1 | IT-Administrator | M.Colburn | J. Sepanak
|  |  | 4.1.2.2 | IT-Assistant | M.Colburn | J. Sepanak
|  |  | 4.1.2.3 | FO-Senior Director | M.Colburn | J. Sepanak
|  |  | 4.1.2.4 | FO-Director, Asso. Director (Engineering, Custodial ,Trades, Grounds) | M.Colburn | J. Sepanak
|  |  | 4.1.2.5 | FO-Assistants | M.Colburn | J. Sepanak
|  |  | 4.1.2.6 | FO-Engineering-Supervising Engineer | M.Colburn | J. Sepanak
|  |  | 4.1.2.7 | FO-Engineering- Engineer | M.Colburn | J. Sepanak
|  |  | 4.1.2.8 | FO-Engineering- Control Center Engineer | M.Colburn | J. Sepanak
|  |  | 4.1.2.9 | FO-Engineering-Project Manager | M.Colburn | J. Sepanak
|  |  | 4.1.2.10 | FO-Custodial-Supervisor | M.Colburn | J. Sepanak
|  |  | 4.1.2.11 | FO-Custodial-Custodial | M.Colburn | J. Sepanak
|  |  | 4.1.2.12 | FO-Trades-Team Leaders | M.Colburn | J. Sepanak
|  |  | 4.1.2.13 | FO-Trades-Trades | M.Colburn | J. Sepanak
|  |  | 4.1.2.14 | FO-Grounds-Supervisors | M.Colburn | J. Sepanak
|  |  | 4.1.2.15 | FO-Grounds-Groundskeeper | M.Colburn | J. Sepanak
| 4.2. | TMA Hardware Installation |  |  | M.Colburn | J. Sepanak
|  | 4.2.1. | Inventory equipment in pilot buildings |  | M.Colburn | J. Sepanak |  | 2011-11-01 | 2011-12-01
|  | 4.2.2. | Complete hardware installation as needed |  | M.Colburn | J. Sepanak |  | 2011-12-01 | 2012-01-02
| 4.3. | Develop TMA Software improvement process |  |  | M.Colburn | J. Sepanak
|  | 4.3.1. | Resolve TMA Users issues |  | M.Colburn | J. Sepanak |  | 2012-01-03 | 2012-03-01
5 | Develop plan to train employees in Facilities Operations group |  |  |  | M.Colburn | P.Panhale
| 5.1. | FO |  |  | M.Colburn | P.Panhale
|  | 5.1.1. | Engineering |  | M.Colburn | C.Dargin |  | 2011-11-01 | 2012-01-02
|  | 5.1.2. | Custodial |  | M.Colburn | D.Wrench |  | 2011-11-01 | 2012-01-02
|  | 5.1.3. | Trades |  | M.Colburn | D.kuffner |  | 2011-11-01 | 2012-01-02
|  | 5.1.4. | Grounds |  | M.Colburn | K.Bolt |  | 2011-11-01 | 2012-01-02
|  | 5.1.5. | Temporary employees |  | M.Colburn | D.Wrench |  | 2011-11-01 | 2012-01-02
|  | 5.1.6. | Assistants |  | M.Colburn | D.Wrench |  | 2011-11-01 | 2012-01-02
6 | Develop plan for Using Mobile TMA in pilot buildings |  |  |  | M.Colburn | J. Sepanak
| 6.1. | Procure Mobile TMA devices |  |  | M.Colburn | J. Sepanak |  | 2011-12-01 | 2012-02-01
| 6.2. | Distribute Mobile TMA Devices |  |  | M.Colburn | J. Sepanak |  | 2011-12-15 | 2012-03-01
| 6.3. | Train Engineers in Mobile TMA use |  |  | M.Colburn | J. Sepanak |  | 2011-12-20 | 2012-03-01
7 | Develop evaluation Tracking Methodology |  |  |  | M.Colburn
| 7.1. | Work order completion time for Low /medium/high/Emergency Status |  |  | M.Colburn | P.Panhale |  | 2011-12-01 | 2012-03-01
| 7.2. | PM Completion time for 30/60/90 days pass due date Status |  |  | M.Colburn | P.Panhale |  | 2011-12-15 | 2012-03-01
| 7.3 | Evaluate Mobile TMA Vs. Computer use |  |  | M.Colburn | P.Panhale |  | 2012-02-01 | 2012-03-01
|  | 7.3.1. | Develop close out process for Mobile TMA |  | M.Colburn | P.Panhale |  | 2012-11-15 | 2012-03-01
|  | 7.3.2. | Develop close out process for computer |  | M.Colburn | P.Panhale |  | 2012-11-15 | 2012-03-01
|  | 7.3.3. | Time to close on Mobile TMA and synchronize to computer Vs. to close on Computer |  | M.Colburn | J. Sepanak |  | 2011-12-01 | 2012-03-01
8 | Pilot Program result |  |  |  | M.Colburn | P.Panhale
| 8.1 | Develop measurements for pilot buildings TMA evaluation |  |  | M.Colburn | P.Panhale |  | 2011-12-01 | 2012-04-01
| 8.2. | Record evaluation status |  |  | M.Colburn | P.Panhale |  | 2012-01-03 | 2012-04-01
| 8.3 | Develop recommendation for improved process |  |  | M.Colburn | P.Panhale |  | 2012-02-15 | 2012-04-01

## Responsibilities Matrix
|  | Roles |  |  | Urgency
HURON RECOMMENDATIONS - IMPLEMENTATION RESPONSIBILITIES - DRAFT |  | Huron | FP&M | Other WSU Units | 1, 2, 3 |  |  | Notes
Organizational Alignment - Custodial | [5 empty] | Role Key
| Redefine current custodial zone boundaries - geographically contiguous | A | P |  | 1 | P | Primary | Custodial should be more involved than engineering
| Redefine current custodial responsibilities - balanced supervisor responsibilities | A | P |  | 1 | S | Secondary
| Move majority of daytime custodial shifts to PM shifts to allow for fewer distractions | A | P |  | 1 | A | Advisory
| Maintain a special projects team (evening shift) to address issues (e.g. floor stripping, waxing, buffing) | A | P |  | 1
| Set supplies budgets and raise purchasing limits for supervisors | A | P |  | 3 | Urgency Key |  | for this and above, there are some accounting challenges, Jim would like to do this as a later date
Organizational Alignment - Engineering | [5 empty] | 1 | High Priority
| Redefine engineering organziational structure and responsibility centers | A | P |  | 1 | 2 | Medium Priority | Jim feels that they're doing the best they can here with the new structure
| Define roles and responsibilities between trades and engineers | A | P |  | 2 | 3 | Long-term | Among challenges we'll face, budgets have been authorized for FY12, 29 positions being deleted, have to imlement this org structure, can post the positions -- have to hire 3 first class, a few seconds, the AD positions, will take some time to hire this - incl. the go between -- change to a 2 b/c will take more time to get that person hired, etc.
| Add a PM shift to engineering focused on preventive maintenance, and add trades in time if needed and if possible | A | P |  | 1 |  |  | Need more time to assess this w/ regards to the trades - have talked about this, might happen eventually, but not yet
| Set supplies budgets and raise purchasing limits for supervisors | A | P |  | 3 |  |  | for this and above, there are some accounting challenges, Jim would like to do this as a later date
Job Training and Leadership Development | [7 empty] | Build budget for APPA training, etc.; can OTL help?
| Perform a training needs assessment |  | P |  | 3 |  |  | they agree this is necessary, donald is working on this… megan is beg to work with donald today to work on charting the buildings scheduled for service over the various shifts, hopefully that will be done for us next week, after this is established, Jim wants custodial to work on developing this to be for SLAs
| Set internal performance expectations and standards |  | P |  | 2
| Ensure adequate training is provided to staff |  | P |  | 3 |  |  | in complete agreement that TMA is really important, among the top 3 initiatives they need to address, very concerned about the schedule… within the end of the month hope to get feedback about the use of this -- established an IT steering committee, Jims direct reports minus larry plus jason
Technology & TMA | [7 empty] | TMA is currently assessing usage and capabilities
| Assess current and build TMA capabilities | S | P |  | 1
| Review task codes, prioritize preventive maintenance schedules and populate the TMA system | S | P |  | 1 |  |  | Integrate cost accounting capability; Temps or students?
| Mobile TMA pilot | S | P |  | 1
| Train staff |  | P |  | 1 |  |  | Assess how vendor can help
| Mandate TMA's use across FP&M |  | P |  | 1
| Replace pager system | S | P |  | 1
| Bring work order assignment process fully online | S | P |  | 1 |  |  | Will be possible once TMA is fully in use
Transparency and Trust
| Create a GIRF customer brochure | S | P | S-Marketing | 1 |  |  | Huron provided sample to Megan Etue
| Give customers visibility into budgeting | S | P | S-Budgeting | 1 |  |  | Need to coordinate with budgeting recommendations
| Establish a Guide to Services and Service Level Agreements | A | P |  | 1
| Set KPIs | A | P |  | 2
| Perform regular customer surveys | A | P | S-Multiple | 2 |  |  | Megan reaching out to other units across campus who have implemented surveys
DCS Process Improvements
| Job Order Contracting (JOC) | P | S |  | 1
| Perform Construction Audits | A | P |  | 2 |  |  | Internal audit has begun this already
| CM at Risk | A | P |  | 1
| Update Campus Design Standards | A | P |  | 1
| Bring Rigor to Change Order Record-Keeping | A | P |  | 1
| Raise signatory authority levels for AVP FP&M | P | S | S-Board | 1 |  |  | Need Rick's buy in and Board approval; Huron can help write something up and get it approved
Energy Management
| Implement Performance Contracting | P | S |  | 1
| Sub-metering - to enable unit level-budgeting, sub-meter each building | P | S |  | 1 |  |  | Will be part of PC
| Shift utilities budgeting to units | S | P | S-Budgeting | 1 |  |  | Need to coordinate with budgeting recommendations
| Implement robust marketing plan | A | P | S-Marketing | 2 |  |  | Long-term strategy, for once PC allows sub-metering, see if we can work with Michael Wright on this
| Create a central monitoring and control station | A | P |  | 1 |  |  | Already working on this, but can be expanded with PC, integrated with technology approach
| Develop a plan to consolidate distributed boilers and chillers (long-term strategy) | A | P |  | 3
| Establish a Long-Term Energy Conservation Strategy | A | P |  | 1 |  |  | Huron can help FP&M with visioning and strategy creation
| Establish a plan for LEED Certification | A | P |  | 3
| Negotiate rates where possible (irrigation water and cooling tower makeup water exempted from campus sewer charges) | S | P |  | 3

## List of Recommendations
Enhance Productivity
Human Capital | Better management of FMLA and leave | Dedicate at least a portion of an FTE to actively manage leave requests and complement the services provided by FMLA Source (this is further addressed in Huron’s HR assessment) | TBD | 5 staff additions proposed - tent
| Zone realignment and level distribution of staff responsibilities | Redefine current custodial and engineering zone boundaries and responsibilities, define the currently vague roles and responsibilities between trades and engineers as this delineation is not currently understood by the workers themselves nor by the clients they serve | x
| Work shift re-alignment | Move majority of daytime custodial shifts to PM shifts to allow for fewer cleaning distractions; Add a PM shift to engineering and trades focused on preventive maintenance and a PM shift to custodial services to handle heavy cleaning; Delay planned reductions of custodial staff | x
| Job training and leadership development | Set internal expectations and standards; ensure adequate training is provided to custodial and all staff; provide managers with ongoing leadership development opportunities | x
| FTE adjustments | Strategic investments will allow FP&M to realize opportunities to decrease its FTE count; however, FP&M should allow for an increase in FTEs to support its administrative function | TBD
Technology | Fully utilize current technology | Focus on fully populating the TMA system, training staff, and mandating its use across FP&M, bringing paper processes online | x
| Implement new technology | Institute a pilot project to roll out Mobile TMA; replace antiquated pager system | x
Policies & Procedures | Enhance work order assignment process | Enhance the capabilities of the TMA system to bring the process fully online | x
| Improve DCS procedures, incl. GIRF | Implement job order contracting and strategic sourcing for outsourced construction work, create a GIRF customer brochure, hold contractors responsible through construction audits and use of CM at risk, update campus design standards, bring more rigor to internal record-keeping, raise signatory authority levels for AVP FP&M | x
| Redefine purchasing authority and limits | Set supplies budgets and raise purchasing limits for custodial, trades and engineering supervisors to help eliminate procurement delays | X
| Improve customer transparency and trust | Give customers visibility into budgeting, establish a Guide to Services and Service Level Agreements, set KPIs and perform regular customer surveys | X
| Implement Job Order Contracting and Strategic Sourcing, Develop a Customer Brochure for GIRF work | Implement job order contracting (JOC) and strategic sourcing with support from WSU’s purchasing office to enable less expensive and quicker construction procurement and delivery, development of a partner relationship based on work performance, and standard pricing and specifications via a published unit price book. Job order contracting is expected to save up to 10% in design and engineering costs. Define the options available (Just do it, etc.), the steps involved, the criteria FP&M uses to prioritize requests, and the process to refund unused customer money in a timely fashion. | x
| Perform Construction Audits | WSU’s Office of Internal Audit should perform construction audits on all new major construction projects; external auditors may be used if necessary. Continue to ensure that language is included in contracts to allow for such audits to take place. Experience has shown that audits yield savings in excess of the audit cost itself. | x
| Increase Use of the Construction Manager-at-Risk Project Delivery Method (CM-at-Risk) | WSU should increase the use of the CM-at-Risk project delivery method for capital and large GIRF projects. CM-at-Risk requires the contractor to provide the university with a guaranteed maximum price for all costs associated with design, construction, and delivery of the project—this places the onus to control costs on the contractor rather than the university. | x
| Update Campus Design Standards | Update the campus design standards and put a process in place to ensure they are updated annually. Make certain the engineers’ and trades’ preferences on the standards are regularly sought and incorporated in each update cycle. | x
| Bring Rigor to Change Order Record-Keeping | DCS needs to bring more rigor to the processes they use to record cost increases and schedule impacts resulting from scope creep initiated by client changes. Client changes should be handled as a change order to the project where the client agrees, as indicated by their signature approval, to cost additions, schedule changes and any other impacts or risks that may be indicated. | x
| Increase Signatory Authority for AVP FP&M | While the authority of the AVP of FP&M was recently revised, Huron recommends a further increase to this position’s delegated signature authority on all construction contracts, change orders and professional services contracts to $250K (from $100K for construction contracts, N/A for design contracts). | x
§Provide for sub-metering: As a key enabler for unit level-budgeting, each building should be separately metered, like a home, to accurately attribute usage to the appropriate owner.
§Shift utility budgeting responsibilities: Better budgeting provides Deans and Directors with a detailed understanding of their department’s energy usage and incentivizes them to decrease consumption by allowing the department to reabsorb savings realized through conservation measures.
§Implement a robust marketing plan: FP&M, in concert with WSU’s marketing department, should introduce a comprehensive campaign focused on changing WSU’s attitude and behavior towards energy consumption. Such a campaign will help students, professors, and staff understand the consequences of unnecessary energy usage and provide examples of ways they can impact WSU’s collective goal of reducing energy consumption.
§Performance contracting: Establish a performance contract with a major utility infrastructure vendor. This will allow the university to finance much needed energy infrastructure improvements at little to no upfront cost.
§Create a central monitoring and control station: By digitizing WSU’s energy producing infrastructure and tying it all into a central unit, FP&M can decrease its overall consumption by monitoring and controlling energy usage from a central control room, reducing its need for such a large force of engineers.
§Implement system shutdowns during non-peak times and adjust building temperatures: WSU should commence systematic shutdowns of non-critical energy systems during evening hours and weekends. Thermostats should be digitized and set to a standard, efficient, yet comfortable temperature during the day.
§Consolidate distributed boilers and chillers: Boilers and chillers are widely distributed on campus, requiring a multitude of engineers to operate, maintain, and repair the units. WSU should begin distributing steam and AC according to a district concept by consolidating units into neighboring plants as they end their useful lives.
§Set achievable goals and make them public: To generate momentum behind WSU’s energy plan, campus leadership should set a public goal of reducing specific levels of consumption by a certain date and update the campus regularly on the progress of the campaign. Milestones should be publicly celebrated and units rewarded for any contributions made towards reaching these milestones.
§Establish a plan for LEED Certification: A plan should be set in motion to ensure any major capital projects or renovations are constructed according to green building practices to ensure they are as efficient as possible; the Board of Governors should require that any capital project moving forward attain a LEED Rating of “Silver” or higher.
§Negotiate rates where possible: Negotiate with the City to have the irrigation water and cooling tower makeup water exempted from campus sewer charges.

## Lists
Workplan order
| Huron Role | Priority
Performance contracting incl. sub-metering | P | 1
JOC | P | 1
AVP FP&M Signatory Authority | P | 1
Technology & TMA | S | 1
Transparency - GIRF brochure | S | 1
Transparency - budgeting | S | 1
Utilities budgeting | S | 1
Energy strategy | S | 1
Monitoring and control center | S | 2
Negotiate rates (water) | S | 3
Owners
Huron
FP&M
-
Dara Moses
Bob Hascall
Jim Sears
Megan Etue
Larry Fodor
Larry Fodor/ Jim Sears
Randy Paquette
Mike Colburn
Mike Colburn/Randy Paquette
Larry Fodor/Daryl Pierson
Piyush Panhale
Angela Strickland
Mike Pines
Jason Sepanak
Ricardo Kisner
Rick Nork
Budgeting Office
Marketing Office
Status
Not Started
Underway
Delayed
Complete

## TASKS TAKEN OFF
HURON / FP&M IMPLEMENTATION WORKPLAN - DRAFT | [5 empty] | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
[6 empty] | 2011-08-01 | 2011-08-08 | 2011-08-15 | 2011-08-22 | 2011-08-29 | 2011-09-05 | 2011-09-12 | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2011-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02
Steering Committee Meeting | Will likely taper to bi-weekly meetings | [6 empty] | 2011-08-16 | 2011-08-23 | 2011-08-30 | 2011-09-06 | 2011-09-13 | 2011-09-20 | 2011-09-27 | 2011-10-04 | 2011-10-11 | 2011-10-18 | 2011-10-25 | 2011-11-01 | 2011-11-08 | 2011-11-15 | 2011-11-22 | 2011-11-29 | 2011-12-06 | 2011-12-13 | 2011-12-20 | 2011-12-27 | 2012-01-03 | 2012-01-10 | 2012-01-17 | 2012-01-24 | 2012-01-31 | 2012-02-07 | 2012-02-14 | 2012-02-21 | 2012-02-28 | 2012-03-06 | 2012-03-13 | 2012-03-20 | 2012-03-27 | 2012-04-03
Board of Governors Meeting | http://bog.wayne.edu/meetings/index.php | [6 empty] | 2011-09-20: 2011-09-21; 2011-12-06: 2011-12-07
Tasks/Activities | Primary Owner | Secondary Owner | Status | Start | End
IV. Raise signatory authority levels for AVP FP&M | Huron | FP&M | Not Started | - | -
A. Review Huron recommendation with Rick Nork & gain sign-off | Huron | Jim Sears | Not Started | 2011-08-15 | 2011-08-26 | bar: 2011-08-16 to 2011-08-23
B. Develop revised policy language | Huron | Jim Sears | Not Started | 2011-08-29 | 2011-09-16 | bar: 2011-08-30 to 2011-09-13
C. Present proposal to Board of Directors & gain sign-off | Rick Nork | Jim Sears | Not Started | 2011-09-21 | 2011-09-21 | bar: 2011-09-20
D. Implement policy revision | Huron | Jim Sears | Not Started | 2011-09-26 | 2011-10-14 | bar: 2011-09-27 to 2011-10-11
V. Technology & TMA - timeline TBD | FP&M | Huron | Underway | - | -
A. Initial conversations with TMA representatives | FP&M | Huron | Underway | 2011-08-05 | 2011-08-26 | x | x | bar: 2011-08-16 to 2011-08-23
B. Assessment of database and evaluation of current module use | FP&M | Huron | Underway | 2011-08-01 | 2011-09-02 | x | x | bar: 2011-08-16 to 2011-08-30
C. Evaluate TMA's plan to enhance product utilization | FP&M | Huron | Not Started | 2011-09-05 | 2011-09-16 | bar: 2011-09-06 to 2011-09-13
D. Fully populate TMA database | FP&M | Huron | Not Started | 2011-09-19 | 2011-10-14 | bar: 2011-09-20 to 2011-10-11
E. Train staff on full TMA utilization, incl. work order assignment process | FP&M | - | Not Started | 2011-10-10 | 2011-11-04 | bar: 2011-10-11 to 2011-11-01
F. Mobile TMA Pilot | Huron | FP&M | Not Started | - | -
1. Evaluate options - cellular vs. mobile, replacement of pagers | FP&M | Huron | Not Started | 2011-09-05 | 2011-09-16 | bar: 2011-09-06 to 2011-09-13
2. Purchase needed equipment | FP&M | Huron | Not Started | 2011-09-19 | 2011-10-14 | bar: 2011-09-20 to 2011-10-11
3. Develop evaluation tracking methodology | FP&M | Huron | Not Started | 2011-10-03 | 2011-10-28 | bar: 2011-10-04 to 2011-10-25
4. Train staff | FP&M | Huron | Not Started | 2011-10-10 | 2011-11-04 | bar: 2011-10-11 to 2011-11-01
5. Implement Pilot | FP&M | Huron | Not Started | 2011-11-07 | 2011-12-02 | bar: 2011-11-08 to 2011-11-29
6. Evaluate Pilot | FP&M | Huron | Not Started | 2011-12-05 | 2011-12-30 | bar: 2011-12-06 to 2011-12-27
VII. Give Customers Visibility into Budgeting | FP&M | Huron | Underway | - | -
A. Review Huron recommendation with Rick Nork & gain sign-off | Jim Sears | Huron | Complete | 2011-08-15 | 2011-08-26 | bar: 2011-08-16 to 2011-08-23
B. Meet with Budgeting Office to discuss implementation | Jim Sears | Huron | Complete | 2011-08-22 | 2011-08-26 | bar: 2011-08-23
C. Gain Provost Sign off | Budgeting Office | Huron | Complete | 2011-08-29 | 2011-08-30 | bar: 2011-08-30
D. Develop Pilot Project - incl. Terms/Incentives | Mike Colburn | Huron | Underway | 2011-08-29 | 2011-09-22 | bar: 2011-08-30 to 2011-09-20
E. Develop Communications Materials for Deans (PPT) | Mike Colburn | Huron | Underway | 2011-09-07 | 2011-09-21 | bar: 2011-09-06 to 2011-09-20
F. Communicate Pilot Project to Deans | Mike Colburn | Huron | Not Started | 2011-09-22 | 2011-09-22 | bar: 2011-09-20
G. Coordinate billing processes between Angie and Celeste | Mike Colburn | Huron | Not Started | 2011-10-01 | 2011-11-15 | bar: 2011-09-27 to 2011-11-15
H. Implement Pilot Project | Mike Colburn | Huron | Not Started | 2011-10-01 | 2011-10-01 | bar: 2011-10-04
VIII. Shift utilities budgeting to units | FP&M | Huron | Not Started | - | -
A. Review Huron recommendation with Rick Nork & gain sign-off | Jim Sears | Huron | Complete | 2011-08-15 | 2011-08-26 | bar: 2011-08-16 to 2011-08-23
B. Meet with Budgeting Office to discuss implementation | Jim Sears | Huron | Complete | 2011-08-22 | 2011-08-26 | bar: 2011-08-23
C. Gain Provost Sign off | Budgeting Office | Huron | Complete | 2011-08-29 | 2011-08-30 | bar: 2011-08-30
D. Develop Pilot Project - incl. Terms/Incentives | Larry Fodor | Huron | Underway | 2011-08-29 | 2011-09-22 | bar: 2011-08-30 to 2011-09-20
E. Develop Communications Materials for Deans (PPT) | Larry Fodor | Huron | Underway | 2011-09-07 | 2011-09-21 | bar: 2011-09-06 to 2011-09-20
F. Communicate Pilot Project to Deans | Larry Fodor | Huron | Not Started | 2011-09-22 | 2011-09-22 | bar: 2011-09-20
G. Coordinate billing processes between Angie and Celeste | Larry Fodor | Huron | Not Started | 2011-10-01 | 2011-11-15 | bar: 2011-09-27 to 2011-11-15
H. Implement Pilot Project | Larry Fodor | Huron | Not Started | 2011-10-01 | 2011-10-01 | bar: 2011-10-04